## Sheet1
[17 empty] | Nov 2015 Status | Jan 25 2016 Status | Oct 7, 2016 Status
[11 empty] | with scope in April 2014 | Run267 | Run304 | with scope in July 2014 |  | suggested action
wires:
[9 empty] | S1 | FDC1,C1,S1-24 | ??? |  |  | to be tested |  |  | Fine | Fine
| FDC1 | U2-8BOT | slot7 | ch.45 (top connector #21) | no signal | TDCROC4 | slot4 | ch.45 | S22 | FDC1,C6,S1-24 | bad 3M |  |  | to be tested |  | bad 3M very certain!!! Fix it! | Fine | Fine
| FDC3 | U2-4BOT | Slot 8 | ch.73 (bottom connector) | no signal |  |  |  | S73 | FDC3,C4,S73-96 | [5 empty] | signal sometime appears when cable is bending | No signal | No signal | Fine
All current wire problems below:
| FDC1 | Cell 1 |  | ch 0 | [13 empty] | No Signal (new) | No signal (old)
| FDC1 | Cell 1 |  | ch 25 | [5 empty] | FDC1,C1,S25-48 | [6 empty] | Low Signal | Low Signal | No signal
| FDC1 | Cell 1 |  | ch 49 | [5 empty] | FDC1,C1,S49-72 | [6 empty] | Low Signal | Low Signal | Low signal (old)
| FDC2 | Cell 6 |  | ch 70-96 | [5 empty] | FDC1,C1,S73-96 | [6 empty] | No signal (disconnected connector?) | No signal | Low Signal
| FDC3 | Cell 4 |  | ch 73 | [5 empty] | FDC1,C1,S73-96 | [6 empty] | No Signal (old) | No Signal (old) | Low signal (old)
| FDC1 | Cell 1 |  | ch 49-72 | [13 empty] | Noisy connector (new) | Noisy connector (slightly noisy)
| FDC4 | Cell 3 |  | ch 49-72 | [13 empty] | Noisy connector (new) | Noisy connector (VERY noisy)
| FDC1 | Cell4 |  | Ch1-28 | [13 empty] | No signal for 24 channels, low sig for 4 channels | Fine
| FDC2 | Cell1 |  | Ch48-71 | [13 empty] | A bit noisy (or perhaps below ch are low?) | Fine
| FDC2 | Cell2 |  | Ch48-71 | [13 empty] | A bit noisy (or perhaps below ch are low?) | Fine
| FDC3 | Cell3 |  | Ch55-66 | [13 empty] | A bit noisy (or perhaps below ch are low?) | Fine
| FDC4 | Cell5 |  | Ch50-64 | [13 empty] | A bit noisy (or perhaps below ch are low?) | Fine
| FDC1 | Cell 2 |  | ch 54 | [12 empty] | Noise | Noisy (with some noise in surrounding channels) | Noisy
| FDC1 | Cell 3 |  | ch 26,49-55,58 | [12 empty] | Noise | Noisy, ch27-28,56 noisy, 58 fine | Noisy
| FDC1 | Cell 4 |  | ch 49,51 | [12 empty] | Noise | Fine, ch50 a bit noisy | Still a few noisy channels
| FDC1 | Cell 5 |  | ch 50-52,56 | [12 empty] | Noise | Noisy | Still a little noise
| FDC2 | Cell 4 |  | ch 26 | [12 empty] | Noise | Fine | Noisy
|  | List of all old problems below | [6 empty] | S5 | FDC2,C4,S1-24 | ??? |  |  | to be tested
strips:
| FDC1 | U2-4-TOP | slot4 | all channels | noisy | ROC4 | slot1 | all channels |  | FDC1,C1,D169-192-23 | x | disconnected |  | no noise |  |  | Fine
|  | U2-4-TOP | slot5 | ch.71 | low | ROC4 | slot2 | ch.0 | D97A | FDC1,C2,D97A-120-0 | bad | disconnected |  | 70 mV |  |  | Fine
|  | U2-4-TOP | slot7 | ch.69 | no pedestal | ROC4 | slot4 | ch.69 | U75 | FDC1,C4,U73-96A-2 | x | disconnected |  | OK | bad again in run 176 |  | Fine
|  | U2-4-TOP | slot7 | ch.71 | low | ROC4 | slot4 | ch.71 | U73 | FDC1,C4,U73-96A-2 | bad | disconnected |  | max 50mV | ok at 100 (ADC units thresh.) |  | Fine
|  | U2-4-TOP | slot9 | ch.0 | low | ROC4 | slot6 | ch.0 | U24 | FDC1,C5,U1-24-23 | bad, some noise | disconnected |  | 50 mV, noise 30mV 23-13 down to 15mV on rest |  |  | Low signal (old problem)
|  | U2-4-MID | slot5 | ch.25 | low | ROC5 | slot2 | ch.25 | U167 | FDC1,C5,U145-168-22 | bad | disconnected |  | max 60mv |  |  | Fine
[9 empty] | U73 | FDC1,C5,U73-96A | OK | disconnected |  | to be checked | bad in run 176 |  | Fine
| FDC2 | U2-4-MID | slot8 | ch.32 | no pedestal | ROC5 | slot5 | ch.32 | D136 | FDC2,C1,D121-144-15 | x | disconnected |  | OK |  |  | Fine
|  | U2-4-MID | slot14 | ch71 | low | ROC5 | slot9 | ch.71 | U97A | FDC2,C4,U97A-120-0 | bad | disconnected |  | 60 mV |  | cable pulled during insertion? Already happened once | Low signal (old problem)
|  | U2-4-MID | slot15 | ch59 | no pedestal | ROC5 | slot10 | ch.59 | U85 | FDC2,C5,U73-96A-12 | x | disconnected |  | OK |  |  | Fine
| FDC3 | U2-5-TOP | slot14 | ch0 | no signal | ROC7 | slot9 | ch0,4 | D192 | FDC3,C1,D169-192-23 | bad | D192 | D192 | no signal no noise (<6mv) |  | try fixing 3M??? If doesn't help not worth fixing it (tried everything else) | No signal (old)
|  | U2-5-TOP | slot14 | ch4 | no pedestal | ROC7 | slot9 | ch0,4 | D188 | FDC3,C1,D169-192-23 | x | D188-ok;D175(new) | D175 | OK |  |  | Fine
|  | U2-5-TOP | slot15 | ch67 | low | ROC7 | slot10 | ch67 | D101A | FDC3,C2,D97A-120-4 | bad | D101A-ok | ok | max 50mV |  | was fixed once, bad pre-amp connector | Fine
|  | U2-5-MID | slot6 | ch25,26 | very low | ROC8 | slot3 | ch25,26 | D70,71 | FDC3,C6,D49-72-22 | 3 bad | ok | ok | max 60mV, 2 bad |  | can be fixed by bending up, #1,2,3 appearred before | 70 low signal, 71 fine
|  | U2-5-MID | slot7 | ch24 | very low | ROC8 | slot4 | ch24 | D144 | FDC3,C6,D121-144-23 | bad | ok | ok | max 60mV |  | difficult to fix it | Fine
|  | U2-5-MID | slot7 | ch0 | very low | ROC8 | slot4 | ch0 | D168 | FDC3,C6,D145-168-23 | bad | ok | ok | max 50mV |  | fixed by bending up very little, but re-appearred several times | Low signal (old)
|  | U2-5-MID | slot8 | ch1 | very low | ROC8 | slot5 | ch1 | U23 | FDC3,C6,U1-24-22 | bad | U23-ok; U1,U2(new) | ok | max 50mV |  | next to manifold, depending how bend tube, could be #23,24 or #2 (now) | Fine
|  | U2-5-MID | slot8 | ch24 | no | ROC8 | slot5 | ch24 | U72 | FDC3,C6,U49-72-23 | bad | U72 | U72 | no signal no noise |  | 3M??? | No signal (old)
|  | U2-5-MID | slot9 | ch25 | very low | ROC8 | slot6 | ch25 | D167 | FDC3,C1,D145-168-22 | bad | D167-ok | ok | max 40mV |  | fixed once by bending up | Fine
|  | U2-5-MID | slot10 | ch0 | low | ROC8 | slot7 | ch0 | U168 | FDC3,C3,U145-168-23 | bad | ok | ok | up to 150mV, but most ~50mV |  |  | Low signal (old)
|  | U2-5-MID | slot16 | ch47 | very low | ROC8 | slot11 | ch47 | D25 | FDC3,C6,D25-48-0 | bad | ok | ok | max 70mV |  |  | Low signal (old)
| FDC4 | U2-5-MID | slot17 | ch0 | low | ROC8 | slot12 | ch0 | D24 | FDC4,C1,D1-24-23 | bad | ok | ok | to be checked | x |  | Fine
|  | U2-5-MID | slot19 | ch65,68,70,71 | very low | ROC8 | slot14 | ch65,68,70,71 | D97,98,100,103A | FDC4,C2,D97A-120-0 | 5 bad | ok | ok | max 40,50,40,50 mV, total 4 | x | one channel fixed before by pushing tubes on both sides, not worth fixing | 97,98 Low, 100,103 Fine
|  | U2-5-BOT | slot4 | ch24 | very low | ROC9 | slot1 | ch24 | U72 | FDC4,C4,U49-72-23 | bad | ok | ok | OK | x |  | Low signal (old)
|  | U2-5-BOT | slot5 | ch25 | no pdestal | ROC9 | slot2 | ch25 | U143 | FDC4,C4,U121-144-22 | x | U143 | U143 | OK | x |  | Fine
|  | U2-5_BOT | slot6 | ch47 | low | ROC9 | slot3 | ch47 | U49 | FDC4,C5,U49-72 | bad | ok | ok | max 50mV | x |  | Low signal (old)
|  | U2-5-BOT | slot7 | ch47 | low | ROC9 | slot4 | ch47 | U121 | FDC4,C5,U121-144-0 | bad | ok | ok | max 50mV | x | re-seating helps | Fine
|  | U2-5-BOT | slot8 | ch24,25,26 | low | ROC9 | slot4 | ch24,25,26 | D48,47,46 | FDC4,C5,D25-48-23 | only 48 bad | ok | ok | max 50,50,50 mV, total 3 | x | fixed by bending tube up out of plane, all three were not working at some point | 46 fine, 47/48 low
|  | U2-5-BOT | slot8 | ch48 | very low?no? | ROC9 | slot4 | ch48 | D108B | FDC4,C5,D85B-108B-23 | bad | ok | ok | no signal no noise (<6mv) | x | 3M??? | Fine
|  | U2-5-BOT | slot10 | ch0 | no | ROC9 | slot7 | ch0 | D168 | FDC4,C6,D145-168-23 | bad | D168 | ok | no signal no noise (<6mv) | x | 3M??? | No signal (old)
|  | U2-5-BOT | slot10 | ch23 | low | ROC9 | slot7 | ch23 | D145 | FDC4,C6,D145-168-0 | x | ok | ok | OK | x |  | Low signal (old)
|  | U2-5-BOT | slot13 | ch20 | no pedestal | ROC9 | slot8 | ch20 | U4 | FDC4,C6,U1-24-3 | x | U4,U1(new) | U4 | OK | x |  | Fine
|  | U2-5-BOT | slot14 | ch0 | no | ROC9 | slot9 | ch0 | D168 | FDC4,C2,D145-168-23 | bad | D168 | D168 | no signal no noise (<6mv) | x | 3M! worked with another cable! | No signal (old)
|  | U2-5_BOT | slot14 | ch2 | no pedestal | ROC9 | slot9 | ch2 | D166 | FDC4,C2,D145-168-21 | x | D166-ok,D157(new) | D157 | OK | x |  | Fine
|  | U2-5-BOT | slot17 | ch24,25,29 | low | ROC9 | slot12 | ch24,25,29 | U48,47,43 | FDC4,C4,U25-48-23 | 3 bad | ok |  | max 50, 50, 40 mV | x | fixed before by bending tube up out of plane | 48 fine, 43,47 both low
| FDC2 | U2-6-TOP | slot8 | ch11,12 | medium | ROC10 | slot5 | ch11,12 | D181,180 | FDC2,C6,D169-192-12 | x | D181,180-ok;183-187(new) | ok | OK |  |  | Fine
| FDC3 | U2-6-TOP | slot13 | ch0,21,23 | low | ROC10 | slot8 | ch0,21,23 | U24,3,1 | FDC3,C1,U1-24-23 | bad only 24 | ok | ok | max 40,50,50 mV, 3 total |  | 1,3 were fixed by re-seating | U23 low, rest fine
|  | U2-6-TOP | slot13 | ch24,34 | low | ROC10 | slot8 | ch24,34 | u72,62 | FDC3,C1,U49-72-23 | bad | U72-????,U62-ok | ok | max 40,40 mV |  | once fixed by changing pre-amp | Low signal (old)
|  | U2-6-TOP | slot14 | ch43,47 | low | ROC10 | slot9 | ch43,47 | U125,121 | FDC3,C1,U121-144-4 | 5 bad | U125,121-ok | ok | max 60,50 mV, 2 total |  | once fixed by bending tube significanly | 121 low, 125 fine
|  | U2-6-TOP | slot14 | ch48,50 | low | ROC10 | slot9 | ch48,50 | U120,118 | FDC3,C1,U97A-120-23 | 4 bad | U120,118-ok | ok | max 60,40 mV, 2 total |  | once fixed by bending tube significanly | 120 low, 118 fine
|  | U2-6-MID | slot3 | ch48 | low | ROC11 | slot0 | ch48 | D120 | FDC3,C3,D97A-120-23 | bad | ok | ok | max 60 mV |  | works after bending tube inwards | Fine
|  | U2-6-MID | slot4 | ch71 | low | ROC11 | slot1 | ch71 | U85B | FDC3,C3,U85B-108B-0 | bad | ok | ok | max 50 mV |  | LV disconnected after insertion, checked only after final insertion. | Fine
|  | U2-6-MID | slot5 | ch26 | med/low | ROC11 | slot2 | ch26 | U142 | FDC3,C6,U121-144-21 | x | ok | ok | max 60 mV |  | never had problems before | Fine
|  | U2-6-MID | slot5 | ch48 | no | ROC11 | slot2 | ch48 | U120 | FDC3,C6,U97A-120-23 | bad | ok | U120 | no signal no noise |  | 3M!, always different channnels not working | No signal (old)
|  | U2-6-MID | slot5 | ch69 | medium | ROC11 | slot2 | ch69 | U99A | FDC3,C6,U97A-120-2 | bad | ok | ok | max 50 mV |  | works if bending inwards | Fine
|  | U2-6-MID | slot7 | ch20 | low | ROC11 | slot4 | ch20 | D172 | FDC3,C5,D169-192-3 | x | ok | ok | max 50 mV |  | never had problems before | Fine
|  | U2-6-MID | slot7 | ch35,37,39,40,43,45,47 | low | ROC11 | slot4 | ch35,37,39,40,43,45,47 | D133,131,129,128,125,123,121 | FDC3,C5,D121-144-12 | 5 bad | ok | ok | 40,43OK, but 44 low!!!, total 6 bad |  | bending tube out of plane helped a lot (fixing all but #24) | Still many problems
|  | U2-6-MID | slot7 | ch49,50,51,57,58,59,60,62 | low | ROC11 | slot4 | ch49,50,51,57,58,59,60,62 | D119,118,117,111,110,109,108,106 | FDC3,C5,D97A-120-22 | 8 bad | ok | ok | 49 OK, 54 low, total 8 bad |  | has g10 insert, very delicate!!! | Still many problems
|  | U2-6-MID | slot9 | ch22 | low | ROC11 | slot6 | ch22 | D146 | FDC3,C5,D145-168-1 | bad | ok | ok | very low rate 40mV |  | after re-palcing pre-amp many were fixed, but this one only | Fine
|  | U2-6-MID | slot9 | ch24,25,26 | medium | ROC11 | slot6 | ch24,25,26 | D168,167,166 | FDC3,C4,D145-168-23 | x | ok | ok | all OK!!! |  |  | Fine
|  | U2-6-MID | slot10 | ch0 | medium | ROC11 | slot7 | ch0 | U168 | FDC3,C1,U145-168-23 | bad | ok | ok | up to 100 mV |  |  | Low signal (old)
|  | U2-6-MID | slot13 | ch46 | no sig., ped up | ROC11 | slot8 | ch46 | U26 | FDC3,C1,U25-48-1 | bad | U26 | U26 | no signal no noise |  | had problems before with #1&#24 fixed by bending inwards outside manifold (if absolutely needed), now #23 3M??? | No signal (old)
|  | U2-6-MID | slot13 | ch51 | low | ROC11 | slot8 | ch51 | D105B | FDC3,C1,D85B-108B-20 | x | ok | ok | 60 mV |  | never had problems before | Fine
|  | U2-6-MID | slot15 | ch26 | low | ROC11 | slot10 | ch26 | U166 | FDC3,C2,U145-168-21 | bad | ok | ok | 60 mV |  |  | Low signal (old)
| FDC4 | U2-6-MID | slot17 | ch0 | no | ROC11 | slot12 | ch0 | U24 | FDC4,C1,U1-24-23 | bad | U24 | U24(low) | no signal no noise | x | fixed before by pressing inwards, next to the manifold!!! | No signal (old)
|  | U2-6-MID | slot17 | ch21,23?? | Ok | ROC11 | slot12 | ch21,23?? | U3,1 | FDC4,C1,U1-24-23 | x | ok | ok | signals OK on scope!! |  |  | Fine
|  | U2-6-MID | slot17 | ch28 | neg. pedestal | ROC11 | slot12 | ch28 | U68 | FDC4,C1,U49-72-19 | x | ok | ok | OK | x |  | Fine
|  | U2-6-MID | slot19 | ch26 | no ped | ROC11 | slot19 | ch26 | U70 | FDC4,C2,U49-72-21 | x | U70 | U70 | OK | x |  | Fine
|  | U2-6-BOT | slot3 | ch24,25 | low | ROC12 | slot0 | ch24,25 | D72,71 | FDC4,C2,D49-72-23 | 2 bad | ok | ok | 50, 70 mV | x |  | Fine
|  | U2-6-BOT | slot7 | ch32 | no sig,ped up | ROC12 | slot4 | ch32 | U40 | FDC4,C3,U25-48-15 | bad | ok | ok | no signal no noise | x | 3M!!! after bending cable signal appeared | Fine
|  | U2-6-BOT | slot7 | ch24 | no sig,ped up | ROC12 | slot4 | ch24 | U48 | FDC4,C3,U25-48-15 | x | ok | ok | to be checked | x | same cable!!! | Fine
|  | U2-6-BOT | slot8 | ch71 | med/low | ROC12 | slot5 | ch71 | D73 | FDC4,C4,D73-96A-0 | bad | ok | ok | to be checked | x |  | Low signal (old)
|  | U2-6-BOT | slot10 | ch1,2,6 | med/low | ROC12 | slot7 | ch1,2,6 | D191,190,186 | FDC4,C5,D169-192-22 | 3 bad | D186-ok,D190,191,D192(new) | ok | 40, 40, 40 mV, total 3 | x | bending a little up helped for #3, changing pre-amp no effect | Still medium/low statistics
|  | U2-6-BOT | slot14 | ch0 | low | ROC12 | slot9 | ch0 | U168 | FDC4,C6,U145-168-23 | bad | ok | ok | to be checked | x |  | Low signal (old)
|  | U2-6-BOT | slot15 | ch0,1 | low | ROC12 | slot10 | ch0,1 | D168,167 | FDC4,C5,D145-168-23 | 2 bad | ok | ok | 40, 40 mV | x | #1 was fixed before by bending tube up out of plane, #2 re-appeared and fixed by just little touching | 168 low, 167 fine
|  | U2-6-BOT | slot16 | ch48,49 | low | ROC12 | slot11 | ch48,49 | D96,95A | FDC4,C5,D73-96A-23 | x | ok | ok | 60, 50 mV | x | both were fixed before by bending tube up out of plane | Fine
|  | U2-6-BOT | slot17 | ch0,1 | low? or rare? | ROC12 | slot12 | ch0,1 | D192,D191 | FDC4,C6,D169-192-23 | x | D191-ok;D192;D184,189,190(new) |  | OK on scope | x |  | Fine
|  | U2-6-BOT | slot19 | ch2,23 | low, med | ROC12 | slot14 | ch2, 23 | D46, D25 | FDC4,C4,D25-48-21 | 2 bad | ok | ok | 40, 40 mV | x | #24 (D25) was fixed before by bending tube up out of plane, but #3 appeared bad, then both | Fine
| FDC1 | U2-7-TOP | slot6 | ch60 | no sig, ped up | ROC13 | slot3 | ch60 | D96B | FDC1,C2,D85B-108B-11 | x | D97B(calc[301-Nch]) | U97B | OK |  |  | Low signal (old problem)
|  | U2-7-TOP | slot15 | ch70 | no pedestal | ROC13 | slot10 | ch70 | D98A | FDC1,C5,D97A-120-1 | x | D98A | D98A | OK |  |  | Low signal (old problem)
| FDC2 | U2-7-MID | slot14 | ch22,23 | low? or rare? | ROC14 | slot9 | ch22,23 | D1,2 | FDC2,C3,D1-24-0 | x | D1,2-ok;D11-24 (new) | ok | OK | D12-24 bad in run176 |  | Fine
ALL current strip problems (As of Jan, 2016) below
| Pkg | Cell |  | Cathode Number | Old Problem |  |  |  | Strip number | [7 empty] | Status (Nov 2015) | Status Jan 2016 | Current Status (Oct 2016)
| FDC1 | Cell 1 Up |  | Cathode0_0_0 | [14 empty] | Noisy connectors (ch49, 73-84,109-144)
| FDC1 | Cell 1 Down |  | Cathode0_0_1 | [14 empty] | Noisy channels (ch84,109,216)
| FDC1 | Cell 2 Down | slot6 | Cathode0_1_1 | no sig, ped up | ROC13 | slot3 | ch60 | D96B | FDC1,C2,D85B-108B-11 | x | D97B(calc[301-Nch]) | U97B | OK |  |  | Low signal (old problem) | No Signal (old) | No Signal (old)
| FDC1 | Cell 4 Up |  | Cathode0_3_0 |  |  |  |  | U74 | [8 empty] | Low signal (new) | Low signal (old)
| FDC1 | Cell 4 Down |  | Cathode0_3_1 | [14 empty] | Noisy Channel (ch213)
| FDC1 | Cell 5 Up |  | Cathode0_4_0 | low |  |  |  | U24 | FDC1,C5,U1-24-23 |  |  | U189 |  |  |  | Low signal (old problem) | Low signal (old) | Low signal (old)
| FDC1 | Cell 5 Up |  | Cathode0_4_0 |  |  |  |  | U167 | [8 empty] | Low signal (new) | Low signal (old)
| FDC1 | Cell 5 Down |  | Cathode0_4_1 | no pedestal |  |  |  | D98A | FDC1,C5,D97A-120-1 | [6 empty] | No signal (old problem) | No signal (old) | No signal (old)
| FDC1 | Cell 5 Down |  | Cathode0_4_1 |  |  |  |  | D102A | [8 empty] | Low signal (new) | Low signal (old)
| FDC1 | Cell 6 Down |  | Cathode0_5_1 |  |  |  |  | D143 | [7 empty] | Low signal (new) | Low signal (old) | Low signal (old)
| FDC1 | Cell 6 Down |  | Cathode0_5_1 |  |  |  |  | Most channels | [9 empty] | Noise throughout all channels
| FDC2 | Cell 1 Up |  | Cathode1_0_0 |  |  |  |  | U48 | [7 empty] | No signal (new) | No signal (nov) | No signal (old), 2 channels noisy, 84, 109)
| FDC2 | Cell 2 Up |  | Cathode1_1_0 |  |  |  |  | U189 | [7 empty] | No signal (new) | No signal (nov) | No signal (old)
| FDC2 | Cell 3 Down |  | Cathode1_2_1 |  |  |  |  | D48 | [8 empty] | Low signal (new) | Low signal (old)
| FDC2 | Cell 4 Up |  | Cathode1_3_0 | low |  |  |  | U97A | FDC2,C4,U97A-120-0 | [6 empty] | Low signal (old) | Low signal (old) | Fine
| FDC2 | Cell 5 Up |  | Cathode1_4_0 |  |  |  |  | U85A, U96A, U120 | [7 empty] | No signal (new) | No signal (nov) | No signal (old)
| FDC2 | Cell 5 Down |  | Cathode1_4_1 |  |  |  |  | D146 | [7 empty] | Low signal (new) | Low signal (nov) | Low signal (old)
| FDC2 | Cell 5 Up |  | Cathode1_5_0 |  |  |  |  | U54 | [9 empty] | No Signal (new)
| FDC2 | Cell 5 Down |  | Cathode1_5_1 |  |  |  |  | D123 | [9 empty] | Low signal (new)
| FDC3 | Cell 1 Up |  | Cathode2_0_0 | low |  |  |  | U24,62,72,120,121,168 | [7 empty] | Low signal (old) | 62, 121 okay, rest Low | All still low (even 62, old)
| FDC3 | Cell 1 Up |  | Cathode2_0_0 |  |  |  |  | U63,76 | [7 empty] | Low signal (new) | 63 okay, 76 low | 63 low, 76 okay
| FDC3 | Cell 1 Up |  | Cathode2_0_0 | no sig., ped up |  |  |  | U26 | [7 empty] | No signal (old) | No signal (old) | No signal (old)
| FDC3 | Cell 1 Down |  | Cathode2_0_1 | no signal |  |  |  | D192 | [7 empty] | No signal (old) | No signal (old) | Fine
| FDC3 | Cell 1 Down |  | Cathode2_0_1 |  |  |  |  | D175 | [7 empty] | No signal (new) | No signal (nov) | No signal (old)
| FDC3 | Cell 1 Down |  | Cathode2_0_1 |  |  |  |  | D167, D88B | [8 empty] | Low signal (new) | 88B is fine, 167 low
| FDC3 | Cell 2 Up |  | Cathode2_1_1 | low |  |  |  | U166 | [7 empty] | Low signal (old) | Low signal (old) | Fine
| FDC3 | Cell 2 Down |  | Cathode2_1_1 |  |  |  |  | D96A | [7 empty] | No signal (new) | No signal (nov) | No signal (old)
| FDC3 | Cell 3 Up |  | Cathode2_2_0 | low |  |  |  | U168 | [7 empty] | Low signal (old) | Fine | Fine
| FDC3 | Cell 3 Up |  | Cathode2_2_0 |  |  |  |  | U162,189, 191 | [7 empty] | Low signal (new) | Low signal (nov) | 189 still low, rest are fine
| FDC3 | Cell 4 Up |  | Cathode2_3_0 |  |  |  |  | U192 | [7 empty] | No signal (low statistics, though) | Fine | Fine (hard to tell between low signal or low statistics)
| FDC3 | Cell 5 Up |  | Cathode2_4_0 |  |  |  |  | U119 | [9 empty] | Low
| FDC3 | Cell 5 Down |  | Cathode2_4_1 | low |  |  |  | D 98A, 102A,103A, 108,110,113-115 | [7 empty] | Low signal (some new & old) | Low (some new & old, updated ch list) | D72 also Low
| FDC3 | Cell 5 Down |  | Cathode2_4_1 | low |  |  |  | D117,119,121-125,127,131,142,147,150,172 | [7 empty] | Low signal (some new & old) | Low (some new & old, updated ch list) | Low
| FDC3 | Cell 6 Up |  | Cathode2_5_0 | no |  |  |  | U72,120 | [7 empty] | No signal (old) | No signal (old) | No signal (old)
| FDC3 | Cell 6 Up |  | Cathode2_5_0 |  |  |  |  | U96A | [7 empty] | No signal (new) | No signal (nov) | Low signal (old)
| FDC3 | Cell 6 Up |  | Cathode2_5_0 |  |  |  |  | U65,71,72 | [8 empty] | Low sig (72 no sig, new) | 71 okay, 65/72 still bad
| FDC3 | Cell 6 Down |  | Cathode2_5_1 |  |  |  |  | D71,168 | [7 empty] | Low signal (old) | Low signal (old) | Low (old)
| FDC3 | Cell 6 Down |  | Cathode2_5_1 |  |  |  |  | D25,121 | [7 empty] | Low signal (new) | Low signal (nov) | Low (old)
| FDC3 | Cell 6 Down |  | Cathode2_5_1 |  |  |  |  | D47,107B | [8 empty] | Low signal (new) | 47 Okay, 107 Low
| FDC4 | Cell 1 Up |  | Cathode3_0_0 | no |  |  |  | U24 | [7 empty] | No signal (old) | No signal (old) | No signal (old)
| FDC4 | Cell 1 Down |  | Cathode3_0_1 |  |  |  |  | D119,120 | [7 empty] | No signal (new) | No signal (nov) | D117 also Low, 119/120 Low
| FDC4 | Cell 1 Down |  | Cathode3_0_1 |  |  |  |  | D24 | [8 empty] | Low signal (new) | Fine
| FDC4 | Cell 2 Down |  | Cathode3_1_1 | low |  |  |  | D97A,98A,168 | [7 empty] | Low (168 no signal) (old) | Low signal (old) | Low, (168 no sig, old)
| FDC4 | Cell 2 Down |  | Cathode3_1_1 |  |  |  |  | D115,121,157,182 | [7 empty] | Low signal (157 no signal) (new) | 121 ok, ch72 low (nov) | 121 low again, 119 low, 182 fine.
| FDC4 | Cell 3 Up |  | Cathode3_2_0 |  |  |  |  | U48 | [9 empty] | Low (new)
| FDC4 | Cell 4 Up |  | Cathode3_3_0 | low |  |  |  | U43,47,72 | [7 empty] | Low signal (old) | Low signal & noise (old) | 43 is okay, rest low
| FDC4 | Cell 4 Up |  | Cathode3_3_0 |  |  |  |  | U45,46 | [7 empty] | Low signal (new) | Low signal & noise (nov) | Low (old)
| FDC4 | Cell 4 Down |  | Cathode3_3_1 | med/low |  |  |  | D72, 73 | [7 empty] | Low signal (old) | Low signal (old) | Low (old)
| FDC4 | Cell 4 Down |  | Cathode3_3_1 |  |  |  |  | D14,15,17,18,21,48 | [7 empty] | Low signal (new) | Low signal (nov) | 47, 83 also Low, rest still low
| FDC4 | Cell 4 Down |  | Cathode3_3_1 |  |  |  |  | D25 | [8 empty] | Low signal (new) | Low (old)
| FDC4 | Cell 5 Up |  | Cathode3_4_0 | low |  |  |  | U21,49 | [7 empty] | Low signal (21 new, 49 old) | 49 okay, 21 low | 49 Low again, 21 low
| FDC4 | Cell 5 Up |  | Cathode3_4_0 |  |  |  |  | U146,147,168 | [7 empty] | No signal (new) | 147 okay, rest no sig | 147 okay, rest no sig
| FDC4 | Cell 5 Down |  | Cathode3_4_1 | low |  |  |  | D47,48,168 | [7 empty] | Low signal (old) | Low signal (old) | Low (old)
| FDC4 | Cell 5 Down |  | Cathode3_4_1 |  |  |  |  | D73,166 | [7 empty] | Low signal (new) | Low signal (nov) | Low (old)
| FDC4 | Cell 5 Down |  | Cathode3_4_1 |  |  |  |  | D23,46,95A,96A,183,186,187,190,191 | [8 empty] | Low signal (MANY new) | 95A okay, 85B low
| FDC4 | Cell 6 Up |  | Cathode3_5_0 | low |  |  |  | U168 | [7 empty] | Low signal (old) | Fine | Slightly Low
| FDC4 | Cell 6 Up |  | Cathode3_5_0 |  |  |  |  | U24, 96A | [7 empty] | No signal (new) | No signal (nov) | No signal, 24 no sig (new)
| FDC4 | Cell 6 Down |  | Cathode3_5_1 | low |  |  |  | D145 | [7 empty] | Low signal (old) | Fine | Slightly Low
| FDC4 | Cell 6 Down |  | Cathode3_5_1 | no |  |  |  | D26,168 | [7 empty] | No signal (old) | No signal (old) | 26 also no signal

## Sheet2
| Previous | Run N
FDC1_Cell1_Upstream | ok | 193-216
FDC1_Cell1_Downstream | ok | 0-192
FDC1_Cell1_Wires | s1 | ok
FDC1_Cell2_Upstream | ok | 169-216
FDC1_Cell2_Downstream | D97A,D96B | 73-192,204(97B)
FDC1_Cell2_Wires | ok | 49-63(noisy)
FDC1_Cell3_Upstream | ok
FDC1_Cell3_Downstream | ok
FDC1_Cell3_Wires | ok
FDC1_Cell4_Upstream
FDC1_Cell4_Downstream
FDC1_Cell4_Wires
FDC1_Cell5_Upstream
FDC1_Cell5_Downstream
FDC1_Cell5_Wires
FDC1_Cell6_Upstream
FDC1_Cell6_Downstream
FDC1_Cell6_Wires
FDC2_Cell1_Upstream
FDC2_Cell1_Downstream
FDC2_Cell1_Wires
FDC2_Cell2_Upstream
FDC2_Cell2_Downstream
FDC2_Cell2_Wires
FDC2_Cell3_Upstream
FDC2_Cell3_Downstream
FDC2_Cell3_Wires
FDC2_Cell4_Upstream
FDC2_Cell4_Downstream
FDC2_Cell4_Wires
FDC2_Cell5_Upstream
FDC2_Cell5_Downstream
FDC2_Cell5_Wires
FDC2_Cell6_Upstream
FDC2_Cell6_Downstream
FDC2_Cell6_Wires
FDC3_Cell1_Upstream
FDC3_Cell1_Downstream
FDC3_Cell1_Wires
FDC3_Cell2_Upstream
FDC3_Cell2_Downstream
FDC3_Cell2_Wires
FDC3_Cell3_Upstream
FDC3_Cell3_Downstream
FDC3_Cell3_Wires
FDC3_Cell4_Upstream
FDC3_Cell4_Downstream
FDC3_Cell4_Wires
FDC3_Cell5_Upstream
FDC3_Cell5_Downstream
FDC3_Cell5_Wires
FDC3_Cell6_Upstream
FDC3_Cell6_Downstream
FDC3_Cell6_Wires
FDC4_Cell1_Upstream
FDC4_Cell1_Downstream
FDC4_Cell1_Wires
FDC4_Cell2_Upstream
FDC4_Cell2_Downstream
FDC4_Cell2_Wires
FDC4_Cell3_Upstream
FDC4_Cell3_Downstream
FDC4_Cell3_Wires
FDC4_Cell4_Upstream
FDC4_Cell4_Downstream
FDC4_Cell4_Wires
FDC4_Cell5_Upstream
FDC4_Cell5_Downstream
FDC4_Cell5_Wires
FDC4_Cell6_Upstream
FDC4_Cell6_Downstream
FDC4_Cell6_Wires