## Tracking
FDC Construction Tracking 11/11/2011
Package 1 |  | End Window | EW003
| Cell 2 | Type 3 Cathode | C003 | Wireboard | W005 | Gas Spacer | Type 3 Cathode | C004
| Cell 3 | Type 1 Cathode | C006 | Wireboard | W009 | Gas Spacer | Type 2 Cathode | C008
| Cell 4 | Type 1 Cathode | C007 | Wireboard | W008 | Gas Spacer | Type 2 Cathode | C010
| Cell 5 | Type 1 Cathode | C009 | Wireboard | W011 | Gas Spacer | Type 2 Cathode | C011
| Cell 6 | Type 1 Cathode | C012 | Wireboard | W010 | Gas Spacer | Type 2 Cathode | C013
| Cell 7 | Type 1 Cathode | C014 | Wireboard | W012 | Gas Spacer | Type 2 Cathode | C015
|  | End Window | EW004
Spare |  | End Window | EW001
| Cell 1 | Type 3 Cathode | C001 | Wireboard | W002 | Gas Spacer | Type 3 Cathode | C002
| Cell 8 | Type 1 Cathode |  | Wireboard | W001 | Gas Spacer | Type 2 Cathode
| Cell 9 | Type 1 Cathode |  | Wireboard | W003 | Gas Spacer | Type 2 Cathode
| Cell 10 | Type 1 Cathode |  | Wireboard | W006 | Gas Spacer | Type 2 Cathode
|  | End Window | EW002
Package 2 |  | End Window | EW005
| Cell 11 | Type 3 Cathode | C016 | Wireboard | W013 Capacitors | Gas Spacer | Type 3 Cathode | C017
| Cell 12 | Type 1 Cathode | C018 | Wireboard | W007 | Gas Spacer | Type 2 Cathode | C019
| Cell 13 | Type 1 Cathode | C020 | Wireboard | W014 Cables | Gas Spacer | Type 2 Cathode | C021
| Cell 14 | Type 1 Cathode | C022 Glue Frame | Wireboard | W015 Tension Meaurements | Gas Spacer | Type 2 Cathode | C023 Transfer Ring
| Cell 15 | Type 1 Cathode |  | Wireboard | W016 Current Testing | Gas Spacer | Type 2 Cathode
| Cell 16 | Type 1 Cathode |  | Wireboard | W017 Replace Capacitors | Gas Spacer | Type 2 Cathode
|  | End Window | EW006
Package 3 |  | End Window
| Cell 17 | Type 3 Cathode |  | Wireboard |  | Gas Spacer | Type 3 Cathode
| Cell 18 | Type 1 Cathode |  | Wireboard |  | Gas Spacer | Type 2 Cathode
| Cell 19 | Type 1 Cathode |  | Wireboard |  | Gas Spacer | Type 2 Cathode
| Cell 20 | Type 1 Cathode |  | Wireboard |  | Gas Spacer | Type 2 Cathode
| Cell 21 | Type 1 Cathode |  | Wireboard |  | Gas Spacer | Type 2 Cathode
| Cell 22 | Type 1 Cathode |  | Wireboard |  | Gas Spacer | Type 2 Cathode
End Window
Package 4 |  | End Window
| Cell 23 | Type 3 Cathode |  | Wireboard |  | Gas Spacer | Type 3 Cathode
| Cell 24 | Type 1 Cathode |  | Wireboard |  | Gas Spacer | Type 2 Cathode
| Cell 25 | Type 1 Cathode |  | Wireboard |  | Gas Spacer | Type 2 Cathode
| Cell 26 | Type 1 Cathode |  | Wireboard |  | Gas Spacer | Type 2 Cathode
| Cell 27 | Type 1 Cathode |  | Wireboard |  | Gas Spacer | Type 2 Cathode
| Cell 28 | Type 1 Cathode |  | Wireboard |  | Gas Spacer | Type 2 Cathode
End Window
Complete
In-Process

## Wireboards
| Wireboard # | Epoxy | Humi-seal | Replaced Capacitors | Wire Deadened
Spare | W001 | Epo-lite | No | No | No
Spare | W002 | Epo-lite | Yes | No | Yes
Spare | W003 | Epo-lite | No | No | No
Spare | W006 | Epo-lite | Yes | No | No
Package 1 | W005 | Epon | Yes | No | Yes
| W008 | Epon | No | Yes | Yes
| W009 | Epon | No | Yes | Yes
| W010 | Epon | No | Yes | Yes
| W011 | Epon | No | Yes | Yes
| W012 | Epon | No | Yes | Yes
Package 2 | W007 | Epon | No | Yes | Yes
| W014 | Epon | No | Yes | Yes
| W015 | Epon | No | Yes | Yes
| W017 | Epon | No | Yes | Yes
| W019 | Epon | No | Yes | No
| W016 | Epon | No | Yes | No
Package 3
Package 4

## Current Tracking
FDC Construction Tracking | [11 empty] | 2012-01-11
FDC1 | UP | End Window | EW003 | X | [8 empty] | 100%
| Cell C6 | Type 3 Cathode | C003 | X | Wireboard | W005 | X | Gas Spacer | X | Type 1 Cathode | C006 | X
| Cell C5 | Type 2 Cathode | C008 | X | Wireboard | W009 | X | Gas Spacer | X | Type 1 Cathode | C007 | X
| Cell C4 | Type 2 Cathode | C010 | X | Wireboard | W008 | X | Gas Spacer | X | Type 1 Cathode | C009 | X
| Cell C3 | Type 2 Cathode | C011 | X | Wireboard | W011 | X | Gas Spacer | X | Type 1 Cathode | C012 | X
| Cell C2 | Type 2 Cathode | C013 | X | Wireboard | W010 | X | Gas Spacer | X | Type 1 Cathode | C014 | X
| Cell C1 | Type 2 Cathode | C015 | X | Wireboard | W012 | X | Gas Spacer | X | Type 3 Cathode | C004 | X
| Down | End Window | EW004 | X
FDC2 | UP | End Window | EW005 | X | [8 empty] | 100%
| Cell C6 | Type 3 Cathode | C016 | X | Wireboard | W007 | X | Gas Spacer | X | Type 1 Cathode | C018 | X
| Cell C5 | Type 2 Cathode | C019 | X | Wireboard | W014 | X | Gas Spacer | X | Type 1 Cathode | C020 | X
| Cell C4 | Type 2 Cathode | C021 | X | Wireboard | W015 | X | Gas Spacer | X | Type 1 Cathode | C022 | X
| Cell C3 | Type 2 Cathode | C023 | X | Wireboard | W017 | X | Gas Spacer | X | Type 1 Cathode | C024 | X
| Cell C2 | Type 2 Cathode | C025 | X | Wireboard | W019 | X | Gas Spacer | X | Type 1 Cathode | C026 | X
| Cell C1 | Type 2 Cathode | C028 | X | Wireboard | W016 | X | Gas Spacer | X | Type 3 Cathode | C017 | X
| Down | End Window | EW006 | X
FDC3 | UP | End Window | EW007 | [9 empty] | 21%
| Cell C6 | Type 3 Cathode | C029 Daughter Cards |  | Wireboard | W020 Stringing |  | Gas Spacer |  | Type 1 Cathode | C027
| Cell C5 | Type 2 Cathode | C031 Cut Foil |  | Wireboard | W021 Gas Blocks |  | Gas Spacer |  | Type 1 Cathode | C032 Cut Foil
| Cell C4 | Type 2 Cathode |  |  | Wireboard |  |  | Gas Spacer |  | Type 1 Cathode
| Cell C3 | Type 2 Cathode |  |  | Wireboard |  |  | Gas Spacer |  | Type 1 Cathode
| Cell C2 | Type 2 Cathode |  |  | Wireboard |  |  | Gas Spacer |  | Type 1 Cathode
| Cell C1 | Type 2 Cathode |  |  | Wireboard | W013 Capacitors |  | Gas Spacer |  | Type 3 Cathode | C030 Mylar Flaps
| Down | End Window | EW008
FDC4 | UP | End Window | [10 empty] | 0%
| Cell C6 | Type 3 Cathode |  |  | Wireboard |  |  | Gas Spacer |  | Type 3 Cathode
| Cell C5 | Type 1 Cathode |  |  | Wireboard |  |  | Gas Spacer |  | Type 2 Cathode
| Cell C4 | Type 1 Cathode |  |  | Wireboard |  |  | Gas Spacer |  | Type 2 Cathode
| Cell C3 | Type 1 Cathode |  |  | Wireboard |  |  | Gas Spacer |  | Type 2 Cathode
| Cell C2 | Type 1 Cathode |  |  | Wireboard |  |  | Gas Spacer |  | Type 2 Cathode
| Cell C1 | Type 1 Cathode |  |  | Wireboard |  |  | Gas Spacer |  | Type 2 Cathode
| Down | End Window
Spare |  | End Window | EW001 | [9 empty] | 35%
| Cell 1 | Type 3 Cathode | C001 |  | Wireboard | W002 |  | Gas Spacer |  | Type 3 Cathode | C002
| Cell 8 | Type 1 Cathode |  |  | Wireboard | W001 |  | Gas Spacer |  | Type 2 Cathode
| Cell 9 | Type 1 Cathode |  |  | Wireboard | W003 |  | Gas Spacer |  | Type 2 Cathode
| Cell 10 | Type 1 Cathode |  |  | Wireboard | W006 |  | Gas Spacer |  | Type 2 Cathode
|  | End Window | EW002
Complete
In-Process
[10 empty] | X | Assembled In Package