## Design Esitmate
Hall D Design Esitmate
Task | % Complete | Engineering Man Hours | Design/CAD Man Hours | Drafting Man Hours | Total Man Hours to complete
Magent Cryogenic Box
JT valves | 60 | 16 | 16 | 32 | 64
Helium Tank | 40 | 12 | 10 | 16 | 102
LN2 Tank | 40 | 48 | 10 | 10 | 68
Two Heat Exchangers | 100 |  |  |  | 0
U-tubes | 60 | 12 | 24 | 48 | 84
Relief valves | 0 | 24 | 10 | 20 | 54
Current Leads | 0 |  | 40 | 40 | 80
Internal Piping | 5 | 48 | 56 | 56 | 160
Expansion Can | 10 | 24 | 48 | 48 | 120
FEA Analysis of puffing Ravi | 75 | 36 |  |  | 36
Puffing Billy(Cryogenic Box) |  | 8 | 12 | 36 | 56
Transferline |  | 48 | 48 | 48 | 144
|  |  |  | Total | 968
|  |  |  | Days | 121
|  |  |  | Months | 4.0333
Mechanical Supports for Magent & Barrel Calorimeter
Steel support for magnet | 60 | 16 | 24 | 48 | 88
Yoke modifications | 40 | 6 | 8 | 8 | 22
Magnet End Plate | 20 | 6 | 8 | 6 | 20
Barrel Calorimeter Support | 10 | 56 | 48 | 48 | 152
|  |  |  | Total | 282
|  |  |  | Days | 35.25
|  |  |  | Months | 1.175
0
Total Man hours needed to complete work for the above listed items |  |  |  | Months | 5.2083
Approx : 6 months