# MEMORANDUM

To:	Distribution

From:	F. Dylla

Subject:	FEL Upgrade Project Weekly Brief – December 1-5, 2003

Date:	December 5, 2003

Highlights:

Since the last full weekly report (Nov. 21) before the Thanksgiving holiday break we have made significant progress on commissioning of the FEL Upgrade.  On Wednesday, Nov. 26, we re-established pulsed lasing at 10.1 microns with approximately 700 watts of average power during the macropulse.  With this achievement we are essentially fully recovered from the hiatus caused by Hurricane Isabel.  Except for a short break on Thursday, Nov. 27th for caloric loading of the staff with family and friends, we have been hard at work to set-up and optimize the accelerator for cw operations.  This week clean, energy recovered, cw operation has been achieved at 2 mA.  We also characterized the THz radiation emitted downstream of the outcoupler mirror as a function of average current and peak charge and do not feel this will be a limiting factor for heating of the optics in our present set-up.  More details of the extensive work done in the last two weeks are given in the commissioning section below.  A break in operations today and through the weekend will allow us to deal with a punch list of maintenance and minor hardware fixes that have accumulated since we re-started beam operations on the 19th. We plan to resume commissioning activities on Monday.

NOTE: HOLD THESE DATES:

The next (tri-services) semiannual project review of the FEL Upgrade will be held at Jefferson Lab on Jan. 29-30, 2004.

The 2004 FEL Users/Laser Processing Consortium Workshop will be held at Jefferson Lab on March 10-11, 2004.

Commissioning:

We took extensive data on the THz generation with a calorimeter as a function of charge and average beam current.  Under the present bunching setup (much less aggressive than last August) the level of heating does not appear to be a major source of mirror distortion.  We measure on the order of 5W/mA/100pC.  At that level the THz heating would only account for 3% of our thermal distortion budget at full current and would not appear to be a factor in limiting FEL output power.  Preliminary spectra are shown below.

A very short report was given in last week's report so we will describe last week’s activities in more detail as well as this week.

Last week got off to a slow start when we lost power in the building due to a ground fault.  This took several hours to recover from.  When we were back up we were able to clean up the transmission to the energy recovery dump so that we could run high duty factor beam with no beam loss monitor trips.

On Tuesday we worked on matching the electron beam through the machine.  We obtained a good match to the backleg.  The emittance looked quite good (10 microns vertical and 15 microns horizontal).  We continued to measure 0.5 psec FWHM bunch lengths.  No lasing was found however.

Wednesday we continued to match through the machine and were able to find a good match to the wiggler.  We managed to get lasing for the first time since Isabel.  The laser was quite insensitive to most parameters.  It was optimized for the design buncher gradient, unlike earlier lasing.  There was a discrepancy between the energy change in the electron beam (0.7%) and the calculated efficiency from the power measurement (0.36%).  We also discovered that the drive laser pulse controller was not producing the proper repetition rates for low frequencies.  This partly explains why we could not see any lasing up to this time, since the requested frequency of 4.678 MHz was not being delivered.  This has since been fixed and we lase routinely at 4.678 MHz.

On Friday and Saturday we optimized the FEL and found quite a low lasing threshold compared to the one in August.   We could not make the laser lase at 6 microns despite seeing strong and reproducible lasing at 10 microns.  We believe there may be some problem with the mirrors. 
On Monday we addressed drift and jitter issues that have been troubling us for the last few weeks.  We found that the water for a chill plate used to stabilize the buncher phase was not turned on.  We turned it on and the buncher seems to be more stable this week.  The beam position monitor timing was found to be too close to the end of the macropulses, leading to jitter, and this was fixed as well.  Finally, we traced an injector energy jitter to the drive laser phase jitter.  Attempts have been made during the week to reduce the drive laser phase jitter, so far without success.  We recorded the size of the beam at the injector cryounit to aid in quick phasing of the injector.  This helped us narrow down the source of phase drift this week. 
Tuesday was devoted to getting a better re-injection match to the linac.  We found, during this effort that the first arc sextupoles were misbehaving and causing beam loss.  We are working today to fix this problem.

Wednesday we carried out a full series of difference orbits to look for discrepancies between the model and the machine.  A few suspects were found, primarily involving calibration factors for a few BPMs and small deviations of quadrupole excitation, likely due to hysteretic effects.  Most elements match the model well.  We also found that some of the beam loss we were seeing in the linac was due to the first pass beam rather than the second pass beam.  This was cleaned up and we were able to run CW beam and take good data of the THz radiation power vs. charge and current. The measurement indicated total power emitted was 5 W/ma/100pC. This means 80 W total power at 10 mA and 135 pC. We do not know how much of this power will be absorbed in the mirror.

Thursday we carried out phase transfer measurements of the linac from its entrance to the wiggler.  Ideally the phase transfer function is a vertical line.  As seen in the attached figure that is exactly what we found.  The horizontal scale is 136 fsec per unit so the noise is less than 700 fsec full width.  The noise is due to drive laser phase noise and should be smaller when we get that reduced.  We could adjust the curvature using the sextupoles and the slope using the trim quads.  The slope is vertical for the design trim quad values.

We also took data on gun noise from two stack operation and looked at the drive laser transport through the light box.  In the IR Demo we found that, if the laser was vignetted in the light box, halo was formed that prevented high current operation.  That is exactly what we are seeing now and, in fact, we found that the beam was being clipped in the light box.  This will be fixed this weekend.

In summary.  We now have a good (though not perfect) electron beam match up to the wiggler.  There are some losses after the wiggler and near the dump.  We will optimize this next week.  We can run up to 2 mA CW limited by the halo that is present on the beam due to vignetting in the light box.  This should be fixed next week as well.  THz power has been seen that may be a problem at very high current but is not a problem yet.  The laser lases well and is nearly optimized for the design parameters.  Drift has been reduced and can be compensated for easily now.  Jitter from the drive laser needs to be reduced to previously attainable levels to have very stable laser operation.

Management:

A successful semiannual review of the UV FEL Upgrade project was held on Nov. 25th.

We received a summary evaluation of the review from our AFRL program officer (John Eric) with his assessment.  John was pleased with the progress on the 10 kW IR FEL commissioning, the delivery of hardware that was jointly procured for both the IR and UV Upgrades (chicane dipoles and quadrupoles, and optical cavity vacuum chambers), Aerospace Corporation’s progress on the design of the microfabrication station, and preliminary plans for FY04 activities. Draft work statements for the Jefferson Lab UV FEL efforts and the Aerospace effort for FY04 were approved pending final resolution of the amount and availability dates for the FY04 AF funding for these tasks.

Several rounds of (email) discussions were held this week with ONR on our proposed work on the 100 mA injector test stand and associated rf hardware.  A conference call is being planned

for Dec, 15th on the subject of the rf hardware.

Preparations continued with our partners at AES for our joint design review on Dec. 15th for the US Army for our THz beamline project.

WBS 4 (Injector):

We performed a cathode recesiation today.  The QE on the location of the laser spot increased from 0.7% to 4%.  The last recesiation was performed on Nov 20th. Today's QE is about 90% of that on Nov. 20th. The cathode delivered pulsed beam at 135 pC, and up to 2.0 mA of cw beam current at 110 pC. The charge was limited not by the photocathode gun , but from losses in the dump.

We made progress on the field emission testing of the coated electrode.  The electrode was tested at 30 mV/m for a total of six hours.  Some conditioning was observed and the gradient was increased up to 31.25 MV/m.  After 30 min at that gradient, the average current at 30 MV/m dropped from 140 pA (recorded in a previous test) to about 40 pA. Long runs at 30 MV/m will continue next week.

Gun HVPS - Tests were conducted on the Gun HVPS for both 1 and 2 drive stack operations at 350kV.  The 1 drive stack responded well with a low (5v p-p)ripple voltage for 1 mA current pulses, but it is limited to about 5 mA maximum current. The 2 drive stack mode of operation becomes very noisy as the output voltage is passes through 250kV.  The measured current abruptly jumps from about 0.030 to 0.300 mA.  This precludes any HV processing with 2 stacks.  Under pulsed 1mA load conditions, the output voltage jumped between 349kV to 367kV.  Under heavier (2 ma CW) load the output voltage was stable at 350kV.  The Ripple Voltage monitor indicated 60v p-p.  This information is being forwarded to the vendor to see if they have a solution to the noisy operation under light or pulsed loads.

WBS 5 (SRF):

Work on the third cryomodule continues steadily but slower than we would like. The thermal shield has now been hung from the space frame. The helium circuit bellows that connect the sections of the shield together all had to be modified and custom fit by hand which took longer than expected. We are still finding lots of little modifications that need to be made to make everything fit together. This shield assembly was the first prototype made and was set aside and not used on SL21 for just this reason. We now have to make it work and it is requiring a lot of hands-on detail work. We will get there in the end and the final product will be worth the extra effort to do it right. The schedule is now showing that the module will not be completed before the holidays, despite the best efforts of all concerned. The cryomodule assembly team is already working two shift operation in parallel with SNS production. The module will most likely be delivered now in January. Installation activities will be coordinated with 10 kW running of the FEL, which is the top priority.

WBS 6 (RF):

Buncher - In trying to stabilize the e-beam more, the Buncher was turned off and back on in an off-normal state.  We lost about 4 hours of operations until the technician was located returning from vacation.  On a cell-phone he was able to talk us through to the solution.  He is now putting together an operations and trouble-shooting guide for the Buncher that includes an updated set of drawings.

RF - The RF systems ran very well, except for the time lost on the Buncher and this was not a real failure.

WBS 8 (Instrumentation):

The design for the 64 channel diode/RTD readout chassis is nearly complete. The drawings have been started while the final pinouts are determined. There will be 16 four channel boards that have independent current sources, buffer amps, and analog multiplexers that are set to communicate with out new CAN bus DSP board. (request for quote sent out today for 5 DSP prototypes - they are due in 4 weeks) One stage of this project will be complete for the arrival of the upgrade cryomodule in January.  This new module has a total of 54 Si diode thermometers for monitoring temperatures throughout the module. 
The Linux IOC frame grabber project will be available for use in beam measurements beginning Monday.  A second SCION card has arrived and will now be used for system development (and as a spare).  After well structured research combined with the assistance of Al Grippo and Arne Freyberger, the framegrabber's memory allocation problem has been solved.  The OS was assigning virtual memory addresses for the capture card memory that was being mapped to the software. The problem with the way the OS was controlling this was that it never checked to see if the virtual address is short of or exceeds the allowable used area of the kernel's memory.  In summary, the OS gave the framegrabber software a memory address that it was forbidden to use so the program would abort unexpectedly without freeing any of it's consumed resources. Through me explaining the details of what the Linux OS was doing, Al and I realized that we could try to hold on to the area that we were assigned and try to read new frames mapped to the old locations. This was then implemented and through a small adjustment the frames were coming in fine. All viewers will be calibrated by Monday morning for calculation of their individual x and y scale factors.  So that maybe we won't have scientists measuring beam widths with ink pens.

A new design for upgrading the SF6 gas transfer system is being finalized.  The new system will have larger diameter piping and additional pumping speed.  The new system will be entirely automated such that transfer of the gas can be initiated with the push of a button and take place while other activities such as a radiation survey take place. The manual valves will be replaced by electric valves and a Programmable Logic Controller (PLC) will be programmed to pass the gas back and forth before and after each re-cesiation of the gun. The bulk of the work and documentation will be done with our mechanical and electrical engineering students.

The video system became unreliable this Thursday in its switching accuracy. After initial troubleshooting, the digital controls have been ruled out. We then discovered a large amount of noise on the grounds of the signals coming up from the machine vault. The source of this noise is believed to be the cause of the systems unpredictable behavior. The problem is ongoing but with today being a 'maintenance' day, we should have it fixed by the end of the day.

Machine documentation continues.  Check prints have been received from EECAD for the following: Charge/Dump Current Monitor Beam Envelope Board; Optics Heater Control Board, Rev. A; Dump Water Control System, System Diagram; and the Dump Water Skid Interface Box, Wiring Diagram. Completed drawings were received for Rev. B to the 12 CH BLM Breakout module and the Wiring Diagram for the OutCoupler Temperature Control Chassis. Several User Lab cameras were assembled and tested. Noise measurements on the Digitel 500 Ion Pump Power supplies are in progress in an attempt to get a cleaner signal into EPICS for the current readback. The fail-safe interlock boxes for the OCR diagnostics solenoids have been completed and are ready for implementation. The 2F06 chimney viewer has been fully assembled and aligned on the viewer test stand. Installation will happen during our maintenance day.  The revision to the Outcoupler Temperature Control Chassis is complete. A circuit board was added to filter noise fluctuations from the controller.  It will be re-installed and tested today.

There was near disaster this morning when the caffeine generator could not make the proper temperature gradient resulting in only gurgling. That coupled with depleted spare grounds forced the team to start a bit slow on decaff. Repeated flushing with a 5% solution of acetic acid restored it to near perfect operation, a quick trip to the local warehouse was also needed to replenish stocks and restore the team to peak performance.

WBS 11 (Optics):

A lot has happened these last two weeks (with the only time off being Thanksgiving and part of Sunday for some of us).  We reacquired lasing at ~ 10.1 um, and gave the optical diagnostics a good checkout.  See the Commissioning section of this report for information on the performance.  However, we were perplexed by the inability to lase at 6 um.  While we have the optical cavity assemblies open to install new 10.6 um optics, we will remove and test it for optical figure, then reinstall it to further minimize possible mounting stress.  We used our mirror metrology system to track the change in the mirror radius of curvature as a function of beam-induced THz radiation.  The change was 0.06% for ~ 5 W (assuming it is all absorbed).  Using an analysis produced by S. Benson (Tech Note 97-005 and its successors) this is a 0.25% change in the Rayleigh range.  Scaled for 10 mA, this should not prove a big impediment to our ability to achieve high power, although it does eat into our absorbed power budget. In order to increase our chances of lasing at high power, we are installing our spare 10.6 um HR and OC mirrors in the unoccupied broadband position.  After some "back and forth" between us and our vendor, we received optics that meet or exceed specifications.  The OC mirror is being mounted in the improved mount we've written about, and this will, if nothing else, decrease any mounting-induced aberration and lower the temperature drop across the mirror-mount interface.  The mirrors were both tested in our new laser calorimetry setup, measurements will undergo analysis over the weekend.

One fly in an otherwise positive report has been a deterioration in the mode-locked performance of the drive laser.  At low frequencies (< 0.5 Hz), we measure increased amplitude and phase noise.  While half the group are changing optics downstairs, the other half are fixing the drive laser.  (Thank goodness for hardworking qualified staff!).

Amidst all of this work we have been holding meetings on the optical transport.  Drawings for the modifications and hardware going into the optical control room were signed, and drawings for modifying existing components in the User Lab to handle +10 kW are eminent.

Terahertz Project:

The optical configuration and the mirror sizes and figures were optimized by calculating and propagating the electric field using the Synchrotron Radiation Workshop code in Saclay, France in collaboration with Oleg Chubar and Paul Dumas.  M1 will be an ellipsoidal mirror of 625mm focal length, while M2 will be an ellipsoidal mirror with F1=705mm and F2=2426 mm.  M3 will be planar.  The mirror blanks will fill as much of the 150mm tube as possible, consistent with clearance for adjustment.  Both diamond windows will be 20mm clear aperture, as this transmits most of the light to 0.1 THz, or 3.3mm wavelength.  This configuration means that the final part of the vacuum system from M4 to F3 will have to be shortened.  A sample aluminum single point diamond turned mirror from one of the vendors arrived this week and was sent to Brookhaven for metrology and qualification.  Work continued on documentation for the pre-construction design review, which is now scheduled for December 15th.