MEMORANDUM

To:		Distribution

From:		F. Dylla

Subject:	FEL Upgrade Project Weekly Brief – March 29-April 2, 2004

Date:		April 2, 2004

Highlights:

During this week's efforts for commissioning of the FEL Upgrade, we summarize the following accomplishments:

(1) The rf commissioning of the of the new 3rd cryomodule was completed this week on schedule.  The results are excellent.  The module delivered a gradient of 82 MV with operation on its standard (Zone 4) rf power and control system. The system has had two extended periods (6-12 hrs) of operation without rf trips.  Based on last week's measurements on individual cavities, the maximum gradient for this module is in the range of 86MV.  This is the highest gradient module ever produced by JLab.

(2) We received new low loss optics for the high power tests at 6 microns.  Both optics meet our critical ROC (16m) and surface roughness specs.  One of the optics is being installed in the outcoupler tomorrow.  We are also installing a 10 micron scraper outcoupler.

(3) Modifications of the photogun high voltage power supply were completed and tested with pulsed beam operation up to 7 mA that showed we had eliminated previous noise and ringing problems with this supply.  It successfully demonstrated more that 10 mA supply current.

(4) We did a further test of the injector performance and comparison to theory and believe we now have successfully correlated that performance against bunch length at injection.  See the commissioning results below for details.

Commissioning Summary (Steve Benson and Dave Douglas):

This week was again a short week from a commissioning standpoint.  We had three main goals. The first was to test out the machine modifications made during the Friday and Monday downs. The second was to see if the efficiency at 10 microns was still over 1 kW/mA.  The third was to test out our hypothesis concerning space charge as the cause of the energy asymmetry in the linac.

Checkout of the maintenance changes went well.  Cavity 5 in zone 4 appeared to be quite stable with the replacement of its RF control module.  Small changes in the GU shunts were needed due to a change in the hysteresis procedure.  The biggest success was the gun high voltage power supply (HVPS).  We were able to run high pulsed current with two stacks active with acceptable voltage noise.  This allowed us to run the highest pulsed current to date—over   7 mA.  This was done at 37.425 Mhz so the charge was close to 190 pC.  The pressure in the gun region did not increase very much so the injector setup is good.  We saw some BLM activity at one place known to have large beta function.  At 5 mA pulsed the voltage droop was around    1.3 kV, which is acceptable for pulsed lasing.  Previously we were unable to run over 1 mA pulsed with two stacks of the HVPS working.  The noise while running CW was also reduced and we were able to run over 5 mA with no difficulty at all.

Operation at 10 microns did not go well.  A shorted wire in the motor that controls the pitch of the 10 micron output coupler kept us from aligning the cavity with 10 micron mirrors.  We therefore switched back to 6 microns to test out the new injector setup described below.  The hypothesis that space charge leads to an asymmetry in the energy spread vs. phase in the linac was tested by operating with an injector setup that has a much longer bunch at the linac entrance. This is accomplished by running the second injector cavity 10 degrees off crest instead of the usual 20 degrees and lowering the buncher gradient until a minimum energy is found in the injection chicane.  As predicted, this produced a bunch with a full length of 6 degrees (11 psec). The match to the linac was found empirically but matched the PARMELA solution quite well. The asymmetry was reduced from over 50% to under 20% when this was done, also as predicted by PARMELA.  The pulse length at the wiggler was shortened to approximately 0.5 psec FWHM.  We discovered while measuring the pulse length that steering the electron beam at the Happek OTR makes the Happek scans more symmetric.  Unfortunately the energy spread was larger than we would like.  The rms energy spread was approximately 0.6% and we would like it to be less than 0.5%.  This is best dealt with by operating closer to crest.  We will check this out next week.  Lasing with this configuration was about as strong as the previous configuration but the peak efficiency in the detuning curve was over 1 kW/mA.  This is the first time we have obtained such high efficiency at 6 microns.  The energy spread for this efficiency is still much higher than we would expect.  When we get the new output coupler installed we can see if this persists for a resonator with lower Q.  One difficulty with the new injector setup is that the “ghost” pulses (those that are caused by light leaking through the electro-optic cells) are quite long in the linac.

In general we are now getting excellent agreement between PARMELA predictions and machine behavior.  The measured performance matches the model in detail.  Emittance growth from the linac entrance to the wiggler is the present focus of our attention.

Additional comments from Dave Douglas:

The balanced injector configuration continues to supply excellent injected transverse emittance: the observed value during the linac optics work was around 10 mm-mrad in both planes.
   Last week's discussion of space charge evolved rapidly, and it became apparent that Carlos' PARMELA modeling, estimates, and machine behavior were all quite consistent. The estimates suggested that space charge effects should roll off rapidly with longer injected bunch length; this was observed in further PARMELA simulations, which also gave immediate guidance on how to achieve the longer injected bunch: simply operate unit cavity 3 closer to crest. Steve revised the injector setup in this fashion, and after a bit of optimization determined a) the phase-asymmetry in final momentum spread was reduced, b) the trim settings minimizing the bunch length were close in value to those giving zero M55, and c) the bunch length was reduced to as low as 520 fsec. The FEL lased like gangbusters at 6 microns with the shorter bunch, generating a momentum spread so large that it was not immediately measurable. The recirculator transported the beam back for energy recovery without excessive loss; however, there were however losses at the dump that we did not have time to alleviate before the shutdown for hardware work.  Given the very large energy spread, it is entirely possible we are back to the "momentum spread exceeding longitudinal aperture" situation we had when running at 10 degrees off crest (this setup was at 15 degrees). The losses may therefore possibly be managed simply by raising the exhaust energy slightly and recovering the beam a bit farther out of trough.

The loss may also be related to a separate issue associated with this setup - that of loss of ghost pulses. With the altered injector, the ghost pulse beam from the drive laser is apparently being longitudinally manhandled and injected into the linac with very long bunch length. This is apparent in PARMELA simulations, and manifests itself on the machine as a ghost-pulse beam with extremely large (several percent) relative momentum spread at full energy. The present arc 1 hardware configuration is not intended to manage beams at momentum spreads over a couple percent or so; for example, there is only a single sextupole family presently installed so that nonlinear dispersion is not compensated. The PARMELA simulations suggest that the ghost beam momentum spread will be of order 6 1/2%, and the spread observed on the machine may approach 10%. 
   Simulation and observation of nonlinear dispersion in the transport of the wiggler show 1% momentum offset will yield an orbit with peaks of 1 mm at several backleg locations, and 2 mm just upstream of the wiggler (see Figure below). As the offset magnitude is quadratic, at 3.25% offset (half the spread predicted by PARMELA), the orbit will be displaced a factor of 10 times farther - or ~1 cm at several points and 2 cm before the wiggler - so if PARMELA is right we have a beam that is likely around 1 inch wide just upstream of the wiggler. If our perception of the machine data is correct, the half-width is 5%, so the beam is 25 times bigger than the 1% offset - or 25 mm (1 inch!) at several locations in the backleg and 50 mm just upstream of the wiggler. This should be a problem - and is. We were loss limited by trips not only at the dump (which are likely manageable as noted above) but also by losses at the wiggler. Furthermore, surveys following beam operations indicated that the location of one of the early peaks in the backleg (3F04, see Figure) was activated. We have yet to analyze where any beam that makes it past these lost points ends up after the wiggler.
   It therefore appears that some combination in reduction of ghost pulse intensity, management of the injected ghost pulse distribution, and correction of arc 1 nonlinear dispersion is in order. These steps are under discussion and analysis.

Management:

We prepared an updated status report on our Feb. 6th 10 kW plan that we will be forwarded to the Navy program office and the FEL steering committee next week.

On Thursday and Friday of this week, we participated in DOE's annual on-site review of JLab's operations and long term institutional plans for DOE's Office of Science.

WBS 4 (Injector):

The DC Photocathode Gun continued to deliver 135pC beam for FEL ops during the week

(including brief operation at 190pC).

PARMELA simulations of the injector and propagation through the first accelerator cryomodule continued this week.  A new setup for the injector was tested in the simulations to produce a longer bunch at injection.  Later on that setup was successfully implemented on the machine.

Gun HVPS - The modifications to the Gun's HVPS proved to be satisfactory this week for high current pulsed operations.  This was not possible with the original HVPS as the current controlled driver would cause a large voltage spike(10 - 20 kV) on the Gun.  The new configuration experiences a small droop during the current pulse with less than 1 kV recovery overshoot.  The noise voltage at 350 kV is approximately 70 v p-p.

WBS 5 (SRF)

The rf commissioning of the of the new 3rd cryomodule was completed this week on schedule.  The results are excellent.  The module delivered a gradient of 82 MV with operation on its standard (Zone 4) rf power and control system. It has had two extended periods (6-12 hrs) of operation without rf trips.  Based on last week's measurements on individual cavities, the maximum gradient for this module is in the range of 86MV.  This is the highest gradient module ever produced by JLab.

WBS 6 (RF)

RF - All RF systems are operational.  The klystron powering cavity 4-7 appears to be receiving more reflected power than is expected.  The calibration will be checked and if still a problem, the circulator will be replaced.  The commissioning of FL03 is nearly complete.  The HOM filters for the RF Control Modules are being adjusted.  Measurements are continuing on how best to guard against HOM's in the cavities.  Stub tuners on the HOM ports are being considered.

WBS 8 (Instrumentation):

The beam viewer ITV1F02 was slowed down to try to limit the induced microphonics in the adjacent cryomodule. This viewer was tripping off cavities when inserted and retracted. It did not posses a particularly isochronal motion, but some of the cavities were none the less splenetic. 
   Parts continue to arrive for the cryogenic mirror experiment. We moved "Big Bertha II" into the vault for additional power. Bertha is a 480 to 208 volt transformer  and service panel which plugs into a welding outlet to provide up to 200Amps of additional 120VAC power. This will some the problem of lack of AC power near output coupler precipitated from the lack of an optical transport line. 
   More RTD's were connected and configured for the Optical Dump that was installed at the downstream OCCMS.  These will provide temperature read backs for both the water inlet and outlet.  Additional 4 Wire RTD's were connected and configured to provide temperature read backs for the Scraper Dump water inlet and outlet.  All channels have been tested and are displayed in EPICS.  Modifications to the Optical Cavities Flow Chassis to allow for flow status of both the HR and OC water flow are in progress. 
   The I&C Pre Amp Module (F0295) PCBs have been ordered and are expected in early next week. The Analog I/O Board (F0190) REV_B PCBs for the HVPS Control Chassis arrived from the vendor two will be assembled and tested, one for operations and one for a spare. The new DSP board that we contracted, the design and fabrication is complete and testing has begun. The updated backplanes for the diode thermometry system has been sent out for a 2 week turn. This incorporates the aforementioned DSP as a controller. 
   Revisions of chassis panel drawings were received from EECAD.  They will be added to the current Auto Cad library that is being constructed of objects that are frequently used. Progress continued on the SF6 pump system. Fabrication continued of the 32 channel Video Switcher chassis after receiving the front and back panels from the vendor.    FEL Allsave Data graphing - All of the GSETs and PSETs as well as many of the magnets settings from the archived "Allsave" data for the machine setups has been extracted and imported into a database. Once the data was acquired, a page was written that shows a scatter-plot graph of the channel values and the dates they were made. The page is accessible at: 
http://laser.jlab.org/devlore/FELAllSaveData.asp 
   Configuration Control Database - Searching, and editing tools are being refined, a significant 
update will be posted over the weekend.

WBS 9 (Beam Transport):

Sextupole Lite Re-coiling to obtain higher field

•	The order for the 48 new add-on coils was placed with New England Technicoil for an incentivized delivery in 4 weeks.

Wiggler

###### Electromagnetic Wiggler for 2.8µ

•	As part of the prototyping order, Process Equipment Company (PECo) is doing a test on the cooling plate production method where they will reverse the fabrication order. They like cutting the plates out entirely by water jet and then brazing the tubes on. This reversal eliminates the extra care the water jet vendor takes when a cooling tube is in place. We avoided this earlier because potential distortion mismatch with the pole tips. The developed tacking and brazing method may bypass any distortion.

•	PECo received cooling plate material and is anticipating receipt of conductor material for full water jet production of all components next week.

•	PECo continues machining the core pieces.

•	Ancillary fabricated parts are on order from local shops.

•	In the design area, the assembly drawing is now taking shape and the fastener parts list is good enough to order all fasteners.

•	The shop is cleaning all the parts for new beam chamber for the 2.8 Micron Wigglers before they weld it.

Sextupole (SF)

•	Procurement on hold pending 10 kW efforts

WBS 10 (Wiggler):

The order for the 5.5 cm fixed-gap wiggler support structure was placed Wednesday, March 31. Delivery is 5 weeks as per the schedule.  Magnet and pole clamps are arriving today, also on schedule.  Everything else is also on track and there have been no slips in the schedule.  Lorrie Sanborn calls suppliers frequently and they call her as well if they note any manufacturing or schedule issues.  For manufacturing changes STI Optronics releases ADCN's (Advanced Document Change Notices which are formal red-lines needing project, engineering, design, manufacturing and QA approvals).

WBS 11 (Optics):

Plan A is to obtain low loss 6 um optics.
   We received the new substrates made with the lowest loss material available.  They will undergo metrology today then be shipped out for coating.  We also received the refigured and recoated 92% outcouplers.  They passed all specifications.  One was readied for mounting and brazed last night, but it appears our choice of temperature was a bit too low (160 deg C vs 170 deg C), so the braze parially melted but did not wet the optic.  We are rebrazing it and will install it this afternoon.  New HRs are at the vendor.  We should receive them in about 1 week.

Our three Plan B's had the following progress:

Scraper outcoupler:  The first article was polished and passed flatness (</= 3 waves at HeNe, vs 10 waves spec) and roughness (measured 1 um PV vs 1 um rms spec).  It was ion etched, then gold was sputtered onto the surface.  As this report was being written it was having the water-cooling tubes welded to it.  It will then be installed later this afternoon.  Ancillary diagnostic hardware was mounted on a small breadboard, and will be installed after the scraper installation is complete.  Thanks to the I&C group for working late last Friday to run another beamviewer cable, and for the new RTD readbacks for the extra laser beam dumps.

Cryomirror:

The holder that will thermally isolate a 3" mirror in a 4" holder is finished and ready for installation.  It should be ready next week.  Tom Elliot’s pump system is flowing liquid nitrogen at 8 psi, he feels the very long coil of copper tube is causing excessive pressure drop, and is trying a shorter length to raise the pressure.

George Biallas had this report:

The cryogenic mirror mount design, as it has matured, exposes the entire mirror edge to a thin niobium interface, backed with flowing cryogenic fluids. This interface is a sleeve that extends beyond the mirror. This construction provides radial flexibility that we believe may minimize any distortion caused by differences in contraction during cool down.

•	This assembly is ready for brazing early next week.

•	Sam Morgan, the sheet metal fabricator for the SRF Institute was able to find thicker niobium sheet in our stock pile and he fabricated .010 thick sleeves, on very short notice, to substitute for the .004 sleeves we had formed last week. The thicker sleeve is judged to be suitably robust.

•	The work on the cryo cooling liquid flow continued to advance. Tom Elliot’s pump system was tested and most tubing, valves and controls are on order.

2.8 micron mirrors:  In fabrication.  One each mirror holders for 2" and 3" arrived this week and are being cleaned in preparation for brazing.  more arrive next week.  We received  2" Si HRs, the OCs will arrive in about two weeks later.  3" mirrors are in fab, expected in mid May.

Other activities:

We replaced the drive laser rod for a good spare, and remounted the second spare.  When we pulled the rod that had been in service for over 5600 hours of use, we saw that it was thinner and showed preferential erosion along the crystallographic axes.  We needed to do a more complete alignment than anticipated, but once done we are producing > 16.5 W at our normal operating current, and in excess of 4 W of SHG, all with low phase and amplitude noise.

Besides adding the scraper outcoupler (and the modifications it entailed) and the new mirror, we also replaced all load springs with less stiff versions.  This makes the motors respond better, and should eliminate the failures we've seen.  A motor that developed a short at the casing, preventing us from lasing at 10 um, was replaced.  The wiring in the HR vessel was changed to the new orientation that makes it faster to work on the optics.  A cable tray was mounted on the floor in the OC area to provide a better conduit for the signal cables to the ever-growing number of diagnostics.

The noncontact profilometer that was purchased as part of our JTO contract on laser damage studies was installed, and we are already making use of it to check the ROC of mirrors that are hard for the laser interferometer to measure, and the microroughness of the surfaces.

Terahertz Project:

The M1 and M2 mounts have been modified to accept the phytron actuators, and are being shipped with the M3 and M4 modified mounts to Jefferson Lab.  Fabrication of M1 is nearing completion.