# MEMORANDUM

To:		Distribution

From:		F. Dylla

Subject:	FEL Upgrade Project Weekly Brief – October 25-29, 2004

Date:		October 29, 2004

Highlights:

We have made great progress this week bringing the FEL Upgrade back on the air after the recent installation period:

- an initial injector set-up is in place

- the linac has been phased

- e-beam has been transported from the gun through the linac, first arc, the new wiggler, THz

chicane and  second arc to the beam stop in front of the re-injection point

- the above machine set-up activities have been used to train three new operators

- the optical transport system from the outcoupler in the FEL vault to the Optical Control

Room is under vacuum

Management:

As we check-out the machine and train new operators we are using this opportunity to review and improve all of machine operational procedures and related documentation.

We have confirmed Dec. 16th as the date for status review of the UV FEL project with our AFRL program office.  In the past few weeks, we have made good progress in design of the UV chicane which is now modified to deal with THz mirror heating.

On Thursday, we hosted a visit from four members of the council that governs the American Society of Photobiology.  This group is surveying various light sources around the country for application to frontier problems in the field.

Commissioning (Steve Benson):

We made good progress this week in getting beam most of the way around the machine and roughly phasing the RF systems.  The injector is steered up and ready for the final phasing algorithm.  We discovered this week that we can accelerate the beam through the cryounit at two points in injection phase.  One of them is the one we want.  The other has large losses in the cryounit and quite ratty beam after the unit.  Of course we first found the wrong one.  This provided good enough beam to thread the beam to the straight ahead dump and do transient phasing on those cavities.  Once we found the correct phase for cryounit injection, we roughly phased the injector and carefully phased the linac.  During linac phasing we worked to check out the diagnostics and steering in the backleg.  We found a group of punch list items that are being fixed today.  We should be ready to finish the MPS checkout on Monday.  At this point most systems are functional but not signed off.  Next week will involve system checks so that systems can be signed off.

WBS 3 (Beam Physics):

Work continued on UV transport layout and tuning. A draft design for the linac-to-wiggler transport is more or less complete. Progress has been made on the UV energy recovery transport. Moving the chicane to this region influenced aberration control in an untoward manner, and some effort has been required in learning to balance the various effects. In a preliminary study, it appears that making the chicane in the vertical plane will allow an acceptable balance of chromatic and geometric aberrations. Dynamic chromatic acceptance appears to be 6% or better (we've simulated the recovery of an 8% wide beam), softly limited by phase space distortion during energy recovery, in a chamber with a physical acceptance of well over 10%. The most recent spec from the felman (Friday AM) is  6% "but I'd rather have 7". With this chromatic configuration, noticeable geometric aberrations are induced by the sextupoles, becoming apparent at large, but not enormous, amplitudes. Orbit dependences to the optics will therefore become visible as the beam is steered toward the nether regions of the chamber, but do not appear too severe under normal operating conditions. Investigation of these effects is ongoing.

Machine operations provided training opportunities for a number of folks, got beam through the recirculator for checkout, and once again astounded the audience by presenting yet another longitudinal beam dynamical marvel. During injector setup, it was observed that the beam accelerated at multiple cryounit phases - the "normal" operating phase (where the beam quality was "good") and phases around 180 degrees either way  (where the beam quality was "ratty"). After some acrimony (particularly by DD, who ultimately insisted on putting his fingers "into the wounds", and thus now has bloody fingers), all agreed that the off-phase acceleration was due to a conspiracy of phase slippage in the first SRF cavity. This is readily simulated ("the wounds", so to speak) by solving the equation of longitudinal motion through a 5 cell pi-mode cavity. The nominal acceleration profile through such a cavity is shown below in Figure 1 for an injection kinetic energy of 350 MeV (energy in MeV vs. time in RF periods in blue, longitudinal position in RF wavelengths vs. time in RF periods in pink; note that the energy starts at around 861 MeV because it is full, not kinetic, energy). Both energy and position increase monotonically to around 5 MeV/0.5 m.

Figure 1:


A dephased profile, with the injection time offset by ~2/3 RF period, is shown in Figure 2. The energy (blue) initially sags to nearly the rest energy; the beam slows down (the pink curve of z(t) showing a sag) until the beam is well into the cavity, at which point the energy again rises to 4 or 5 MeV. The beam arrival time at the second cavity is delayed by an additional half RF period - so (with the initial phase offset) it is displaced by a full RF period from the nominal timing - and can be accelerated by the second cavity as well! However, because the beam spends a prolonged time at low energy, space charge (and who knows what other nonlinear electrodynamic effects in the SRF cavity) severely degrades the beam quality.

Figure 2:



Amongst all the other entertainment, we also (inadvertently) found it possible to process a field emitter site off an SRF cavity. For some months, the first injector cavity (of multiphase fame, above) has provided a well-defined back-streaming low current electron beam when at nominal gradient. This could be observed on the viewer upstream of the cryounit.  As of this week, it was also observed to provide fore-streaming field emission as well; the fore-streaming becoming apparent only after installation of the new DESY-style viewer after the cryounit. Using this very sensitive viewer we noted that the emission turned on at around 6.75 MV/m. It was in fact apparent enough to the hardware that it correlated with trips of the arc detectors; pushing the cavity gradient up and down through this point a few times led to some arcing and sparking which, after a few (well, okay, several) iterations provided suppression of the emission site altogether.

WBS 4 (Injector):

The gun continued to deliver pulse beam for machine setup operations during this week.

Support to the THz beamline installation continued during the week.

The Ground ring for the high voltage test stand has been polished and ready for cleaning. Modifications (jack screws) have been made to the top flange of the high voltage test stand for easy insertion/retraction of the coated test tube. A second test tube is being polished to be coated later in the W&M's plasma-source ion-implant chamber. Started polishing work on the ball electrode for the second gun assembly.

The cathode coulomb counter archiver is operational. This will be a valuable tool for cathode lifetime studies. Below is an image of the coulomb archiver for beam run during this week. It shows all the conditions and the totals for charge and time.

Gun HVPS - The HVPS is operational.

WBS 4 – Fig 1

WBS 6 (RF):

RF - All RF systems are operational.

CHL had a planned outage this week and cryomodule FL03 was run dry of liquid helium.  Since the cavity temperatures never exceeded 40°K, there was no Q disease degradation.

The Buncher experienced low LCW flow through a filter and a sticky control valve this week.  The filter and valve were changed and tested today.

The CHL outage and recovery provided a good opportunity for training new operators on how to recover and tune RF cavities.

After recovering the Quarter from arc trips, that were originally caused by wandering beam, an emitter site was burned off.  This reduced the radiation level from the cavity and should help preserve the photo-cathode from back-ion bombardment.

WBS 8 (Instrumentation):

The week progressed with getting the machine into Operations mode. Check off lists were compiled and completion continues of these lists for various diagnostic, instrumentation and magnetic transport systems. The wrong DESY type flag was installed on ITV0F04, this was changed out today and realigned. It was good the vacuum group had time to support this since the shield on the viewer was catching and causing this viewer to hang up. All is good now. Additional viewer electronics (cameras, interface boxes, etc.) were fabricated for the 0G dump, OCR shutter solenoid, THz M1 mirror and new SLM at 4F09. The calibrations for the beamviewers are being done. With the new calibration setup all the different types of viewers around the machine can be properly scaled for the beam profile data gathered with the Framegrabber. Pico motor, video power and video were installed for the OPTS Lite mirror cans. Wiring for the THz M2 mirror was completed and tested. 
    The first article for the User Lab Laser Safety System has arrived. There are going to be a few things we will change for the balance of the 7 units. This one will be mounted to a heavy duty cart and be set up with switches, motors, keys, and shutters to completely simulate a user lab. This will be very helpful when new versions of the PLC code are released and need to be tested without impacting operations. We also received configuration cards for the iClass LPSS card readers (Mifare cards). The cards worked perfectly and the reader is now in the proper mode for LPSS use.  Working on setting up a new laptop with the simulation tools needed to characterize the FEL (for Carlos).
    The Machine Protection System Certification Procedure is undergoing revisions to make it more user-friendly.  The final draft will be checked operationally next week and then a final revision out before the end of November.
    The final "tweaks" are being done to the Analog Monitoring System (AMS), timing, and Video distribution systems. We installed the SVGA to NTSC video converter boxes for the two new scopes (now located remotely in the gallery) and routed them into the video system. These are the scopes named: FELscope01 and FELscope02.  Scope01 is being dedicated for the Happek and M55/M56 diagnostics. To this end, we have re-installed all of the necessary cabling for these systems to operate properly, namely: the connections through the 4Ch. Pre-Amp Chassis and into the digitizer in iocfel8. Also, the AMS was used for the first time in operations this week and we noted the considerable improvement in the over-all system performance from the old system. In using the system we also decided that the o-scope interface that is built-in to the new scopes (felscope01 & 02) is a bit awkward. Since the ops crew has not embraced the web interface (yet) we decided to go ahead and add a GPIB controller to the scopes from iocfel8. This activity is in progress. Six of the seven additional 32x32 AMS/Video Crosspoint Switcher Modules that were being fabricated by FSI Systems have been completed and are on their way back to the lab for testing. An additional AMS chassis has been fabricated and checked out as ok, and is on its way to ECAAD for documentation.
    The Multipass BPM system is progressing. The 4 channel programmable timing module in iocfel3 has been fully tested and is ready for initial testing late next week under real-beam conditions. This timing module will is synchronized to the master oscillator (/40) at 37.425MHz and then further divides that signal down to 1.17MHz. When we run beam at a matching micropulse frequency of 1.17MHz, the system will be able to separate the Accelerating and Decelerating beam pulses to make independent measurements of beam position for each.
    We have been working to update the configuration control database accessibility from the internet to restrict access to certain information based on user-authentication. We will change the site to require a valid JLAB user-login before ANY information is made available. This change should be posted by COB today. The more time consuming approach of having some areas public will be done as time permits.

WBS 10 (Wiggler):

The wiggler viewer cameras were set up and properly focused and steered so that optical alignment could continue.  The wiggler power supply control code was tested with the power supplies active this week and worked flawlessly.  The plexiglass cover is being installed today and the Earth's field compensation coil will be set.  We will then be ready for commissioning with beam next week.

WBS 11 (Optics):

2.8 and 1.06 micron mirrors: 
The 2.8 micron HR and OC mirrors are installed and their figure checked in-situ.  After a hot nitrogen purge, we will start the ion pumps and be ready for lasing.  No change in status for the 1.06 micron coatings; the vendor is awaiting receipt of the specially backed aluminum target.

Other activities:
We continued to make great progress.  At this writing, we had repaired wiring for position readbacks for mirrors we will use in the near future.  We're installing absorber plates that will capture the light that would otherwise be absorbed and scattered off the mirror mounts.  (We measured the reflectivity at 10.6 microns to be 0.3%.)  We aligned the optical transport (OTS Lite version) to the vacuum valve in User Lab 1.  We also pumped the OTS down, and are chasing down a few leaky connections.  Work continues on a new, fast scanning (~ 10 Hz) autocorrelator progresses, as does the design for the optical beam positioning system.  We discovered the gratings for the spectrometer that will be used for the FROG (pulseshape measurement) setup were out of calibration, and we realigned them.

Terahertz Project:

The M2 mount was tested, and the M2 and M3 mirrors were successfully installed. Discussions continued to define the instrumentation requirements of the laboratory.