MEMORANDUM

To:		Distribution

From:		F. Dylla

Subject:	FEL Upgrade Project Weekly Brief –April 4-8, 2005

Date:		April 8, 2005

Highlights:

This week we re-established operation of the FL03 cryomodule after in-situ window surgery. The module appears to have recovered its operation from before we shut down, delivering approximately 50 MeV.  With the total energy now available we should be able to run full power at 1.6 microns and longer.  Quotes have been received for high power mirror coatings for this wavelength and we are preparing the order.  We will re-establish beam operation for lasing starting 0700 on Monday.

We hosted 150 attendees at the 6th International Symposium on Laser Precision Microfabrication 2005 in Williamsburg, the first time this conference has been held in the US.  The JLab FEL got some great publicity from P. Schaaf of Gottingen, Germany, showing the major advantages of nitride coatings produced by the FEL over conventional lasers.  We also got to show off the new Laser Microengineering Station for UV after assembly by Aerospace staff.

The IR wiggler gap mechanism passed final design review with only a very few minor action items.  We look forward to receipt of this system in late summer.

Management:

We passed the 90% drawing review for the Injector Test Stand facility modifications.  We expect to be out for bid in 4 weeks.

We also approved the final design of two trailers to house staff across from the FEL.

We established a tentative installation schedule for UV components on the beamline.  This will entail one week in late May, June, and July, and two weeks in August.

WBS 3 (Beam Physics):

Activity Summary

The RF recovery period has provided an opportunity to ponder the design of a compact driver for a high power FEL. We have a rough optics solution for a machine with the following characteristics:

11 m long 748.5 MHz 6 (five cell) cavity module

30 x 3.3 cm period wiggler (99 cm); 0.4 m nominal betatron envelope at center of wiggler

16 m optical cavity

These features were suggested to me by three people whose opinions I very much respect, but who may not agree with one another, or, for that matter, with any randomly (or deliberately) selected additional parties. Any and all of dissenting opinion are invited to participate in a celebrity cage match; I will gladly follow the instruction of the sole survivor.

The resulting driver system is ~2 m x 20 m in footprint (Figure 1).

Sequentially, following the injection point, we allow

1/2 m utility slot

11 m module slot

1/2 m utility slot

1 m slot for extraction/recirculation

quad triplet

3 dipole mirror bend

quad triplet

4 dipole chicane around upstream end of optical cavity

quad triplet

wiggler

3 dipole THz management chicane (this can be skewed for BBU control if needed)

2 dipole mirror bend

4 quad injection telescope (might be compressed to a triplet)

1.5 m slot for reinjection chicane

for a net of 12 dipoles and 12 quadrupoles (plus some assorted smallish magnets

for injection, extraction, orbit correction, etc.).

The extraction/recirculation & reinjection chicanes may be compressible, provided the adjacent quad triplets admit transverse displacement for appropriate steering of the recirculated beam. This may save order 1.5 m in length, though it will introduce some operational complexity that may cloud the immediate value of the space savings.

A "staircase" injection line clone of the JAERI line (similar to the CEBAF spreader/ recombiners) is under consideration; it will put the 748.5 MHz injector parallel and near to the linac axis just beyond the energy recovery arc. This design attempts to incorporate information from discussions at the ERL workshop; a reasonable but unoptimized optics solution exists and awaits vetting by spacecharge simulation. The need to manage THz radiation drives bending immediately after the wiggler (as far as possible from the downstream optics); this in turn encourages use of a fairly short return arc, clearing the energy recovered beam well before the downstream end of the optical cavity, even for

the relatively short 16 m cavity under consideration.

In consideration of the optical cavity length, we note that the "nearest" pure (divides by 2) subharmonic lengths of 748.5 MHz (0.4 m) are 25.6 m (64 RF periods) and 12.8 m (32 RF periods). Those considering a 100 kW class FEL based on the shorter cavity length are invited to follow guidance provided by

http://mentalhealth.about.com/cs/psychopharmacology/a/antipsy.htm

The longer cavity could in principle wrap completely the accelerator footprint, but in practice would result in only modest parts reduction (the upstream chicane would go away, but additional quads would likely be necessary to handle the beam from wiggler to energy recovery arc; the THz chicane is needed in any event) and, because of the length contribution of that pesky injector hanging off the front end, might actually make the overall footprint a bit longer than were it embedded in the upstream end and hanging out on the injector side. Intermediate subharmonic cavities (such as the selected 40th subharmonic 16 m cavity or a 50th subharmonic 20 m cavity) can be similarly accommodated).

Reasonable optical solutions were developed for the injector (as noted), both passes through the linac. A not unreasonable solution has been developed for the energy recovery arc. A preliminary, unreliable, inaccurate, and thoroughly state-of-the-prior-art model of this line suggests, oh, a 10+% relative momentum acceptance. A rough and similarly unreliably studied solution for the transport from linac to wiggler has been developed; it needs work but shows some promise. I'd include the obligatory beam envelope plot, but the data are scattered across about half a dozen different DIMAD runs and its lunchtime...

Figure 1: Footprint of compact driver for 100 kW system.

WBS 4 (Injector):

We are designing a NEG coating apparatus large enough to coat the gun chamber as well as the UV optical can. This facility will be installed in our ARC lab being prepared now also with a clean area for gun assembly. 

In an effort to understand the discrepancy on the cathode QE measurements observed earlier between the cathode scanner and the drive laser, we have done some calculations to see if the drive laser can be used to measure the QE when the cathode bias is only 200V. The calculations show that as long as the photocurrent stays below the space charge limit for emission (500 nA at 75 MHz rep rate), we should be able to make the measurement by attenuating the drive laser power down to ~100 micro Watts on the cathode. We are planning to perform this measurement early next week. 

On Thursday the photocathode gun was tested successfully to full operating voltage (350 kV). The cathode QE is around 1%, which should be sufficient for tune up beam operations.

WBS 5 (SRF):

- Three of the four 750 MHz cavities gone through the first CMM QA check and two are proceeding through the chemistry and heat treatment processes.  Flange seal parts are due in next week in order to support VTA testing activities.

- A coordination meeting was held at AES & JLab this week in order to coordinate fabrication activities and the design plans for accommodating the inclusion of the third harmonic cavity.

- The return end can assembly is complete. Final checkout is planned for next week.  Fabrication of the supply end can was started this week with tooling setup.

- Procurement progress, for cavity string components, remains on hold until AES receives their funding for this project.

WBS 6 (RF):

All systems were checked out for operation next week.  Everything successfully passed.   We repaired some water hoses that were aging.

WBS 8 (Instrumentation):

The focus this week was to complete hot check out of the I&C systems to support operations beginning Monday 4/11. We have been supporting the re-commissioning of zone 3 for a good portion of the week. Aside from these activities we are getting parts on order to support the source team's effort to sputter NEG material in large chambers. This will be used in both new gun chambers and optical cavities. Discussions continue on how to get the required trim channels and what the field reproducibility will be for the iron core quads. We have a few backup options, stay tuned... 
   While working with Roger Flood from EECAD on the RF-DC Carrier Board and the

4-Ch Filter Board it was decided that it would be more cost effective as well as a better engineering solution to incorporate the 4-Ch Filter Board into the single channel RF-DC Linear Converter PCBs.  This will save the cost of two extra connectors, the Filter Board PCB, and provide a better packaging design for structural support for each of the RF-DC Converter PCBs.  The new RF-DC Linear converters with the filters will be setup for 1.497 GHz RF signals with a 30 MHz bandwidth.  Plans for remote attenuation variations is also being examined as this may be useful for the various types of BPMs implemented throughout the FEL.  Several evaluation boards have been ordered to examine the various component parameters.  The first draft of the 4-Channel Carrier Board has been completed by EECAD.  The carrier board completion is currently limited by the design of the enclosure for the carrier board and the RF-DC Converters, which is underway. 
   Construction of the THz hutch in lab3 continues.  With the last week's delivery, 90% of the skeleton of the hutch has been completed to date.  The few remaining support beams were received from the machine shop within the last day, and will be installed by Friday 04/08/05.  Side panels have been trimmed and measured for mounting hole placement. Installation of LPSS hardware on the lab 4 inner doorway is in progress. Two pairs of Sentrol position sensors have been installed.  All remaining parts for entry control and status for the doorway have been ordered.

IOCFELT2 in Lab 5 is now back up and running. This is our dedicated AMS/Video test IOC. Getting all the pieces back to functional order took-up most of the week, but we were successful and were able to fully test-out our first 32 channel video chassis yesterday. Now that the testing hardware and software have been put through their paces, we will be able to test out the rest of the chassis quickly. 
   We have met with Pavel, Carlos, and Nobuyuki to review to LabView Multislit program that Pavel had developed for the ELBE radiation source at FZ Rossendorf.  The IMAQ module used by LabView for the image manipulation is not available for Linux (our frame grabber runs on Linux NOT Win...). N. Mather, an applications engineer at National Instruments, stated that there are currently no plans for porting IMAQ to Linux.  Other routes for the image manipulation are being researched.  The epics2devlore system is being configured to run on the OPS workstations as well as Linux for testing purposes. We are beginning to convert from EPICS 3.13 to 3.14, first on development machines. 
   Mike Dickey is putting together the drawing cross-reference data for the UV line (Regions: 6F, 7F 8F & 2V), we are importing the "full" document control drawing list into our controls database to incorporate his drawing cross-reference data as a way to navigate the controls database. The Document Control Group's (DCG) MS-Excel "Mechanical Drawings" spreadsheet file has been imported and the methods of setting up pointers is being pursued. 
   There was a design review video conference with STI concerning the new wiggler jaw assembly. On the controls side there were no significant issues. The previous patch cable for the GPIB control cable for the AMS - felscope2 oscilloscope has been replaced with the permanent installation cable.  The 4-Ch Pre-Amp chassis was modified to handle the Happek signals generated by the two different power supplies that are currently used.  The chassis was tested and the modifications are being reported to EECAD for documentation.  Preparations were made for the LPM Consortium Tour that took place this past week as well as for the upcoming JLAB Open House.

WBS 9 (Beam Transport):

Sextupole (SF)

•	Fabrication is continuing at New England Techni-Coil. Core parts are starting final machining. Coil winding form and mold are in manufacture.

Replacement Chicane Dipoles GW)

•   Fabrication is continuing at New England Techni-Coil. Steel core pieces for the third and fourth set of two dipoles are done. The first coil is being prepared for potting. The fourth of eight coils is wound. They are starting work on the Purcell Gap piece glue down procedure.

UV Line

• 	We started testing a QX Quadrupole with a linear ramp hysteresis loop in a number of runs to gain reproducibility data.

• 	Tim Whitlatch has an idea to insert NEG cartridges into the downstream corner chamber, eliminating the bake requirement.

• 	The 3 of five sub-regions layouts of the UV branch (less the chicane) received comments and are being prepared for signature. They continue the designs of the four stand and girder types that we don’t have.

• 	The next priority item to sign off is the stand placement points so that the Survey and alignment folks can start laying out the stand positions – no progress.

• 	Advanced Energy Systems submitted the stand drawings of the stands GW chicane for checking and they are authorized to start detailing the four chambers.

•	The Jlab Shop continues modifying the prototype SC Sextupole to the new SS configuration that meets David Douglas’ criteria.  Tommy Hiatt is poised to put it on the Test Stand the Week of April 11 to verify the quality.

UV Wiggler Progress

• 	Argonne National Lab working up a preliminary cost for the Chamber and have sent it to their business office to add the Overhead costs.

WBS 10 (Wigglers):

The Final Mechanical Design Review for the 5.5 cm period variable gap wiggler as held this week.  The detailed design looks good.  A few minor suggestions were made.  STI Optronics should be able to send out the order for the strongback next week.  They have received the Heidenhain gap gauges.  They tested the gauges and found an accuracy of 0.2 microns over their entire range.  We determined that, with a new routing of the cables, a 68 foot cable length would work.  Routing the cables through existing cable trays requires an 80 foot length.  STI Optronics is exploring whether 80 foot cables are possible to obtain. 
   All documents for the source selection board for the Cornell wiggler modification had been signed off.  All vendor questions have been addressed so far.  We have established a design for the vacuum chamber that the engineer at Argonne agrees they can build.  Argonne has finished the initial pricing effort for the vacuum chamber.  The final price estimate should be available next week.

WBS 11 (Optics):

FEL mirrors:

A procurement request for 1.6 micron high power coatings on our existing substrates was released today for award.  This is the wavelength we believe should have the best performance given the available machine energy, wiggler parameters, and optics capability. 

Metrology continued on the cooled mirrors for the optical transport system to prepare us for providing light for Navy and other users in the near future in Lab 1. 

We performed a readiness checkout of the optical systems in preparation for running on Monday.  All systems go. 

The group attended the Laser Precision Microfabrication Conference to get up to speed on laser capabilities and techniques of other groups, especially the strong industry efforts in Europe and Japan.  This has strong relevance to our efforts in material studies and modification as well as reliably controlling high power beams.

Terahertz:

Work continued in Lab 3 on construction of the hutch and safety interlock systems.  Specifications were drafted for a vacuum chamber for pump-probe experiments.