# MEMORANDUM

To:		Distribution

From:		F. Dylla

Subject:	FEL Upgrade Project Weekly Brief  - January 31 – February 4, 2005

Date:		February 4, 2005

Highlights:

We completed a very successful series of beam break up (BBU) experiments thanks to the efforts this week by Chris Tennant, Eduard Pozdeyev, Dave Douglas and Steve Benson. The work that we proposed more than a year ago (at the Oct. 2003 TAWG meeting) to our Navy program managers and FEL colleagues on this important topic has been completed. A brief summary is given below by Chris and more extensive analyses will appear in Chris’s upcoming Ph.D thesis and follow-on journal articles. As with all good experiments we believe we will be returning to this important topic of analysis and suppression of current limiting modes on srf accelerators as beam time schedules permit.

We also had our first look at lasing with the broad-band output coupler that was installed at the end of last week by the optics team.  We successfully lased at 2.8 microns at 80 watts cw which In addition we had an initial attempt at lasing at 1.7 microns with the same broad band optics.  We are just beginning to learn some interesting things about the effects of cavity astigmatism on FEL performance as indicated in Steve Benson’s report below. Testing of the high power

1 micron optics (which were also installed last week) is planned after we re-set up the machine for 140 MeV operation starting next week now that the BBU experiments are completed.

We continue to be very pleased with performance of the photogun. The gun has delivered cw currents over 6 mA for the BBU experiments and has also delivered more than 400 coulombs since the last recesiation. This record more than doubles our previous record. We believe the increase is due to a combination of improved vacuum (already in the 10-11 torr range) and a change in the type of GaAs we now use for the cathode.

Management:

We held our monthly meeting of FEL team WBS managers with the Project Management office to review the monthly cost-schedule performance for January for both the Navy and AF programs.

We had to re-adjust our FEL run schedules for February to due requested down-days by the Accel. Div. to support central helium liquefier tests today and the a series of maintenance activities the week of  Feb. 14th.

We had a meeting with the ME group this morning to check the detailed engineering layout of the magnetic components in the UV chicane in the first complete translation from Dave Douglas’s DIMAD file.

Beam Operations:  (Steve Benson and Dave Douglas)

The first half of the week was spent supporting BBU measurements.  This went well with the exception of an uncertainty in our current measurement.  At the threshold the current monitors agree, but they disagree at high currents.  We were able to run up to either 6.5 or 8 mA with the phase rotator depending on which current monitor you believe.  We will be taking more data on this next week to pin down the current more accurately.  More details on the BBU are given below. 
   On Wednesday we recovered the 88 MeV lasing configuration and lased with the new hole-coupled resonator.  We were able to get up to 80 W from the FEL at 2.8 microns and found that the laser started to mode hop near the peak of the detuning curve.  This is what one expects for a hole coupled resonator.  The mode tries to avoid the hole.  The higher order modes couple less strongly to the electron beam but have lower losses.  At small detunings they have enough saturated gain to lase. 
   We then raised the energy to 115 MeV, phased things up and matched to the wiggler.  We obtained weak lasing at 1.7 microns.  The transverse match in the wiggler was not nearly as good as the 88 MeV configuration and short wavelengths are more sensitive to the match so we think that stronger lasing is possible. 
   On Thursday we spent more time optimizing the FEL at 1.7 microns but were unable to obtain lasing with the newly optimized cavity.  We now have a procedure that should make lasing at the shorter wavelength easier. 
   One sidelight discovered last week is the sensitivity of the FEL to astigmatism.  This is a subject that has not received any theoretical analysis to date.  I applied a simple model to estimate the dependence of the laser gain on the astigmatism vs. the FEL cavity parameters.  I found that the sensitivity to astigmatism varies linearly with the cavity magnification.  The magnification of the new cavity is a factor of 5 larger than the cavity for the optical klystron.  The astigmatism, seen in the resonators for the optical klystron, should not have had any affect on laser operation.  The same astigmatism is a much stronger affect in the new 2.8 micron,

1 micron, and broadband cavities and so one might expect that the gain or efficiency is reduced.  The curious thing is that we have not seen any evidence for astigmatism in the mode on the mirrors.  Again, there is no theoretical analysis of the effect of hysteresis on the FEL so we don't know if we should see something or not.  It could be that the FEL reactive gain modifies the mode to keep a circular mode on the mirrors.  The good news about this is that the dependence on astigmatism depends on the cavity magnification but not on the wavelength.  This is good for the UV but may be a problem for short Rayleigh range operation.  We are looking at ways to reduce the astigmatism in the mirror we now have to be at least a factor of 5 smaller than what we had in the optical klystron.

Summary of Beam Breakup (BBU) Experiments (Christopher D. Tennant)

This week marked the conclusion of an incredibly successful run of BBU experiments at the FEL. There were two primary goals of our activities: (1) thoroughly characterize the BBU instability and (2) exercise several BBU suppression techniques.

As to the first, we used an 88 MeV configuration for the FEL in which we could directly measure the threshold current for stability to be 2 mA. Once BBU was observed, we identified the frequency of the offending mode (2106 MHz) - which agrees with earlier BBU simulation results. Data were taken in pulsed beam mode for several macropulse currents as an alternative method of measuring the threshold current. One of the critical measurements was the ability to perform difference orbit measurements to characterize the recirculator. With this information in hand, BBU simulations can be performed and compared with our experimental measurements. This benchmarking of the codes is of great importance.

The second goal was to exercise suppression techniques to raise the threshold current of the machine. There were two categories of techniques applied: (1) external Q-damping methods and (2) beam optical methods.

One of the Q-damping schemes involved an active damping circuit. We were able to decrease the Q of the dangerous 2106 MHz HOM by a factor of 5. Using a beam transfer measurement we were able to verify that the threshold current increases approximately by a factor of 5 (as expected because of the 1/Q behavior of the threshold current). The second damping scheme utilized a 3-stub tuner. Although not quite as effective as the previous method, we were able to damp the Q by a factor of ~1.5 and observe the corresponding increase in the threshold current.

The final suppression techniques applied involved changing the electron beam optics. The first method involved activating the local reflector in the 3F region of the FEL. This reflector exchanges the horizontal and vertical phase spaces so that, for example, a vertical kick from an HOM on the first pass is coupled out to a horizontal displacement on the energy recovery pass. In this way, the beam can not feed energy to the HOM and create BBU. With the reflector activated we could immediately increase the threshold current by a factor of 5. By additionally changing the phase advance, we could completely stabilize the 2106 MHz HOM. The second beam optical method required using the so-called “phase trombone”. As the name implies, this method allows one to vary the phase advance of the beam and change the threshold current. With only a change of a few hundred G-cm in quadrupole strength, we could go from decreasing the threshold current to less than 1 mA to completely stabilizing the 2106 MHz mode (i.e. it can no longer cause BBU).

WBS 4 (Injector):

The photocathode continued to deliver CW and pulse beam at 135 pC for FEL ops. There has been no need for re-cesiation since this cathode was made on Dec 17, 2004. The total delivered charge is still in question, (but is at least greater than 400 coulombs) since there is a discrepancy on the current readings reported by the High Voltage Power Supply and the 1G Dump current monitor. We are working closely with the I&C, High Voltage Power Supply and FEL ops teams to resolve the issue. 
   Drawings for the new segmented support tube for the second gun assembly are almost complete. The W&M ion-implant team is preparing the plasma chamber for testing the coating process on 12"-long stainless steel tubes. The goal is to eliminate arcing during the implant run observed on the full length support tube (34" long).  Material for manufacturing the segmented tube will be received on Feb 17th. 

   Work continued this week preparing our new lab in the ARC building by making more available space. Most of the materials for the clean-room area have been received. DI water and fire-proof ultrasonic systems have been ordered.

WBS 6 (RF):

The RF systems are operational.  HVPS is operational.

Please refer to Summary of Beam Breakup (BBU) Experiments for RF activities.

WBS 8 (Instrumentation):

Ohm's Law dominated the discussions this week while we were operating. There is a rather large discrepancy in the current measured at the dump compared to the high voltage power supply. The 10 MeV recirculation dump is loaded to ~ 30 ohms, the reading is larger than the HVPS so a remote calibration technique was added so it can be confirmed while running. A DC current source in the control room was used to null the current at the dump, this was done in a number of different configurations and the current always came out higher than we would expect. We are looking into adding a current transformer to the 2F region, which would be a nice addition to the FEL diagnostics suite.
    Last week’s implementation of the Machine Protection System (MPS) interlocks to protect the optical power meter (OPO1V00) required further editing. We realized very quickly (during Ops) that the new MPS updates we installed last week were *too* restrictive and had to be masked to proceed with ops. After reassessing the situation and agreeing on what the right functionality should be, we were able to update the MPS again and be fully tested and back on the air for the evening shift thanks to the respective persons making themselves available when the first window of opportunity came. 
    The Configuration Control Database (Devlore) upgrade: a lot of effort was placed this week on ensuring a smooth delivery of the new controls database interface. It was not without its obligatory transitional glitches, but these were quickly ironed-out almost immediately as they were discovered. It appears that the new system is running stable with its 1st week of prime time use. We are now working on taking data from the FEL server (FELSRV1&2) and importing directly to a spread sheet. The first version will be triggered by the completed bunch length measurement (Happek scan). The data that will be passed is all RF phases and gradient as well as drive laser parameters, quad & sextupole strengths and the bunch length. This data will be a single line in a spread sheet that is available for down load from laser.jlab.org as a .xls file. 
    The PC that we have been using to provide online FEL EPICS status (top-right video feed (from http://felaxis02.jlab.org:1497) has been infected with as rather pesky virus (no flu shot) and is being serviced this week. It should be back up by COB today.
    Documentation has been completed on the Beam Current Cavity Monitor PCB enclosure, these can now be sent out for fabrication quotes.   The Beam Current Monitor PCB-F0322 final corrections have been submitted to EECAD as well.  A first draft design for a general purpose RF-DC Linear converter for applications in various RF instrumentation systems throughout the FEL has also been submitted to EECAD for documentation.  The carrier board for these cards is also under design and should be ready for documentation next week.  The 2-Channel RF-DC Converter Box for the Button BPMs has been completed and installed at the entrance to the 2nd Arc.  The box has been tested with general signals for functionality testing and some data from actual beam signal has been seen. 
    Fabrication continued on Beam viewer cameras with a total of 15 operational for spares and the UV upgrade. Effort began on increasing our spare and UV inventory of pc boards with the Comparator Isolation Module for the MPS breakout chassis and VME Beam Loss Module boards.  A meeting was held with DC high Power group to identify and order high current (100-350 A) reversing switches for the UV upgrade. Currently, we will need at least four (with 2 spares) 350 A switches for the UV line and researching the idea of using H bridges for the 50V 100A power supplies for the sextupoles. LPSS commissioning has begun for Lab 3 with the new card reader and software.  Effort has begun on the hutch enclosure for the THz experiment also in Lab 3. With the scheduled CHL trip, the I&C group took advantage of the short down period to perform some maintenance activities. With the installation of the ND filters, SLM4F09 is complete and tested. The control software has been modified and screens updated. Replaced Viewer cameras at 0F06, 5F07 and 5F10 and re-aligned various viewers in the 3F region.
    We are making good progress on the Laser Personnel Safety System (LPSS). The THz lab system is close to being certified but we still need to get the hutch built. Lab 1 is waiting on installation of the turning mirrors, these have the same motors and limit switches so it should not be a problem. The alignment mode chassis will be re-certified early next week.

The new card reader system was incorporated into the old LPSS for preparation of the certification of lab 3.  Also an Ethernet connection was established to the new LPSS master.  We are researching the FINS commands used for EPICS PLC communication.  
   Parts are on order for additional Beam Loss Monitor circuit boards, the remaining AMS upgrade chassis and the Video upgrade chassis.  Four new monitors were installed in the control room replacing some older TVs that were being used to monitor the beam.

Patch cables between the Drive Laser Enclosure and the Optical Control Room and the Operations Control Room have been installed, but still require final termination and checks. Thanks to Wes and Dan for attending SSO and ARM training.

WBS 9 (Beam Transport):

Sextupole (SF)

• 	Fabrication is continuing at New England Techni-Coil. No change in status while materials are on order.

Replacement Chicane Dipoles GW)

•   Fabrication is continuing at New England Techni-Coil. Steel for two of the four magnets is in the roughing state such that heat treat can take place over the week end after next. Finish machine follows that with the next two magnets material following by a week. Winding will begin next Monday. Field clamp machining starts next week.

UV Line

•    General check layout against the DIMAD from David Douglas was completed with the change-over in designer responsible for that. Now that the main magnetic elements are fixed, the designer is working with Dave Douglas to position the diagnostic elements at places where the position information or the viewer spots shapes are at their best balanced against not interfering with the magnetic elements. The effort is also attempting to put everything on girders in a standard way.

• 	With regard to our plan to regain our schedule slip, the ME Group has taken a long look at the tasks associated with this effort for both electron and optical beam lines and now has a plan in place to utilize the resources to get the effort done on time and in an efficient manor. .

• 	The contract to magnetically model the conversion of the SC sextupole to the SS sextupole was placed with DULY Research

• 	The faster PC workstations are due for delivery

• 	Tim Whitlatch continues to make progress in the vacuum analysis and design duties

• 	The statement of work to send the dipole chicane stands and vacuum chamber to an outside firm for design is at the checking stage.

•   Design of the upstream corner chamber was started and will most likely be complete by next week

Injector Multi-slit upgrade

•   Parts are out for fabrication and due February 21.

UV Wiggler Progress

•  The wiggler outline drawing was generated from the alignment group data and along with a representation of the OCCMs, the full size outline was pasted to the floor in the vault. From that we could see we have plenty of pit room to service the OCCMs (which are mounted vertically down off the beam line in the pit.) We see that we can also use the existing pit filler block system, moved over by about 6 feet to within 18 inches of the wall to maintain a corridor for movement past the wiggler.

WBS 10 (Wigglers):

Argonne has agreed to supply extrusions and drawings for their undulator A vacuum chambers.  This should ease the design of these chambers and may significantly reduce the cost.   The wiggler pit layout was laid out and the overall design agreed upon for the UV wiggler. 
The IR wiggler upgrade procurement is just about ready to go out.

WBS 11 (Optics):

2.8 and 1.06 micron mirrors:

During the open period last week we retrieved another 2.8 micron HR and after inspection will mount it on another mirror deformer.  We'll install it during the down commencing the 14th.  The 3" dia 1.06 micron HR and OC met all specifications.  The HRs exhibited shallow pinhole flaws not seen on the OCs.  These flaws are very similar to those seen on other HR mirrors, but the dielectrics and deposition techniques are different, so why they exist is currently unknown.  We are discussing it with the vendor.  The 2" HRs were a bit longer than the ROC spec, but since we can correct the ROC, we'll keep them and mount one on a deformer.

Other activities:
This week was devoted to supporting operations and preparing to install components that will bring FEL beam into User Lab 1.  We were pleased that we lased on our broadband optics set.  With the laser wavelength moving into a region shorter than our IR cameras can image (except as heat), we added visible cameras to the HR and OC assemblies.  We began planning a set of measurements of outgassing rates for common materials used in our assemblies, so we can get a better handle on how to leverage our pumping speed.  This has a direct impact on the UV FEL.

#### UV FEL

We mounted viewports on the beamline viewer from I&C, and will test the ability of its flag to scatter (rather than reflect) HeNe light.  We received the prototype gimbal mount and began testing it for short and long term stability.  Since this is in air, and with multiple bounces (to get pathlength) it is hard to separate its contribution from the other mounts in the system.  Nevertheless, these first measurements were encouraging.  Discussions were held on modifications to improve it, and to add position readbacks that would be compatible with the UHV environment.  Our analysis effort on the cryogenic mirror flow parameters is progressing, we hope to start some measurements (at room temperature) to confirm we don't have vibration issues.  We are learning that there is a lot of discrepancy between different literature values of the material properties of sapphire, and held some discussions about doing some measurements in-house.

Terahertz:

The phase 2 postdoc position hiring process continued, the spectrometer operated in lab 3a, and discussions took place regarding THz ports on the chicane for the UV FEL.