MEMORANDUM

To:		Distribution

From:		F. Dylla

Subject:	FEL Upgrade Project Weekly Brief – March 21-25, 2005

Date:		March 25, 2005

Highlights:

This week was another extremely busy week as we time-shared between the ERL Workshop held on-site and the activities in the FEL vault to change-out the rf windows in the FEL-3 cryomodule. Both activities went well.

As of this afternoon we are pleased to report that we successfully changed out 3 rf windows on the FEL-3 module and the cavity assembly within the module has been returned to ultra high vacuum levels (~10-9 torr) in preparation for cool-down early next week.  We plan on rf testing of the module late next week which would provide the true measure of the success of this venture.  We note that the portable clean-room that was designed and installed around the module attained Class 10 conditions (which exceed the standards in our production clean rooms). Also the heated, clean nitrogen purge gas system which we designed for venting the module during the window change-out and subsequent clean-up after window replacement appeared to work well.  The entire operation has gone according to plan to date and we thank the SRF team for their competent execution.

The Energy Recovered Linac (ERL) Workshop held from last Friday until this Wednesday provided a unique forum for over 150 attendees to discuss all aspects of ERL design, construction, application and application. The milestone demonstrations of the IR Demo and FEL Upgrade were recognized as precursors for the increasing world-wide activities based on this technology.  We were pleased to see that engineering activities are proceeding at both the Cornell and Daresbury ERLs that are providing supporting information back to our projects.  The full workshop proceedings will note the array of on-going and proposed new devices and include summaries of the working groups on injectors, transport systems, hardware (rf, cryo,etc) and diagnostics. You will note additional remarks about the ERL workshop from the system manager reports given below.

Highlights of other activities this week include:

-	a visit by the Dahlgren group for initial set-up of their laser materials damage experiment

-	progress on the assembly of one of the Turning Mirror Cassette assemblies for the “full-up” Optical Transport System

-	completion of the design of the sextupole magnets for the UV FEL

-	excellent progress on the IR PM wiggler motion and vacuum systems

-	assembly of the (long-awaited) “multi-slit” diagnostic which will be installed in the injector line for beam emittance measurements

Management:

We used the ERL workshop to advantage to engage with useful discussions with many of our collaborators and vendors who attended.

Initial preparations were made for display material and tour logistics for the Jefferson Lab Open House which will open up the FEL Facility to the general public on April 16th.

Gwyn Williams attended the American Physical Society meeting in Los Angeles, the largest physics meeting in the world.  He co-chaired with Alan Todd (AES) a special focus session on Applications of THz Radiation, which was well attended. Larry Carr (from BNL) presented the JLab facility in his overview talk on high power sources. Gwyn also met with Mark Sherwin and Mike Martin to talk about the National THz Science and Technology network of which Mark is head.

WBS 4 (Injector):

We participated in the ERL Workshop this week with two presentations and plenty of discussion on cathodes and DC Gun technologies. 

We supported Cornell activities on testing one of their electrodes in the High Voltage Test Chamber. 

Work continued this week setting up the clean area in our new lab in the ARC building. 

We hosted a meeting with Dr. Kiangyang Lu from Peking University on High Voltage DC Photocathode Guns. Dr. Lu has a hybrid DC gun SRF injector under construction in Peking and attended the ERL Workshop.

WBS 5 (SRF):

This week the SRF design team got a chance to measure ourselves against the competition, so to speak, at the first international ERL workshop, held at JLab. We presented our high-current cryomodule concept in public for the first time (our FEL technical reviewers had seen some of the work before but for many it was new). We also showed the latest calculations on expected HOM damping for various cavity shapes and damping methods. The material was well received and there was lively discussion in all of the working group sessions. The conveners accepted our findings that it was possible to achieve good HOM damping and accelerating mode efficiency at the same time, and included this in the working group summary. They also took note of our warning that HOM power handling is at least as important as BBU threshold when optimizing these structures. Of all the designs presented ours showed the highest packing factor and potential real-estate gradient. There was also healthy debate about power couplers, especially topical at the moment, with opinion split between coaxial vs waveguide couplers. Since we are pursuing high-power variants of both types, based on proven SNS and B-factory technology respectively, we should be in a good position to select the best choice when the time comes. 
    The ERL workshop aside we have converged on two waveguide end group options that we wish to test, one with four damping waveguides on each end, as previously shown to the review committee, and another with three. The three waveguide option seems to give just about as good HOM damping as the four-pack (better for some dipole modes), with simpler mechanical layout and less static heat leak. We plan to make copper models of each type to measure on existing copper cavity models. We are still comparing cavity cell profiles to try to find the optimum balance of HOM frequencies, Q's and power dissipation. Once we find a good compromise we will go ahead and model that profile as well. 
    All told the ERL workshop was a great success, with our own programs featuring prominently in all working groups (and not just because we were the hosts!). Not long ago the debate was whether high-current FEL's were even feasible, now they are using our machine as a benchmark to show that they are not only possible but practical and affordable.

WBS 8 (Instrumentation):

This week began with our participation in the ERL workshop. One of the many insightful meetings that took place provided us the opportunity to learn about new accelerator modeling tools that are available, specifically one which has been used to model 'our' JLab FEL. Dave Sagen at LNS/Cornell, in working with our CASA group, has recreated our DiMAD model of the IR-FEL with his 'extensible' BMad tool-kit and generated what he has called, "FELV". In short, this tool takes in difference orbit data and then solves the FEL transport model for all of the quadrupole values. To date, we do not have an ops tool to do this, and so we have been excitedly discussing how we can implement this tool into our FEL ops use. Three immediate tasks have been identified. 1) We need to get the existing FELV model running on our system and reproduce the results that Dave Sagen's model does on his system, 2) we need to update the FELV machine description file to match the latest machine configuration (this is being addressed by Chris Tennant) and 3) we need a script which will translate the results of our 'difference orbit data' into a data set that can be supplied to the FELV/BMAD model.  Full documentation on the FELV/BMAD tools is available from the following link: http://laser.jlab.org/devlore/devlore.asp?Item=6714 
  The epics2devlore RF Fault Archiver is still in the process of being tested.  The functionality of the system was tested successfully.  The problem arises with the EPICS channels being used to monitor the state of the RF system only providing fault coverage for the P1 machine faults.  This is not an adequate trigger for viewing all the RF faults that were requested to be monitored.  Through discussing the issue with J. Coleman, G. Lahti, and Al Grippo the RF Zones 2, 3, 4 now have a solution to this problem.  Zone 1 being the oddball is currently being hashed out.  Zone 1 should be completed by close of business today.  A final test run of the RF Fault Archiver system will occur during the beginning of next week, well before we are expected to power on the RF system for checkout. This week the DSP readings for the CTD CAN bus chassis system were slowed back down so that more tests could be run. The voltage mis-readings from the system were tested. It was discovered that the voltage being displayed on EPICS was the same voltage going into the DSP ADC channels A0 and A1, which is correct; however, the voltages themselves were not what should be expected. The CTD boards were pulled from the chassis and tested for correct mux and FPGA operation. 
   Further testing was performed on the two RF-DC Linear Converter PCB prototypes.  Tests to examine their response to RF pulses of different durations as well as output response through an RF Switch were performed.  These data will provide calibration points for pulsed beam, CW beam, and multi-pass beam operations.  These tests are also providing the specifications for the 4 Channel Filter PCBs and the RF-DC Linear Converter Carrier PCBs.  The Optical Dump Multiplexer installation has been completed.  All of the cables have been installed, terminated, and checked out OK.  Some software changes were made to ensure that the correct logic was implemented to match the EPICS screen.  The OCR Optical Dump local flow controller was modified to allow remote control through the Proportional Valve Control Chassis.  The cabling was installed and verified.  A vendor was found that carries the grades of phosphorous powders used for Beam Viewer target coating, 500 grams of both grades were ordered for coating of future Beam Viewer targets. Design of a 4 Channel Solenoid Fail-safe Interlock board for the new Multislit is complete.  A prototype has been built and tested for proof of principle. Rack fabrication and installation began for the Cold Cathode gauges and controls to support zone 3 cryomodule testing. HV and signal cable have been installed for the 4 controllers.  Installation was completed in the control room for the new beauty frame and new flat screen monitors. Assembly of the new multislits destined for 0F04 are underway. All parts have been UHV cleaned and delivered to T. Day.

WBS 9 (Beam Transport):

Sextupole (SF)

•	Fabrication is continuing at New England Techni-Coil. Core parts remain in machining, aiming to get them all rough machined to go to the heat treat in one batch the end of next week. Coil winding form and mold are in manufacture.  Conductor was received.

Replacement Chicane Dipoles GW)

•   Fabrication is continuing at New England Techni-Coil.  Steel core pieces for the second set of two dipoles are being machined. The coil mold is being reworked by NETC to be more precise for their first coil potting.

### UV Line

•	The first trial of a QX Quadrupole with a “Bang-Bang” hysteresis loop on the test stand showed a 1% greater strength with harmonics remaining the same as original tests.  The slow, linear ramp generator was also tested but needs some work.  First indications are that the strength changes, but harmonics remain the same.

•  Tim Whitlatch continues vacuum modeling.

•  The ME design group continues layout and documentation of the entire UV branch (less the chicane). They continue the designs of the four stand and girder types that we don’t have.

•  The first fabrication release was made for the UV Stand/Girder System as the twenty, post style stands were ordered through the Jlab Shop fabrication system.

•  The next priority item to sign off is the stand placement points so that the Survey and alignment folks can start laying out the stand positions.

•  Advanced Energy Systems has made great strides in designing the stands and chambers for the GW chicane.  The stands are almost fully detailed and the layout of the first of four chambers is nearly complete.

### UV Wiggler Progress

• 	We redesigned the viewers for the UV Chamber to have camera and viewer mounted on the robust, plenum side of the chamber. Greatly simplifying the chamber fabrication and eliminating high-risk welds in the thin part of the chamber.  By weeks end, we signed off the revision A of the drawings and transmitted them to Argonne National Lab.

### IR Upgrade Multislit for the Injector

•   Tony Day of the Accelerator instrument group assembled the new design Multislit and we surveyed it so that we will be able to install it and align it by the end of the shut down, next Wednesday evening. The Multislit will be able to measure transverse emittance at the exit of the injector’s Quarter cryomodule.

WBS 10 (Wigglers):

Efforts continue to provide information to the vendor for the wiggler gap mechanism contract, including the details for the motor controller panel and the support design.  Most of the action items from the kick-off review have been completed at this point.  A new action item arose in the last week when the vendor found that they had not designed the lifting points as strong as called out in the specification.  The design was revised to increase the strength of the lifting points.  The rails and motors are now ordered. 
Our contact at Argonne National Lab suggested a design change that would significantly ease construction of the UV wiggler vacuum chamber.  The problem is making a port on the narrow side of the chamber.  This is very difficult in an aluminum chamber.  Instead we will have both the camera assembly and the viewer actuator on the same side of the vacuum chamber.  This side has the plenum chamber on it so that connections can be made very easily.  We have are modifying the chamber concept drawing and the stay clear drawing to indicate this change and will send out changes next week.  We sent out a request for information to the vendors replying to questions from one of the vendors.

WBS 11 (Optics):

FEL mirrors: 
Metrology continues on the new transport mirrors.  Our first set of measurements show that the new elliptical transport mirrors appear to be passing spec uncoated, but are failing when coated.  We will test the rest and get back to the vendor.

Other activities:

The outgas rate study setup is checked out and is being baked for the first time (the resulting aroma caused everyone to stay clear of User Lab 1).  Measurements begin next week.  Work continued on the first turning mirror cassette.  Work in the vault for the streak camera transport from the first arc is essentially complete.  The prototype OBPM is in fabrication.  Michelle and Shukui attended the ERL Workshop.  Michelle met with staff visiting from Peking University, and explained some of the details of the current drive laser system.  We assisted staff from NSWC Dahlgren, who were here to set up their hardware.

UV FEL

The design team is implementing our suggestions from last week's design meeting.  The conceptual design for the optical region between the outcoupler and the collimator was fleshed out.

Terahertz:

Meetings were held with Eric Grossman of NIST, Boulder, CO, Colin Baker, Teraview, concerning imaging experiments in lab 3.