# MEMORANDUM

To:		Distribution

From:		George R. Neil

Subject:	FEL Upgrade Project Weekly Brief – September 17-21, 2007

Date:		September 21, 2007

Highlights:

The new high charge gun is under bake in the GTS.  It was ramping up to 250 C today and so far the level of water contamination is significantly lower than we have seen in the past.  We also got our control computer (IOC and VME crate) for the GTS running.   Both drive lasers were certified for running, too.

Management:

George Neil gave a paper on FELs at a DE conference in Alexandria.

Gwyn Williams attended the Basic Energy Sciences meeting in Bethesda. The Head of the Office of Science, Ray Orbach, announced a new charge to the advisory committee to report by summer of 2008 on the characteristics of a next generation light source that would address the recently identified Scientific Grand Challenges.

Michelle Shinn, Steve Benson and George Neil attended the FEL TAWG at Stanford to give a report on our high irradiance optics tests last spring as well as the GTS status.

The entire staff attended a RadCon Training Session as part of a JLab standown on handling of potentially contaminated components.

Injector:

GTS

The week was devoted to preparing the gun for vacuum bake cycle. On Monday we discovered that the shield door inside the cathode ball got loose from the actuator rood leaving the door half-way open. We had to open one of the upstream flanges but the problem was solved and the vacuum was recovered. On Tuesday we activated the NEG pumps with excellent results, the vacuum chamber ion pumps where reading less than 1 micro-amp of current or about 1E-9 Torr prior to the bake. The RGA shows water partial pressures below the 1E-7 Torr, the lowest we have ever seen from an un-baked gun vacuum chamber. On Wednesday the gun was prepared for baking and the oven panels installed. K. Jordan got us bakeable connector for the NEG pumps which were installed for a partial activation during the 150 C temperature ramp down. On Thursday morning we started the ramp up to 150C in 8 hours. The pressure dropped one order of magnitude overnight. This morning we started the final ramp up to 250 Celsius. Typically the gun bakes takes about three weeks, but based on the observed low pressure this bake might take less than 2 weeks.

The Safety Systems Group continued making progress installing the Personal and Laser Safety Systems. The PSS laser interface chassis was installed in the rack.

We started assembly of the PSS gun interface chassis. We also sent out the PSS/User interface panel for fabrication and engraving. PLCs and 24VDC power supplies were panel mounted and installed in rack. The electricians moved some AC conduit and installed signal conduit to the PSS/User interface panel. There is general discussion about still pending designs at scheduling meeting and more specific discussions about laser hutch design and installation at LPSS meeting - still have some unanswered issues.

GTS – The HVPS for the GTS has been tested to 150 kV with no load and to 5 mA with a short circuit load.  It needs the SF6 system to be finished to test it for higher voltages.  The Conditioning Resistor (330 Mohm) has been made and assembled for the GTS.  The values of the earlier Conditioning Resistors (3 – 4 kM ohm) were out of our desired range.  It is ready for final assembly into the GTS.

RF:

RF – Received the repaired solenoid power supply for Quarter 3 and changed a borrowed unit the borrowed unit.  We then discovered the solenoid power supply for Quarter 4 had just failed.  It was changed it out with the borrowed unit and sent out for repair.  A new spare power supply is due from the vendor in October.  These power supplies have run continuously for the life of the IR Demo machine and to date for the 10 kW Upgrade machine, nearly 10 years total.

Gun HVPS – The Conditioning Resistor was removed to allow work on the Gun.  It will be reassembled when the Gun is ready for it.

Instrumentation and Controls:

This week we continues our efforts in bringing online the IOC for the GTS, IOCFEL11.  With support from the software and network groups we were able to get the IOC up and running.  Currently the applications for the RS-485 are installed along with the 64-Bit GPI/O card.  The GPI/O card is being used to drive four timer cards which will make up the DLPC and synchronization system for the GTS.  Currently two out of the four timer cards are installed and configuration details are being worked out to establish proper communication and control.  As part of the DLPC system we've successfully assembled several cable snakes for I/O.  These snakes are currently being installed before the drive laser table gets installed. Some time was also spent supporting Optics in completing the Antares and Advanced Drive Laser certifications.  Wiring continued on the SF6 control box.  With the front panel wired and installed we were able to cycle the valves and are in the beginning stages of commissioning the system. 
   We've also taken the time to gather all of the VME I/O cards that will be needed for the GTS.  Currently we have the cards to perform RS-485 communication, ADC/DAC channels, BLM interface, Timer Cards, Stepper Motor Control, and signal multiplexing.  Most of these cards will be used for the Drive Laser controls and status readbacks.  Others will be needed later in the project but we're gathering these at one time to avoid the future headaches associated with this. 
   The Analog I/O distribution module has arrived from the board manufacturer.  Currently a lite assembly is being completed by the fabrication group.  Once this assembly is tested and verified three fully populated pcbs will be added to the queue for assembly.  The necessary parts to complete these assemblies were all ordered.  The bill of materials for the HVPS Analog I/O configuration is slowly coming together for this board.

Electron Beam Transport:

Improvements and Upgrades

Gun Test Stand (GTS)

•	In building the SF6 Gun Tank system, the JLab Shop completed welding the large flanges of the main vessel.  The large nozzle hole will be cut early next week.  The flange and the head of the Elongated Tank Head are ready to weld.  Willy will weld the Outer Conductor Extension first thing next week.  All the ASME grade fasteners were ordered.

•	The SF6 Gas Transfer System piping continued with checkout of the solenoid operated valves.  I am working on the documentation of the extension of the compressed air and the nitrogen systems into the GTS per our implementation of 10CFR851.  The air system will be extended to the SF6 System next week.

•	The Assembly Group will install the stands for the beam line early next week on overtime and the Vacuum Group can follow-on to mount all their hardware.

•	We also plan to install the drive laser table (hanging from the ceiling) during the gun bake next week on overtime.

SF Sextupole Magnet Testing

•	Magnet Test completed its first round of testing of the first sextupole with the new power supply and controls.  They will now do repeatability runs followed by use of the alignment group to characterize the position of their probe in X and Y at magnetic center with respect to nominal physical center.

Optics/Transport:

We have fully characterized the 930nm optics this week.  We have two high reflectors and two output couplers.  One high reflector will get bonded to a deformable assembly early next week.  Both the output couplers will go to Tom Elliott next week for brazing.  One will be brazed into a conventionally cooled mount and the other to a cryogenically cooled one. A broad band high reflector mirror was rebounded this week.  This optic had previously failed to deform correctly.  Tom is currently brazing six optical dumps for us.  Half are the 50kW variety need for the User Labs and the other three are the 15kW type with 6 inch conflat flanges.  The later will be used to replace the iso flange ones attached to the Optical Cavity Mirror Metrology System (OCMMS) crosses.

The Vacuum Group has completed installing the X-ray cross in the 4F region of the machine. We will start the OCMMS realignment process early week before the 4F region is pumped down.  The upstream OCMMS has been misaligned for some time and may require some disassembly before it can be functional.

We have received the extruded aluminum hardware needed for User Labs today.  They will be used to support the harmonic block filter and hutch shutters in Labs 3, 3a and 5.  Drawings have been released to the Machine shop to fabricate one prototype insertable mirror assembly. This assembly will be first used in Lab 5 to direct the FEL into the PLD (Pulsed Laser Deposition) apparatus.  Delivery is not expected until the first week of November.  The linear stage needed to complete the mirror cassette in Lab 3 was shipped to us this week.  We hope to make the necessary modifications and install it before we start the machine back up.  Work continues in converting the Turning Mirror Cassette (TMC) drawing from Ideas to SolidWorks.  This is necessary in order to design the modification to the cooling chain attachment point.  The current design does not allow us to slide the cassette assembly out of the vacuum vessel for installation and maintenance.

Lasers and Optical Diagnostics:
We had a laser safety inspection by Lab’s safety group early this week and then finished certification of both advanced drive laser system in drive laser enclosure and the Antares laser in Lab 6.  Both lasers are now operational.  We have optimized the Antares laser to the specifications required by the Gun Test Stand drive laser and are now working towards the integration and systematic testing of the whole system.  An issue with the harmonic converter was found and being fixed.  We also spent time on the optical transport and getting required safety shutters.

Terahertz: 
Work in the THz group this week was focused on continued progress toward completion of the vacuum systems in the THz hutch.  It has been decided to add gate valves to the beam ports on the sample chamber to allow for faster pumpdowns after sample changes, and to limit the frequency that the spectrometer and diamond window at F3 are subjected to the pump/vent transients.

Word version:  FEL Upgrade Project Weekly Brief – September 17-21, 2007