Updated 2/26/06

| Done | ATLIS | Author | Schedule | Title | Status |
| --- | --- | --- | --- | --- | --- |
| x | 4157 | Suleiman | Dec. ‘05 | Merging G0 Injector DAQ with the Main G0 DAQ | Hardware & ioc complete. Analysis (G0) in progress. |
| x | 3496 | Gaskell | Jan. ‘05 | Install Moller kicker at 3C15 | Kicker+ceramic installed Survey TBD |
| x | - | Poelker | ‘til 16th | January 2006 laser setup | BTeam Update |
| x | TBD-1 | Grames | ‘til 21st | Install high resolution HM DAC | Dickson wrote software. Cable fab. + install TBD |
| x | 4305 | Suleiman | 17-21 (4 Days) | G0 Backward Angle Laser Table Setup | Hardware ready. Software in progress. |
|  | 4223 | Kazimi | No time | Alignment survey of the elements around 0L02 spectrometer | Complete during May SAD |
| x | TBD-2 | Kazimi | Setup | Set “5 MeV region” to T=5 MeV using 0L07 | Cancelled |
| x | TBD-3 | CASA | Setup | Setup 650 MeV/pass | ATLIS to be written |
| x | 4306 | Suleiman | Setup 16 hours | G0 Backward Angle Injector Beam Studies | Follows ATLIS 4305 |
| x | 4347 4355 | Chao | Setup 4h,2D,8h | G0 PQB Injector Match | Follows ATLIS TBD-2 |
|  | 4359 | Spata | TBD | AT Line Shielding for 350 MeV Operations | Complete during May SAD |
|  | TBD-4 | Spata | Setup | ½ pass setup at G0 energy 362 MeV | Scheduled for May 5-12 |
| x | TBD-5 | CASA | Setup | Set Hall A/B Program 738 MeV/pass (I=41.5 MeV, NL=SL=369 MeV) while retaining G0 injector (I=36.6 MeV) | Follows Setup |
| partial | 4350 | Chao, Yves, Erb |  | PZTBooster Testing & Commissioning | Discussion complete. Action Item 1/9 Test during setup or BS |
|  | 3510 | Benesch | February | Hall C Moller system mod for G0 (placeholder) | Due March 8th |
|  | 3825 | Benesch | February | Rearrange end of Hall C line for G0 and beyond | Due March 8th |
|  | TBD-B | MEG | February | Install beampipe w/ magnetic shielding between Hall C pivot and G0 girders | Due March 8th |
|  | TBD-C | MEG | February | Reinstall Halo and G0 diagnostics girder | Due March 8th |
|  | 4688 | Suleiman | G0 startup | Parity Quality Beam Injector Measurement (Pre Pockels cell alignement), 4 hours |  |
|  | 4689 | Suleiman | G0 startup | Pockels Cell Alignment, 16 hours |  |
|  | 4707 | Poelker | G0 startup | Reactivate Gun3 Photocathode for G0, 8 hours |  |
|  | 4708 | Poelker | G0 startup | Install Fiber Laser in Hall C Slot, 4 hours |  |