## Slide 1
Readiness Review and Beam Scheduling
Thia Keppel
PREX/CREX Collaboration Meeting
February 2016

## Slide 2: Hall A Projected Experiment Schedule, updated 1/2016 Experiments in red represent PAC42 “high impact” experiments
Spring | Fall | Spring | Fall | Spring | Fall | Spring | Fall
DVCS –I/ GMp | DVCS –I/ GMp |  |  |  |  |  | 
 |  | DVCS –I/ GMp | DVCS –I/ GMp Ar(e,e’p* |  |  |  | 
 |  |  |  | 3H/3He group | 3H/3He group | TBD: APEX PREX12 CREX A1n DVCSII | 
 |  |  |  |  |  |  | SBS Start?
CY
2015
CY
2017
CY 2016
CY
2018
X
*possible best effort
Why we’re here today

## Slide 3: Comments on Schedule
    Not a lot of time for a major installation during winter down
      We have looked into possibility of installing PREX/CREX in this short time
      Would at minimum require overtime, increased manpower
      And would still need summer as well….
    Unclear what result of tritium ERR will be (March 16)
      – Under what conditions will we be able to work in Hall next Summer (Controlled Access only?)?
    SBS absolutely needs a summer installation
      Expect pressure will come from DOE to run SBS
      Modularity in design will assist in de-installation
    Single pass may require change of box supply resistive load to dogleg (?) magnets, few days to a week to change over (and then back again)
      Can’t run anything but single pass for this time??
      Caveat: not sure I have this completely correct
    Scheduling conflicts with other Halls possible
      Hall D can’t run with single pass tune at all

## Slide 4: Hall Activities (in support of PREX/CREX)
    Beamline instrumentation installed
      Second x,y,Q girder (from Hall C), new “Musson” cavity electronics, Hall C halo monitor
      Also lumi monitors (more recent)
    Polarimetry
      New high field Moller commissioned for DVCS polarimetry and taking production data
      First Compton measurements underway
    Established combined target chamber (CREX upstream) approach
      Hall A E&D assisting
    Computation fluid dynamics for target design
      Design effort
      Possible heating tests
    Pb and diamond targets, new septum coils purchased (and here at lab)
    Parity quality beam working group

## Slide 5: “New” Q1 Magnets
    SOS quad functioning on HRS-R
      Multiple optics studies, data obtained by GMp/DVCS
    HRS-L twin due at lab this June 2016
      Will permanently replace superconducting quads
    Mounts to allow forward/backward movement
      – Forward 30 cm for 3H
      Backward for septum experiments
      Optics for the latter should be studied!

## Slide 6
You are here!
http://www.jlab.org/div_dept/physics_division/experiments/scheduling.html

## Slide 8: Physics Division Readiness Process
      This review is largely about safety and operation, not science
      – think differently
      Design must be frozen after this review
      No charge yet
      Radiation shielding will be a critical element
      De-installation must be considered
      Will need documentation (PESAD) for any new or substantially redesigned equipment
        Target(s), Septum, Collimator(s), Shielding,…
        For each, present conceptual design and PESAD draft
      Hall A has 3 ERR reviews this Spring – very busy!

## Slide 9: Other Scheduling Topics for Consideration
      Thinking science now…
      Has the requisite polarization measurement uncertainty been demonstrated?
      How will “parity quality beam” be demonstrated, what are key parameters? Do we have adequate equipment to address this?
      Solution for the compromised Ca target?
      Quad optics
      The usual… DAQ, detectors,…

## Slide 10
    Thanks!