## Slide 1: Click to add title
Click to add subtitle
Allison Lung
UGBOD Meeting
January 14, 2016
12 GeV Upgrade Project - Status

## Slide 2: 12 GeV Upgrade Project
New Hall
Add arc
Enhanced capabilities
in existing Halls
Add 5 cryomodules
Add 5 cryomodules
20 cryomodules
20 cryomodules
Upgrade arc magnets
and supplies
CHL upgrade
Completion of the
12 GeV CEBAF Upgrade was ranked the highest priority in the 2007 NSAC Long Range Plan.
Upgrade is designed to build on existing facility: vast majority of accelerator and experimental equipment have continued use.
Maintain capability to deliver lower pass beam energies: 2.2, 4.4, 6.6….
Project Scope (~96% complete):
Doubling the accelerator beam energy - DONE
New experimental Hall D and beam line - DONE
Civil construction including utilities - DONE
Upgrades to Experimental Halls B & C - ~92%
TPC = $338M
ETC = ~$11M

## Slide 3: CIVIL Construction: 100% Complete
Installation of chilled beams in the tunnel arcs.
FY2015 Utilities Work:
Backup cooling towers were commissioned in Spring 2015.
Tunnel AC finished Summer 2015
October 2015
Chiller at East Arc.

## Slide 4: Hall D Detectors: University Construction
TOF (FSU)
BCAL (UR)
FCAL (IU)
START (FIU)
FDC inside BCAL bore
CDC (CMU)

## Slide 5: Hall D: 100% Complete
  Fall 2014
  (~19 days)
  10.1 GeV
  Amorphous radiator
  CH2 target
  Spring 2015
  (~10 days)
  5.5 GeV
  Diamond
  CH2 target
  Finishing calibrations
  Physics signals
  GlueX Solenoid: Operational Review in July 2015
  Difference between the SLAC and JLab cooling schemes
Modifications done to reconcile; Cooldown in progress
Progress with detector/trigger performance
Diamond thinning has been achieved
KPP achieved – December 2014

## Slide 6: CD-4B Key Performance Parameters
# | System | Technical Definition | PEP Date
6 | Hall B | Detector operational: events recorded with a > 2 nA electron beam at > 6 GeV beam energy (3 pass) | Sep 2017
7 | Hall C | Detector operational: events recorded with a > 2 nA electron beam at > 6 GeV beam energy (3 pass) | Sep 2017
8 | Hall D | Detector operational: events recorded with a > 2 nA electron beam at > 10 GeV beam energy (5.5 pass) | Sep 2017
Target (1cm plastic) location
Z,cm
Beam current (nA)
Beam energy (MeV)

## Slide 7: Halls B & C Construction Progress
Detectors and electronics at 99.4% complete
  Hall C complete
DAQ/Computing (software/firmware) at 87%
  Hall C complete
  Hall B last procurements 2Q FY2016
Beamline at 80%
  Halls B & C complete assembly FY2016
Infrastructure at 89%
  Halls B & C have major installations in FY2016
Magnets at 89%
  Hall C: 2 delivered/cold/powered, 3 underway
  Hall B: both underway

## Slide 8: Hall C: Detector Construction Complete!
Quartz Hodoscope
(NCA&T)
Shower Counters
(ANSL/Nikhef)
Drift Chambers
(HU)
PreShower Counters
NGC (UVa)
HGC Cerenkov
(UR)
Scintillator Hodoscopes
(JMU)
Funded through NSF-MRI:
Scintillator; Quartz;
Drift Chambers; Mount

## Slide 9: Hall C: Infrastructure Progress
Installations Completed:
Moller & Compton Polarimeters in place.
HV & Signal Patch Cables completed. DAQ in use for cosmic tests.
Personnel Safety System. Gas supply & Gas leak detection.
Shield Wall. Shield house doors. Q2 yoke support.
Moller Quads
Compton Stands
Q2 Yoke Support
Rear SHMS Shield Wall
Rear Detectors Installed
Shield Wall
DAQ
Patch Cables

## Slide 10: Hall C: SHMS HB and Q1 Magnets
HB
Q1
Q1 (SMI, UK)
Installed on carriage
Cooled down
Power test to 110% of operational current
Acceptance tests complete
HB (MSU/FRIB)
Installed on carriage
Cooled down
ERR - one open issue
Power test to ~90% of operational current
Full current test next week

## Slide 11: Hall C: SHMS D/Q2/Q3 Magnets
Dipole Collaring
(Sigma Phi, France)
Q3 inspect He vessel
(SDMS, France)
Q2 bore tube / endplate
(SDMS, France)
Q2 shield tack weld
(SDMS, France)
Dipole Integrated
(Sigma Phi, France)
Delay ~3 months due to QA problems on magnet thermal shield fab at subcontractor’s sub
Significant progress in Dec/Jan; Dipole delivery to JLab planned April 2016
Dipole He Leak Test
(SDMS, France)

## Slide 12: Hall C Schedule
Beam Dec 2016
Dipole April 2016
Q2 May 2016
Q3 June 2016

## Slide 13: Hall B: Detector Construction Complete!
FTOF 1-a, 1-b Installed (USC)
Drift Chambers
(ODU, ISU, JLab)
PCAL Installed
(OU)
HTCC Mirror in Vessel
Bit of last LTCC box to do
Some CTOF install tooling
SVT Region 4
CTOF Counters
LTCC

## Slide 14: Hall B: CLAS12 Magnets
Schematic @ ETI (PA)
Solenoid
Torus
Trial fit 1st coil on hub
2 Inner coils wound/potted
2 intermed coils wound;
1 potted, 1 in progress
All 6 coils installed
Inner
Intermediate
Shield
He channel
C1-4 bobbin
Shield coil winding bobbin 3-month delay
6 Coils connected through hex beams

## Slide 15: 12 GeV Project: University Detector Work
Hall | University | Activity | Status
B | Idaho State U | Drift Chamber | Complete
B | Old Dominion U | Drift Chamber | Complete
B | U South Carolina | TOF Counters | Complete
B | Moscow State U (RU) | SVT Testing | Complete
C | Michigan State U | HB Magnet | Testing
C | U Virginia | Noble Gas Cerenkov | Complete
D | U Athens (GR) | Monitoring BCAL, FCAL | Complete
D | Carnegie Mellon U | Central Drift Chamber | Complete
D | Catholic U | Tagger Hodoscope | Complete
D | U Connecticut | Tagger Microscope | Complete
D | Florida International U | Start Counter | Complete
D | Florida State U | TOF Counters | Complete
D | Indiana U | Forward Calorimeter | Complete
D | U Regina (CA) | Barrel Calorimeter | Complete
D | U Santa Maria (CL) | SiPM, Lightguides for BCAL | Complete
B, C, D | U Massachusetts | Electronics Testing | Complete
NSF-MRIs funded most
12 GeV Hall C Detectors
Internat’l contributions
for detectors beyond
base equipment
NSF-MRIs funded
Hall B PCAL Detector,
Long. Polarized Target

## Slide 16: Key Dates
Hall | Key Event | Projected Date
B | Torus 1st Coil Cold Mass Arrived | November 2014
B | Torus 6th Coil in Cryostat Done | June 2015
B | Torus Installation | October 2014 (‘spit’) – May 2016
B | Solenoid Coil Winding | March 2015 – March 2016
B | Solenoid Arrives | September 2016
B | Detector Commission with Beam | March 2017
C | 1st Magnet (Q1) Arrived | January 2015
C | 2nd Magnet (HB) Arrived | March 2015
C | Last Magnet (Q3) Arrives | June 2016
C | Last Magnet Tests | November 2016
C | Detector Commission with Beam | December 2016

## Slide 17: SUMMARY
12 GeV Upgrade Project = 96% Complete
  Accelerator complete & commissioned
  Civil Construction including Tunnel AC complete
  Hall A complete ; Hall D / GlueX complete
  5.5 passes > 10 GeV achieved ……… Hall D Key Performance Parameter met
Strong University collaborations critical to detector construction/commissioning
  Hall B:
Detectors complete*
Torus – all coils installed; cryo underway
Solenoid 4 (of 5) coils wound/potted*
  Delay due to shield coil bobbin fab
  Must complete all prep work asap
Solenoid is Project critical path
  Hall C:
Detectors complete
Q1 magnet installed & fully tested
HB magnet installed; tested to ~90% current
D/Q2/Q3 construction making progress
  Delay due to thermal shield fab
  Issue now resolved for D/Q2
Great Progress in 2015 !

## Slide 18: Back-Up

## Slide 19: Accelerator Construction: 100% Complete
September 2014
N. Linac
Cryomodules
RF - Klystrons
Coldbox
Arc 10
Recombiner
Extraction
Acceleration:
  10 new cryomodules; 8 cavities each
  high-performance, quadruple the gradient
  each cavity has dedicated m-wave source
  duplicate existing cryogenics plant
BEAM TRANSPORT | Existing Upgrade/Replace | Arc 10 New
Dipoles | 357 | 32
Quads | 730 | 40
Power Supplies | > 2000 | 81
Diagnostics | > 700 | 32
Vacuum Line | > 5 km | 0.3 km

## Slide 20: Hall D - Key Performance Parameter
Commissioning run: 3 weeks in Oct-Dec 2014:
Detector operational: events recorded with a > 2 nA electron beam at > 10 GeV beam energy (5.5 passes)
KPP Demonstration:
Detector running for ~one shift recording data from all subsystems.
Snapshots of beam status screens and/or accelerator elog entries demonstrating the electron beam current and energy.
Plots showing relative timing (coincidence) of the signals in TAGx, TOF, BCAL, FCAL, ST, PS (with TAGx).
Event displays showing correlations of particle hits in the CDC, FDC, ST, TOF, BCAL, FCAL.
Plots of reconstructed particle trajectories showing target position.
Particle identification plots using signals from calorimetry and timing detectors (e.g. FCAL, BCAL, TOF).

## Slide 21: Hall D – Key Performance Parameter
KPP achieved – December 2014
Thanks to dedicated effort by Accelerator Ops, Engineering, Hall D staff, and GlueX Collaboration
Target (1cm plastic) location
Z,cm
2-day running period: 50-100nA, 10.08 GeV electrons
See A. Freyberger’s talk
See J. Stevens’ talk
    Commissioning run: 3 weeks in Oct-Dec 2014
Hall D Tagger

## Slide 22: Technical Highlights (1)
Hall D : Silicon Photomultipliers (SiPMs)
What: Avalanche photodiode pixels operating in Geiger mode
Why: immune to strong field; good PDE; compact; no HV needed
Application: GlueX experiment & Bio-imaging
Hamamatsu
4×4 Array of
3×3 mm2 SiPMs
50 mm
Accelerator: C100 Cryomodules
Evolved from CEBAF C20 design & C50 program (reduce field emission & raise gradient)
Requirement 98 MeV, designed for 108 MeV
Experience being leveraged for FRIB and LCLS-II
C100 Cryomodule Energy Gain
Beam Current/pass (mA)
– 150
ENERGY GAIN (MeV)
– 50
– 100
– 200
98 MeV
108 MeV
Array of 80 SiPMs
(See D. Weisenberger’s talk)

## Slide 23: Technical Highlights (2)
Hall B: Silicon Vertex Tracker
Track low p particles with few % angular resolution at high L
New technology to JLab, strong collaboration with FNAL
Good S/N achieved
Leverage for HPS
 | Hall B |  | Hall C |  |  |  | 
 | Torus | Solenoid | HB | Q1 | Q2 | Q3 | Dipole
Type | 6-fold | Self Shielding | “C”, Septum | Cold Iron | Cos 2Θ | Cos 2Θ | Cos Θ
Vendor | JLab/FNAL | ETI | MSU / FRIB | SMI | Sigma Phi | Sigma Phi | Sigma Phi
B0/G0 (T;T/m) | 2.78 Tm @ 5° 0.54 Tm @ 40° | 5.0 | 2.56 | 7.9 | 11.8 | 7.9 | 3.9
Aperture (cm) | 13 | 78 | 14.5 x 18 | 40 | 60 | 60 | 60
Weight (T) | 28 | 20 | 6.8 | 18 | 70 | 18 | 163
Current (A) | 3770 | 2416 | 3930 | 2460 | 3630 | 2480 | 3270
Stored E (MJ) | 14.2 | 16.9 | 0.2 | 0.382 | 7.6 | 3.4 | 13.7
Halls B & C: Superconducting Magnets
7 new; wide variety
Vendors:
  Labs, Univ, US, Foreign
Expanded JLab staff
Leverage for SC
magnet projects

## Slide 24: SHMS Detector System
DETECTOR | PURPOSE | NOTES
S1XY, S2XY Hodoscopes | Lowest-level Trigger. Time reference | 
Drift Chambers | Momentum Measurement. Tracking. | 5mm max. drift 300 micron resolution
Noble-Gas CC * | Particle ID, Trigger. e±/π± at high momentum (replace by vacuum at low p) | Vary Ar/Ne mixture to set index at π± threshold.
Heavy-Gas CC | Particle ID, Trigger. π±/K± discrimination | C4F8O – Vary pressure to set index at K± threshold
Preshower / Shower Counters | Particle ID, Trigger. Electron tag | 
Heavy Gas Cerenkov
Noble-Gas Cerenkov
Drift Chambers
Shower Counter
S2 Hodoscope
S1 Hodoscope
PreShower Counter
* Only the Noble-Gas Cerenkov construction is 12-GeV scope. Other detector construction is primarily contributed.

## Slide 25: Hall C: SHMS
Dipole
Q3
Q2
Q1
HB
Magnet Power Supplies
Cryogenics Distribution
Concrete Detector Shield House
Pivot
Heavy Gas Cerenkov
Noble-Gas Cerenkov
Drift Chambers
Shower Counter
S2 Hodoscope
S1 Hodoscope
PreShower Counter
Particle Detectors

## Slide 26: CLAS12 Schematic
Project equipment
Forward Detector (FD)
  - TORUS magnet (6 coils)
  HT Cherenkov Counter
  Drift Chamber system
  LT Cherenkov Counter
  Forward ToF system
  Pre-shower Calorimeter
  E.M. Calorimeter
Central Detector (CD)
  SOLENOID magnet
  Silicon Vertex Tracker
  Central ToF system
Notes: To meet the physics requirements of high statistics measurements for exclusive processes, the equipment underwent major upgrades. CLAS12 has two major parts to its base equipment with different functions, the Forward Detector (FD) and the Central Detector (CD). The FD covers polar angle range of 5◦ to 35◦ and the CD from about 35◦ to 125◦.
The TORUS has six superconducting coils symmetrically arranged around the beam line, and provides six sectors for charged particle detection. Each sector has its own tracking and particle identification detectors. Tracking is accomplished with a set of 3 regions of drift chambers with 12 layers of hexagonal drift cells arranged in a pattern optimized to provide measurements for pattern recognition and subsequently track reconstruction; then PID (K/p separation up to 4.5 GeV) is obtained using the time-of-flight system from beta measurements. For improved PID, measurements from 2 Cherenkovs are employed: a high threshold counter for e-/pi separation and a low threshold counter for K/pi separation. Neutral reconstruction done using the calorimeters; physics program require the identification of single high energy photons and separation from π0 → γγ up to 9 GeV achieved by adding a preshower calorimeter (PCAL) in from of the electromagnetic calorimeter. For tracks produced at angles larger than 35◦ tracking is done using the Silicon Vertex tracker (up to 4 space points) and PID from beta measurement obtained from C. Time of Flight scintillator barrel. Several upgrades including the micromega detectors are aimed at improving tracking resolutions; the RICH with improve charged particle ID, the CND give neutron ID. A quasi-real photon forward tagging system (FT) will measure electrons at scattering angles from 2◦ - 4◦ .

## Slide 27: Hall B Schedule (as of Aug 2015)
Torus Assembly, Install + Test
Solenoid Install + Test

## Slide 28: Hall B Status
Detectors
  CLAS12 detectors are complete or in final phase of construction (LTCC).
  Forward Carriage: FTOF1a, FTOF1b, PCAL and EC essentially operational 2+ years prior to scheduled beam commissioning.
Magnets
  All Torus coils mounted to spit and connected through hex beams.
  Solenoid coil #4 winding completed – on critical path.
Software
  Offline software released, validation of reconstruction code using cosmic rays.
1st Workshop on preparation of first CLAS12 physics experiment
10/15/2015