## Sheet1
Hall B 12GeV Upgrade Design Tasks | [12 empty] | 2012-09-13
|  |  | Install dates based on Upgrade Schedule DHK 5/14/12 |  |  |  | Baseline Schedule 7/23/13
Subsystem | Activity ID for drawings | Task | Install Date | Drawing Deadline | Start | Finish | Date Component will be Used | Designer | Designer Man-Weeks | Engineer | Engineer Man-Weeks | Physicist | Status
SVT | 142211465 | Detector component and assembly drawings |  |  |  | 2012-12-15 | 2013-03-15 | Brandon | 18 | Saptarshi | 8 | Amrit
|  | Design and drawings R4 |  |  |  | 2013-08-15 | 2014-02-15 | Brandon | 12 | Saptarshi | 4
| 142211450 | Design external cooling system |  |  |  | 2013-05-15 | 2013-08-15 | Brandon | 5 | Saptarshi | 6
| 142211255 | Tooling to rotate SVT from vertical assembly stand to horizontal |  |  |  | 2013-10-15 | 2014-01-15 | Brandon | 3 | Saptarshi | 2
| 142211255 | Cart to move SVT to DC cleanroom |  |  |  | 2013-10-15 | 2014-01-15 | Brandon | 2 | Saptarshi | 2
| 142211800 | Support tube for SVT / MM |  |  |  | 2013-12-15 | 2014-03-20 | Forrest | 3 | Saptarshi | 2
|  | Tooling to join SVT and MM |  |  |  | 2013-12-15 | 2014-03-20 | Forrest | 6 | Saptarshi | 6
| 142211875 | Transport cart for SVT and MM |  |  |  | 2013-12-15 | 2014-04-18 | Forrest | 12 | Saptarshi | 4
| 142211840 | Insertion cart |  |  |  | 2013-12-15 | 2014-04-18 | Forrest | 5 | Saptarshi | 3
|  | Mounts for SVT/MM to solenoid |  |  |  | 2013-12-15 | 2014-04-18 | Forrest | 4 | Saptarshi | 3
Total | [8 empty] | 70 |  | 40
Drift Chambers |  | Load test installation tooling |  | 2012-12-21 | [5 empty] | Bob | 2 | Mac
|  | HV cable strain relief at top of chambers and cable bundle on strongback |  |  |  | 2012-11-15 | 2012-12-15 | Allen | 3 | Bob | 2
|  | Mounts and adjusters to Torus | 2014-09-19 |  |  | 2014-01-15 | 2014-03-31 | Allen | 6 | Bob | 3
|  | Cable trays and gas system mounts |  |  |  | 2013-08-15 | 2013-12-15 | Allen | 12 | Bob | 4
|  | Maintenance platforms |  |  |  | 2013-10-15 | 2013-12-15 | Allen | 6 | Bob | 3
Total | [8 empty] | 27 |  | 14
PCAL |  | Hall ramp cradle | 2013-03-26 | 2012-12-31 |  | 2013-06-30 | 2013-09-27 | Brandon | 5 | Saptarshi | 2 | Stepan | CLAS cradle may work
|  | Installation tooling |  |  |  | 2013-06-30 | 2013-09-27 | Brandon | 9 | Saptarshi | 5
Total | [8 empty] | 14 |  | 7
CTOF | 142231140 | Final drawings for tooling for wrapping |  |  |  | 2012-10-05 | 2012-03-26 | Cyril | 6 | Bob | 0 | Vitaly
| 142231235 | Final drawings for counter storage |  |  |  | 2012-10-05 | 2012-03-09 | Cyril | 3 | Bob | 2
| 142231260 | Final drawings for CTOF support and Solenoid Harness |  |  |  | 2013-01-30 | 2012-06-15 | Cyril | 12 | Bob | 5
| 142231270 | Final drawings for counter installation arm - cart |  |  |  | 2013-02-28 | 2012-09-13 | Cyril | 12 | Bob | 5
| 142231280 | Final drawings for magnetic shield compensating coil |  |  |  | 2012-11-16 | 2012-06-16 | Cyril | 2 | Bob | 0
| 142231285 | Final drawings for magnetic shield components |  |  |  | 2012-11-16 | 2012-05-01 | Cyril | 8 | Bob | 3
|  | Transport rack | 2014-11-14 | 2014-08-31 |  | 2013-03-31 | 2014-02-10 | Cyril | 6 | Bob | 3
| 142231345 | Final drawings for patch panels for LV & HV; 200 ch |  |  |  | 4/31/13 | 2012-05-23 | Cyril | 1 | Bob | 1
| 142231350 | Final drawings for splitter to TDC and ADC; 100 ch |  |  |  | 4/31/13 | 2012-05-23 | Cyril | 1 | Bob | 0
Total | [8 empty] | 51 |  | 19
FTOF |  | 1B frame and mounts | 2013-04-18 | 9/31/2012 |  | 2012-09-30 | 2013-06-30 | Joe | 3 | Bob | 3 | Dan
|  | Strongback mods | 2013-04-18 | 2013-01-31 |  | 2013-08-30 | 2013-10-30 | Joe | 2 | Bob | 2
|  | 1B counter shipping containers and storage racks |  |  |  | 2013-03-30 | 2013-05-30 | Joe | 4 | Bob | 2
Total | [8 empty] | 9 |  | 7
HTCC |  | Containment vessel design | 2014-11-07 |  |  | 2013-03-15 | 2013-07-03 | Allen | 3 | Bob | 2 | Youri
|  | Moeller cup |  |  |  | 2013-05-03 | 2013-09-03 | Allen | 3 | Bob | 3
|  | Awning and window |  |  |  | 2013-08-15 | 2013-12-15 | Allen | 3 | Bob | 2
|  | Transport cart | 2014-11-07 |  |  | 2014-03-06 | 2014-06-06 | Allen | 4 | Bob | 3
|  | Support cart | 2014-11-07 |  |  | 2013-05-03 | 2013-08-03 | Allen | 4 | Bob | 3
Total | [8 empty] | 17 |  | 13
LTCC | 142242035 | Mirror sag test |  | 9/31/12 |  | 2012-12-07 | 2013-02-07 | Joe | 2 | Bob | 2 | Mauri
| 142242145 | Box mods | 2013-05-30 | 11/31/12 |  | 2013-01-15 | 2013-04-02 | Joe | 12 | Bob | 6
| 142242135 | Window design | 2013-05-30 | 11/31/12 |  | 2013-01-15 | 2013-04-02 | Joe | 3 | Bob | 3
|  | Tooling mods | 2013-05-30 | 2013-02-28 |  | 2014-01-15 | 2014-03-19 | Joe | 3 | Bob | 3
Total | [8 empty] | 20 |  | 14
Beamline |  | Beamline drawing | 2013-03-22 | 2013-01-31 |  |  | 2013-12-15 | Joe | 3 | Saptarshi | 0 | FX
|  | Stands for beamline components |  |  |  |  | 2013-12-15 | Joe | 6 | Saptarshi | 3
|  | Apex extension for PCAL | 2013-02-06 | 2012-10-31 |  | 2013-01-31 | 2013-04-22 | Joe | 2 | Saptarshi | 2
|  | Lead nose on FC |  |  |  | 2013-01-31 | 2013-04-25 | Joe | 2 | Saptarshi | 2
|  | Moeller shield |  |  |  | 2014-02-15 | 2014-06-15 | Joe |  | Saptarshi
|  | Forward tagger integration | [5 empty] | Joe | 3 | Saptarshi | 2
|  | Forward tagger spoolpiece |  |  |  | 2014-02-15 | 2014-06-15 | Joe |  | Saptarshi
|  | Integrate central detector | [5 empty] | Joe | 4 | Saptarshi | 2 | Mac
Total | [8 empty] | 13 |  | 7
Subway | 14264008 | Install and align subway rail | 2013-03-22 | 2013-01-31 |  | 2013-01-31 | 2013-03-29 | Forrest | 2 | Saptarshi | 2 | Doug Tilles
| 14264008a | Solenoid motion system |  |  |  | 2014-01-31 | 2014-04-07 | Forrest | 5 | Saptarshi | 2
|  | Solenoid heater system |  |  |  | 2014-03-15 | 2014-06-26 | Forrest | 2 | Saptarshi | 2
Total | [8 empty] | 9 |  | 6
Forward Carriage | 14264019 | Reinforce Fwd Carriage | 2013-02-06 | 2012-10-31 |  | 2012-10-31 | 2013-05-24 | Forrest | 3 | Saptarshi | 2 | Doug Tilles
| 14264017 | Weld PCAL and LTCC brackets | 2013-02-06 | 2012-10-31 |  | 2012-11-15 | 2013-05-09 | Forrest | 3 | Saptarshi | 2 |  | Orlando conceptual design
| 14264018 | Install panel 2 TOF brackets |  |  |  | 2012-11-15 | 2013-05-22 | Forrest | 0 | Saptarshi | 0
|  | Add handrails, stairs, and A/C to level 0 | 2013-02-06 | 2012-10-31 |  | 2012-11-15 | 2013-05-24 | Forrest | 2 | Saptarshi | 1 |  | Coordinate with Civil Engineering
|  | Motion system | 2013-02-06 | 2012-10-31 |  | 2012-10-31 | 2013-05-24 | Forrest | 3 | Saptarshi | 2
Total | [8 empty] | 11 |  | 7
Project Total | [8 empty] | 241 |  | 134
Number of People | [8 empty] | 5 |  | 2
Time to complete (weeks) | [8 empty] | 48.2 |  | 67
Manweeks per person | [7 empty] | Allen | 44 |  | 67 | Bob
[8 empty] | Brandon | 54 |  | 67 | Saptarshi
[8 empty] | Cyril | 51
[8 empty] | Forrest | 50
[8 empty] | Joe | 42