## Slide 1: SHMS Progress Jan 15, 2015
Paul Brindza
Steve Lassiter, Eric Sun, Mike Fowler, Paulo Medeiros, Dan Young,
Bert Metzger, Gary Vettalana

## Slide 2
SHMS Overview
SHMS Q1
SHMS HB
SHMS Dipole
SHMS Q2Q3

## Slide 3
Hall C SHMS Jan 14, 2015

## Slide 4
Hall C SHMS Jan 14, 2015

## Slide 5
Departed SMI Dec 12, 2014
In Norfolk Friday Jan 2, 2015
At JLAB Tuesday Jan 13, 2015
In Hall C Wed. Jan 14 , 2015
Q1 at SMI in the shipping Frame Dec 2014

## Slide 6
Q1 checking thru JLAB security @ 7 PM Jan 13, 2015

## Slide 7
Into the Pit
Wed Jan 15, 2015

## Slide 8
Q1 in Hall C with SMI Techs

## Slide 9
Q1 in Hall C Wednesday January 14, 2015

## Slide 10
HB near complete @ MSU
On Jan 5, 2015
Ship date March 15, 2015

## Slide 11: HB close up of SC bus connections Jan 5, 2015

## Slide 12: Dipole Coils complete @ SigmaPhi Jan 15, 2015

## Slide 13: Dipole Status at SigmaPhi
Dipole coils wound and Vacuum impregnated
Dipole coil A layer splices complete
Dipole coil assembly underway
Collars and collaring fixtures on order for Feb delivery
Dipole cryostat in Fab at SDMS, Lyon France
  He vessel March 2015
  Vacuum vessel & shield April 2015

## Slide 14: SHMS Dipole Cryostat Helium Vessel @ SDMS Jan 12, 2105

## Slide 15: Dipole and Quad Cold Mass assembly
Dipole assembled
Dipole is wrapped in this fixture.
Dipole in the VPI Mold

## Slide 16: Preparation for SHMS Dipole Collaring Jan 12, 2015

## Slide 17: Dipole Coil Assembly Jan 14, 2014
Coil B preparing Leads
Coil A with assembly Jig

## Slide 18
Q2 Coil A or D being prepared for molding
Q2 Coil B ready for rotation and removal from mandrel
Q2 Coil A or D idle
Mandrel being readied for Q3 winding
Conductor spools being readied for Q3 winding

## Slide 19: Quad 2/3 status at SigmaPhi
Quad 2 coils wound- complete Nov 2014
Quad 2 coils B & C Vacuum Impregnated Dec 2014
Quad 2 coils A& D Vacuum Impregnation Jan 2015
Quad 3 winding start Jan 13 2015
Quad 2/3 cryostats in Fab at SDMS
Quad 2/3 assembly tooling same as dipole

## Slide 20
Quad 2 Winding Nov 2014

## Slide 21: Quad 2 Coils Vacuum Impregnated Jan 9, 2015
Quad 2 Coil C
Quad 2 Coil B

## Slide 22: Q3 wind start and clean up of Q2 coils Jan 14, 2015

## Slide 23: Quad 3 coil Winding Jan 14, 2015
Progress on Quad 3 Coil F Layer 1
Start of Quad 3 Coil E

## Slide 24: Quad 3 Winding Jan 15, 2015
Quad 3 Coil F complete
Quad 3 Coil E last turn

## Slide 25: SHMS Infrastructure
AC power complete
LCW complete
SHMS Cryo system- complete & tested
DC power supplies – installed & tested
Controls & Instrumentation – complete & tested
I&C cabling installed & tested
DC bus installed
Yoke steel installed

## Slide 26: SHMS Magnet Test Schedule
SHMS Magnet Test and Commissioning | Quadrupoles | Dipole
Physics Div. Safety Review | Prior to arrival | Prior to Arrival
Arrival Tests | 1 week | 1 week
Cryostat & Yoke assembly | 1 week | 1 week
Dipole Only Assembly | NA | 8 weeks
Cryogenic Tests | 2 week | 2 week
Electrical Tests | 1 week | 1 week
Cool to 80 Kelvin | 2 weeks | 2 weeks
Cool to 4 Kelvin | 0.4 weeks ( 2 days) | 0.4 weeks ( 2 days)
Low Power Tests | 1 week | 1 week
High Power Tests | 2 weeks | 2 weeks
Acceptance Tests | 1 week | 1 week
Total | 11.4 weeks( ~ 3 months) | 19.4 weeks( ~ 5 months)
Arrival to Acceptance

## Slide 27: Conclusions
SHMS/Hall C is ready for first magnet
SHMS Q1 in Hall C Wed Jan 14, 2015!!! Yeah!!
SHMS HB due at JLAB March 2015
SHMS Magnets @Sigma Phi excellent progress
  SHMS Dipole delivery est.- 10/12/15
  SHMS Quad 2 delivery est.- 11/2/15
  SHMS Q3 delivery est.-12/30/15