## EVMS Schedule
|  | Planed |  | Labor | Material | Total |  | Reported
Activity | Activity Name | Start | Finish | Cost US$ | Cost US$ | Cost US$ | Duration | complete | remaining | start | finish | section #straws in %
| Phase 1 Construction setup and straw preparation |  |  | 25563 | 22373 | 47936
195212010 | Procurement epoxy with delivery in phases | 2010-04-06 | 2010-07-30 |  | 22373 |  |  | 95% | 5% | 2010-05-15
195212015 | Installation mandril and end plates | 2010-04-06 | 2010-07-30 | 6391 |  |  |  | 100% | 0 | 2010-05-15 | 2010-08-24
195212020 | aligned and fix end plates | 2010-04-06 | 2010-07-30 | 19172 |  |  | 10 | 100% | 0% | 2010-05-15 | 2010-10-20
| Phase 2 Straw Insertion |  |  | 107065 | 0 | 107065 | 10
195212025 | Straw Preparation Axial section I |  | 2010-08-31 | 3168 |  |  | 1.9 | 100% | 0% | 2010-08-15 | 2010-12-01 | 0.054515
195212030 | Insert straws Axial section I |  | 2010-08-31 | 3168 |  |  |  | 100% | 0% | 2010-08-15 | 2010-12-01
195212035 | Straw preparation Stereo section I-L |  | 2010-08-31 | 4702 |  |  | 2.9 | 100% | 0% | 2010-09-25 | 2011-01-07 | 0.082907
195212040 | Insert straws Stereo section 1-L |  | 2010-08-31 | 4702 |  |  |  | 100% | 0% |  | 2011-01-07
195212045 | Straw preparation Stereo section 1-R |  | 2010-09-30 | 6363 |  |  | 3.9 | 100% | 0% | 2010-09-25 | 2011-02-04 | 0.113
195212050 | Insert strwas Stereo section 1-R |  | 2010-09-30 | 6363 |  |  |  | 100% | 0% |  | 2011-02-04
195212055 | Straw preparation Axial section 2 |  | 2010-09-30 | 8280 |  |  | 5.1 | 100% | 0% | 2010-09-25 | 2011-03-10 | 0.14651
195212060 | Insert straws axial section 2 |  | 2010-10-29 | 8280 |  |  |  | 100% | 0% |  | 2011-03-10
195212065 | Straw preparation stereo section 2-R-1 |  | 2010-10-29 | 4734 |  |  | 3 | 100% | 0% | 2010-09-25 | 2010-03-29 | 0.17263
195212070 | Insert strwas stereo section 2-R-1 |  | 2010-11-30 | 4734 |  |  |  | 100% | 0% | 2011-03-10 | 2011-04-06
195212075 | Straw preparation stereo section 2-R-2 |  | 2010-11-30 | 5117 |  |  | 3 | 100% | 0% |  | 2011-06-07
195212080 | Insert straws stereo section 2-R-2 |  | 2010-12-30 | 5117 |  |  |  | 100% | 0% |  | 2011-06-07
195212085 | Straw preparation stereo section 2-L-1 |  | 2010-12-30 | 5500 |  |  | 3.5 | 100% | 0% |  | 2011-06-30 | 0.19989
195212090 | Insert straws stereo section 2-L-1 |  | 2011-01-31 | 5500 |  |  |  | 100% | 0% |  | 2011-06-30
195212095 | Straw preparation stereo section 2-L-2 |  | 2011-01-31 | 5884 |  |  | 3.5 | 100% | 0% |  | 2011-07-22
195212100 | Insert straws stereo section 2-L-2 |  | 2011-01-31 | 5884 |  |  |  | 100% | 0% |  | 2011-07-22
195212105 | Straw preparation Axial Section 3-1 |  | 2011-02-28 | 6395 |  |  | 4.1 | 40% | 60% | 2011-07-25 |  | 0.23055
195212110 | Insert strwas axial section 3-1 |  | 2011-02-28 | 6395 |  |  |  | 25% | 75% | 2011-07-25
195212115 | Straw preparation Axial Section 3-2 |  | 2011-03-31 | 6779 |  |  | 4.1
195212120 | Insert Straws Axial Section 3-2 |  | 2011-03-31 | 6779
| Phase 3 Shell Installation. |  |  | 14781 | 0 | 14781 | 35
195212125 | Install Gas lines in CDC volume |  | 2011-04-29 | 2769 |  |  | 1
195212130 | Install sensors in CDC Volume |  | 2011-04-29 | 1426 |  |  | 0
195212135 | Installation outer shell |  | 2011-05-31 | 10586 |  |  | 2
| Phase 3 Chamber stringing |  |  | 113839 | 0 | 113839 | 3
195212140 | String 1st axial section |  | 2011-05-31 | 6335 |  |  | 1.9 | 100% | 0% | 2011-05-02 | 2011-06-15
195212145 | String 1st stereo section |  | 2011-06-30 | 9403 |  |  | 2.9
195212150 | String 2nd stereo section |  | 2011-07-30 | 12726 |  |  | 3.9
195212155 | String 2nd axial section |  | 2011-08-30 | 16560 |  |  | 5.1 | 50% | 50% | 2011-05-12 | 2011-06-23
195212160 | String 3rd stereo section (inner) |  | 2011-08-30 | 9467 |  |  | 3
195212165 | String 3rd stereo section (outer) |  | 2011-09-30 | 10234 |  |  | 3
195212170 | String 4th stereo section (inner) |  | 2011-10-30 | 11000 |  |  | 3.5
195212175 | String 4th stereo section (outer) |  | 2011-11-30 | 11767 |  |  | 3.5
195212180 | String 3rd axial section (inner) |  | 2011-12-30 | 12790 |  |  | 4.1
195212185 | String 3rd axial section (outer) |  | 2012-01-31 | 13557 |  |  | 4.1
| Phase 4 Chamber instrumentation |  |  | 65403 | 0 | 65403 | 35
195212190 | Electronics installation 1st axial section |  | 2012-01-31 | 4162 |  |  | 1.2 | 5% | 95%
195212195 | Electronics installation 1st stereo section |  | 2012-02-29 | 6143 |  |  | 1.9 | 5% | 95%
195212200 | Electronics installation 2nd stereo section |  | 2012-02-29 | 8290 |  |  | 2.5 | 5% | 95%
195212205 | Electronics installation 2nd axial section |  | 2012-03-30 | 10766 |  |  | 3.3 | 5% | 95%
[7 empty] | 1.9 | 5% | 95%
195212210 | Electronics installation 3rd stereo section inner |  | 2012-03-30 | 6185 |  |  | 2
195212215 | Electronics installation 3rd stereo section outer |  | 2012-04-30 | 6680 |  |  | 2.2 | 5% | 95%
195212220 | Electronics installation 4th stereo section inner |  | 2012-04-30 | 7175 |  |  | 2.3
195212225 | Electronics installation 4th stereo section outer |  | 2012-05-31 | 7671 |  |  | 2.5
195212230 | Electronics installation 3rd axial section inner |  | 4/31/2012 | 8331 |  |  | 2.7
195212235 | Electronics installation 3rd axial section outer |  | 2012-06-29 | 8826
| Phase 5 Chamber operational tests |  |  | 52777 | 0 | 52777 | 22.5
195212240 | Close up gas upstream and downstream gas plenum |  | 2012-07-31 | 10086 |  |  | 3
195212245 | Gas leak tests |  | 2012-08-31 | 16477 |  |  | 5
195212250 | HV tests |  | 2012-10-31 | 15768 |  |  | 8
195212255 | Operation tests |  | 2013-02-28 | 10446 |  |  | 16
195212260 | Phase 7 Chamber shipping |  | 2013-03-29 |  | 5000 | 5000
|  |  |  | 379428 | 27373 | 406801
Consumables Purchased during construction