MEMORANDUM

To:	Distribution

From:	F. Dylla

Subject:	FEL Upgrade Project Weekly Brief – April 26-May 2, 2003

Date:	May 2, 2003

Highlights:

We spent the afternoon and evening shifts this week performing the high voltage conditioning of the photogun.  As of press time we have successfully completed conditioning of the gun to

420 kV, which provides our desired 20% head room in conditioning above the nominal 350 kV operating voltage of the gun.  We also continued putting RF power to the acceleration system during the gun conditioning activities.  Next week we move on to bring the gun and injector on line with electron beam.

Management:

On Thursday evening and Friday we met with two members of our Maritime Technical Advisory Committee, Admiral Ted Parker and Dr. Alan Berman, for review and counsel on the Lab’s FEL program.

On Tuesday, participants in the joint NSWC, NRL JLab laser materials lethality studies project met at JLab to discuss planned experiments when the 10 kW FEL goes into operation.

We submitted on Monday “Work for Others” agreements to the DOE Site Office for their review and approval for a joint project with AES on a terahertz beamline for the FEL with funding provided by the US Army Night Vision Lab, and for the next increment of lethality studies with funding from  the NSWC as noted above.

On Tuesday, S. Chattopadhyay and F. Dylla gave presentations to the SURA Board of Trustees on accelerator light source developments at SURA’s spring SURA board meeting in Washington.

WBS 4 (Injector):

At the end of last week’s gun conditioning activities, the gun was conditioned to 300 kV by midnight on Friday night.  Starting on Monday of this week we spent 10-12 hr shifts on conditioning activities as we brought the system up 420 kV.  We encountered a half dozen field emission sites that required a few hours of processing per site.  In general the conditioning went very smoothly and bored the operators as we incremented the voltage by 1 kV steps to keep vacuum excursions in the upper UHV range.  Early next week we plan to do the in-situ heat clean and cesiation to prepare the photoemitting surface on the GaAs cathode, do the final alignment on the drive laser and fire up the gun.

WBS 6 (RF):

We put power on all the SRF acceleration systems for approximately 15 hrs this week for conditioning and controls adjustments.  Both cryomodules were operated at “drive highs”.  The injector cryounit maximum gradient was pushed from 7 MV/m to 9 MV/m for each cavity as we adjusted tuning and monitored window heating effects.  This is 10-15% below where we want to be so we will continue this activity next week.

WBS 8 (Instrumentation):

Completed interlocking the box supplies for the 1st Arc, DY Arc, and Wiggler (on/ off and current out) to the MPS beam mode module. Checkout and calibration is complete.  Modifications to the current measurement output board and the FSD/MPS status relay for the 5kW extraction power supply  has begun. MPS wiring for the 2nd Arc string has begun.  The last AC distribution chassis for the Danfysik power supplies has been delivered and installed. Shunt modules for 4F06, 4F06A and 2F08 and the 1st Arc shunt chassis were pulled for repair and check out will continue when re-installed. The vacuum signals  have also been checked out through EPICS and MPS. The MPS-Ops screen has been reviewed and the 1st set of changes is underway.

Beam Loss Monitors (BLMs) - The exact positions of the BLM heads have been determined and we are preparing to install the permanent support structures for each channel.  The BLM PMT signal monitoring cables are all installed and can be connected to the analog monitoring system (AMS) as needed.

The Dump Water Temperature/Pressure Monitoring Chassis' for the 2G and 5F dumps are connected to the sensors in the vault and have been tested.  The Machine Protection System chain in each chassis is also functional.  The drawings for the chassis are being revised to reflect the new MPS chain.

The new Charge/Dump Current Monitor Buffer Driver has been installed at the 2G dump and tested satisfactorily.  Cables for the Buffer Drivers for the 1G and 5F dumps have been pulled and are terminated in the Control Room rack. The EPICS readout has also been checked out.

The web-server PC 'laser.jlab.org' is undergoing maintenance to keep it up to date and secure

WBS 9 (Transport):

Dipoles

Injector Dipoles (DU/DV)

•	The Large and Small Injection Chicane Dipole in the 5F region were fully aligned.

Arc 180 Degree Dipoles (GY)

•	The data from measurements of the first GY at 210 MeV/c fields is consistent with the

145 MeV/c data.  The magnet looks good.

•	Wang NMR reports that the potting of the second coil of the second GY dipole was successful.  No shorts -big sigh of relief.  They are doing a trial fit and brazing the fittings on the leads.  Their plan is to ship on Wednesday.

Octupole (OT)

•	The order for the core machining is ready to be placed when funds are available.

## Correctors

•	The second (and last) coil of the special GA vertical corrector (the last First Light punch list item) of the Optical Chicane was glued together and will be ready to be installed with its bracket next week.

## Commissioning

•	The vacuum group continued its vacuum quality assurance procedure for chambers, completing the optical chicane and the first half of the second arc.

•	Dave Waldman performed tests of the helicoflex seals vs. o-rings for the windows in the GY chamber.  He sees a 1.5 mil deflection of the rectangular flange with o-ring and no deflection with the helicoflex.

•	Dave Waldman received the circular quartz window and the machined rectangular flange covers with hole for the circular window that are the work-around for the rectangular windows on the GY chamber that are late from Ceramaseal.  It is a robust solution to the problem that will be ready for when the GY magnet is needed for recirculated beam.

WBS 11 (Optics):

Work on the e-beam beamline progressed to the point that we were able to get a clear path back to the HR assembly.  This allowed us to affirm that the optical beam shields were doing a great job at eliminating beam jitter due to air currents.  The residual jitter was mostly attributed to the optical bench supports.  Since we had anticipated this, we began adding plates that would stiffen the bench and saw a dramatic improvement.  In order to connect the optical cavity to the GX magnet chamber, we purged the OC vacuum vessel with dry nitrogen; this also gave us the opportunity to change out the ultraviewer mirror holder clips and the viewport.  We also added a spacer flange to the insertable mirror (for the spontaneous output) that had been inadvertently left off during assembly.  At this writing the entire OC vacuum assembly was pumped down sufficiently to get the ion pumps on.  In preparation for the cavity length determination efforts, the optical breadboard for the in-vault diagnostics was anchored in place.  The pyroelectric detector for that diagnostic suite arrived this week, as did the upgraded spectrometer.  We received the molybdenum cooling rings the 4" diameter OC mirror mounts in (required for high power operations) and they will be sent out for cleaning and plating.  The water chiller for the optical cavity was filled with water and checked out.  We are fabricating the breakout boxes for the piezos (and optical encoders).  We continue to work on the problem of noise and drift in the LVDT readbacks.  We received a fast shutter which we intend to use as a replacement of the second EO cell.  With it, we can chop the drive laser beam for periods as short as 1 ms, and repetition frequencies as high as 200 Hz.  This is a more flexible arrangement (yet inexpensive) compared to our chopper.  We will retain our chopper scheme for those cases where short duration periods are required.

#### Other activities

We assisted our users in User Lab 6 by loaning them our fast IR detector and a preamplifier, as well as some vacuum hoses and connectors to vent their He dewar.  We hosted a meeting with staff from NSWC Dahlgren and PMS 405.