MEMORANDUM

To:	Distribution

From:	F. Dylla

Subject:	FEL Upgrade Project Weekly Brief – June 9-13, 2003

Date:	June 13, 2003

Highlights:

We are pleased to report that yesterday (June 12th) we produced spontaneous emission of 6 micron light from the FEL Upgrade –an important accomplishment as we progress towards our “first lasing” milestone. In last week’s report we noted that we had pushed the electron beam through the wiggler into the first light dump. Since last Friday night we have had four days of near continuous beam operations as we optimized the electron beam parameters and performed several length scans on the optical cavity looking for lasing.  We were limited in our ability to set the cavity length to its micron level tolerance because our laser interferometer suffered an infant mortality in its diode pump and (spare promises by the manufacturer to the contrary) can not be repaired until next week.  We decided to go ahead and try to manually scan the cavity length anyway expecting to gain experience in other operational characteristics in the process.  A summary of these commissioning activities is given below for those interested in the details.  Today and through the weekend we are performing a check on our optical cavity length survey measurements, fixing some minor problems accumulated through the week, and preparing to restart commissioning on Monday.

All in the team are pleased with how the Upgrade hardware is performing during this shakedown cruise.

Commissioning:

Last weeks activities centered on roughly setting up the injector and linac, threading the beam to the tune-up dump past the optical klystron, and commissioning the optical klystron.  This week, including last Saturday, was involved with careful setup of the injector, linac and beam transport, and optical systems, including many hours of length scans looking for lasing.  The modeling tools available have greatly aided in setting up the machine to match the design. 

On Saturday we carefully set up the linac phasing and optimize the bunch length using the 1st arc multi-poles.  We then centered in all the machine quadrupoles and saved the orbit.  Finally we obtained a decent match to the wiggler and looked for lasing using an IR camera and the electron spectrometer.  No lasing was seen.

Monday was spent in maintenance and PSS re-certification required when a logic unit failed.  We ran briefly and took data on current linearity in the diagnostics (they all track except for the laser power).   All the magnets whose polarity was found to be wrong last week were fixed and one missing trim channel was added.

On Tuesday we carefully set up the injector to match the Parmela model as closely as possible.  The match to the linac was good and the spots throughout the machine were greatly improved.   The injector energy was also shifted closer to design.  We then set up the rest of the machine and re-optimized the bunch length using multi-pole values closer to the model.  The design values are much stronger than those used last week.  We also measured the sensitivity to the gun voltage and determined that the voltage droop caused by the conditioning resistor should not hurt us.  After shutdown we installed the spectrometer and a more sensitive detector so that spontaneous radiation could be seen.

Wednesday we studied reproducibility and found that most magnets reproduced well.  The DY used in the IR Demo did not reproduce quite as well (one part in a thousand) and a pair of iron core correctors did not reproduce well at all.  We developed a procedure to bring the machine back within a few minutes of bringing the machine back up.  The stronger sextupoles in the

1st arc created some distortion in the beam and some time was spent trying to center in them.  Once this was done we tried again to look for lasing.  We could not see the spontaneous and found no lasing.

Thursday we fixed a problem in the RF system that was leading to frequent trips and, using a more compact beam transport to the detector, succeeded in seeing a strong spontaneous radiation signal.  We scanned the cavity length and found a few candidates for a length enhancement but could not obtain lasing on any of them.  We also measured the spots sizes in the machine and used these and the model to derive a better match to the wiggler.  We also discovered that we could better optimize the bunch length by steering the electron beam to center in the detector aperture.  Despite having a very nice electron beam in the wiggler we were unable to find a length enhancement.

Analysis of surveying data indicated that the proper length might be outside of the scanned range.  We are now refining the surveying data to allow us to set the cavity length to better than 1 mm.  We are also going to make a new cathode (heat clean followed by recesiation) to allow higher charge.  Finally, we found that the high reflector in the optical cavity is slightly astigmatic and we are installing our spare high reflector so that the optical mode is closer to ideal.

In conclusion, we have used the modeling techniques developed in the IR Demo to set up the machine to match the model in an efficient manner.  The system is now close to the design point but running at low charge.  The optical cavity has some problems that are being addressed.  With these problems resolved and the charge increased we should see lasing soon.

Management:

We prepared draft presentations on the FEL program for our annual DOE Science and Technology Review which is scheduled for June 25-26th.

The kick-off meeting for our joint project with AES on terahertz imaging funded by the US Army is scheduled for July 22 at Jefferson Lab.

WBS 4 (Injector):

The photogun has performed extremely well since it was commissioned on May 7th.

Generally, quantum efficiencies have been obtained in the 3% range after cesiation. After the last two weeks of operation the QE has fallen to 1.1%, so we are processing a new cathode during today’s shut-down with a standard (670C) heat clean, followed by re-cesiation and HV conditioning up to 360 kV.

WBS 8 (Instrumentation):

The commissioning the BLM Beam-Veto function continues. The beam loss signals from the PMT heads arrives a few hundred nanoseconds ahead of the 50 ohm Beam Sync signal. As a result, the BLM cards can not generate a veto pulse for the same macro pulse that triggered it. The initial solution was to make use of the periodic nature of our tune-up mode at 2Hz and predict the arrival of the next pulse. In attempting to implement this method, it was observed that the pulse to pulse accuracy of the existing pulse control electronics is only 0.1%. This means that in a pulse mode with a period of 0.5sec (2Hz), the pulse-to-pulse jitter of the macro pulse will be as much as 500 us. The BLM electronics was then trying to place a 400 us veto window over a 250 us signal whose arrival time was fluctuating within 500 us. The correct solution will be to implement the new pulse control electronics in the drive laser clean room which will not only have better pulse-to-pulse accuracy but will also be able to delay the gating of the EO cells which will delay the light pulses to the cathode, giving all the other electronics in the machine including the BLM cards a pre-trigger beam sync signal to use. The upgrade of the pulse control electronics is scheduled to occur during the July shut-down.

The firmware in the DLPC chassis has been upgraded to include Beam Mode 3 into our tune-up mode commissioning use. The redefined mode will be the same as Beam Mode 2 which has a 0.05% duty factor limit (i.e. 250us at 2Hz) except that Beam Mode 3 will allow pulsed beam with duty factors as much as 0.15% or 750 us at 2Hz. The MPS will provide the proper permissions to enter this mode.

There were errors identified with the QT/GC Panofski quadrupole & vertical trim combo magnet. The magnet measurement group made an access to check it out but was unable to identify what was wrong. The work around was to use other elements to give the required vertical trim. Upon further investigation the jumper cables that ran upstairs were wired incorrectly. This has been fixed. Work continues on the GC trim power supplies. These need to be 4 quadrant floating supplies to be able to ride on the 75 volt bipolar quad supply. The high power dump Vertical and Horizontal Fast Raster Control chassis and power supplies were installed and are awaiting the magnet for testing.  The schematic for the HVPS Control Chassis Analog I/O board was completed and signed off.  New boards need to be ordered so one can be stuffed and tested for installation.

The crystalline quartz windows for GN/HR experiment are in. The amount of pressure that they can withstand must be determined. An apparatus was designed to apply a known pressure to the piece of quartz in order to determine its maximum load capacity. The device has been partly assembled, and the procedure documented. The experimental procedure has been written and will be performed shortly.

The W&M implantation station is down. The I&C group is attempting to help in troubleshooting in between the 16+ hour days commissioning the FEL. People are still smiling - could be rigor mortise.

The documentation on the Optical Cavities Analog Breakout Chassis is proceeding well. The check prints on the HR & OC Analog Buffer Board are in the progress of being marked up so the schematic can be completed.  The fabrication of the chassis is completed and the wiring is 95% completed, the chassis will be turned into EECAD for schematics and fabrication drawings as soon as it is ready.

Performance Integration of the I&C systems - The new database at: http://laser.jlab.org/fel is now our one-stop-shop for access to: system documentation, cable lists, maintenance & commissioning priorities, performance logs, IOC reboot call lists, operations & check-out procedures as well as all other support notes and archived information for the I&C systems. As the system is still new, we are engaged in the data entry process, but current group activities and system configurations changes are being documented with this tool.

WBS 11 (Optics):

This week was devoted to operating the optical cavity hardware "for real".  Given the uncertainty in cavity length, we had to scan the cavity length well beyond the 1mm range we had anticipated ever needing, and found that we had some drifts in the HR mirror orientation to contend with.  That made attempts to lase more difficult.  When the laser did not start after repeated length scans, we opted to look for changes in the spontaneous emission output, and found out diagnostics were unable to detect them.  We setup a simpler arrangement, and this worked well.  The failure of the cavity to show the expected length enhancement could arise from several factors, one being the astigmatism in the high reflector making it harder to align with HeNe lasers.  The accumulation of several factors made it clear that we interrupt operations in order to a) allow Survey and Alignment to perform another determination of the cavity length, b) replace the HR mirror with a spare, and c) incrementally add some extra functionality to the optical diagnostics.  This is all occurring as of this writing.  We also found that with use, one of the ultraviewers was becoming very air pressure dependent.  We instituted a temporary fix by adding a pressure regulator, and will incorporate a better fix in the next few weeks.

The drive laser performed flawlessly, however it is clear we need more power.  We are going to install the fast shutter as a replacement for the second EO cell, this will raise the throughput by

~20-25%.