MEMORANDUM

To:	Distribution

From:	F. Dylla

Subject:	FEL Upgrade Project Weekly Brief – March 3-7, 2003

Date:	March 7, 2003

Highlights:

We had an important and successful project review with ONR, NAVSEA and DOE this past Monday.  Our contract monitors were able to see the FEL Upgrade in its completed first light configuration prior to the start of the review.  We are cleaning up punch list items on our commissioning list as noted below as the gun components are being prepared for re-assembly later in the month.  The last remaining magnets for the high power configuration (in the 2nd recirculation Arc) were mounted on the qualification stand this week.

Commissioning Activities:

Beam Transport:

The first of two remaining GQ dipole magnets for the 2nd recirculation ARC went on the magnet test stand yesterday.  The Purcell gap glue down for the 2nd ARC 180 bend dipole (GY) was successfully completed this week and the magnet is being reassembled today for start of qualification measurements next week.

Controls and Diagnostics:

The switched electrode Beam Position Monitors are ready for control room checks.

Optics:

The insertable optical dump assembly is being installed today.  This assembly will allow the cavity length measurements and adjustments to begin next week.

Photoelectron Gun:

The gun ceramic stack assembly (without the electrode structure) is cleaning up nicely with a 250C bake all week while the electrodes are being prepared.  Repolish of the ball electrode continues.  In parallel, all other gun parts are being cleaned and pre-baked so that all parts can be staged for re-assembly.

Special Meeting Notices:

FEL Users and Laser Processing Consortium Workshop:  March 19-20, 2003

Our annual users meeting will be held on March 19-20 at the CEBAF Center Auditorium at Jefferson Lab.  This meeting is open to anyone interested in past and planned future use of the FEL User Facility for basic, applied and mission related R&D.  The preliminary agenda for this meeting is posted on the JLab WEB site.

FEL Upgrade Cost and Schedule Teleconference:  March 24, 2003

FEL IR/UV Upgrade Semiannual Review:  April 9-10, 2003

At Jefferson Lab (ONR/AFRL/DOE invitees only)

Management:

On Monday, March 3rd we held a project status review on the FEL Upgrade project for our ONR and NAVSEA project managers.  Topics of discussion included the status of the FEL Upgrade hardware qualification and commissioning activities, negotiation of the revised ONR/Navy MOA for the second half of FY03 FEL Upgrade activities, technical discussions on the gun, magnet, optical systems commissioning, technical discussion on the cryomodule design and fabrication, and initial discussion on JLab's plans for FY04 activities including support the Navy's high power FEL development program.  A draft MOA was agreed upon, signed by our DOE contract monitor and forwarded to ONR HQ for signature.  On Thursday a draft agenda was forwarded to the ONR/AFRL and DOE program offices for the upcoming April 9-10 semiannual project review which will include many of the topics discussed in the March 3rd meeting.

On Friday March 7th G. Neil attended (at NAVSEA's request) a review of Northrop Grumman's studies on FEL development for naval applications.

WBS 4 (Injector):

The hot nitrogen purge for the gun chamber was turned off on Monday.  The assembly has been kept at 250 C all week while the electrode structure is being prepared.  The gun chamber pressure at 250C peaked at 3.5 10E-6 torr and has since fallen to 4.3 x 10E-7 at the same temperature.  The residual gas spectrum is now dominantly (>99%) hydrogen) and we have been monitoring the clean up of residual hydrocarbons all week. After checking the partial pressures early next week, this bakeout process may be terminated.

The steps remaining to complete re-assembly and high voltage conditioning of the gun were scheduled at the daily task level so that we could add extra labor where needed.  The cathode support electrode has been re-polished; the ball polishing started late last week and should finish up next week. In parallel all the other gun parts are being re-cleaned and rebaked.

In the process of requalifying all cleaning procedures, we found that DI water from the R&D Chem Room no longer meets specifications.  All DI water in use anywhere in the project is now coming from the Production Chem Room until the R&D Chem Room source is requalified.  We are also checking the integrity of the dry nitrogen purge lines that are in the FEL Vault using on of our clean RGA systems.

WBS 6 (RF):

The RF systems are complete and need only maintenance to keep them operational.  All systems were operated last night except zone 2 that had a Phase Imbalance fault.  This will be repaired today.  Maintenance testing will be run again this afternoon if machine time is made available.

WBS 8 (Instrumentation):

Effort continued on the commissioning of the transport system from racks FL05B10 thru B13. Commissioning effort has begun on the DY, DW string and the 5 kW extraction power supply for the temporary dump.  Installation of the 896 power supplies has been completed in Zone 1 and 5.

SEE BPM installation was completed except for the GY in the 2nd Arc String.  Testing can begin next week.  Commissioning of Beamviewers, Ultraviewers and the insertable mirrors continued from the 3F region to the Output Coupler.  15 additional Beamviewer cameras are available for installation as assemblies become available.

Layout of the optical cavity process flow and analog signals continue.  The three chassis fabrication will begin next week.  The two Machine protection - Machine Mode interface chassis are completed and are waiting on return of the interface PCBs.  The cables are being installed for these from zone 1 and 5 to zone 2.

Drawings completed this week:

F0190 - High Voltage Interlock Analog I/O Board

F0191 - High Voltage Interlock Comparator Isolation Module

F0192 - User Lab Patch Panel Front

The check-prints for both schematics and board layouts on a number of projects have been reviewed and marked-up for final prints.

F0117 - VME Interface Module

F0118 - 4 Channel Fiber Driver Module

F0119 - 16 Channel Relay Module

F0079 - General Purpose VME Carrier Board

F0151 - VME BLM front board

Patty Hunt and Deborah looked at the fire block installation.  She is satisfied that the requirements of the ODH assessment and fire safety have been met.  These will be added to the start-up check list to ensure that if they are removed during a "down" they are replaced prior to start-up.

WBS 9 (Transport):

Work Arounds

Substitution of IR Demo 180° Bend (DY) for the Upgrade 180° Bend (GY) in the First Arc and installation of a GW beyond the Optical Klystron as a diverter-to-the-dump magnet.

•	The first arc 180 degree magnet (DY) (and the temporary linac spectrometer magnet on the same circuit) passed hi pot check and were powered to 84 A (anticipated maximum of 220 A).  The power supply folks are checking out a DC overload and leakage to ground problem that appeared at that current value.

•	The temporary diversion dipole at the end of the optical cavity, used for pulsed operation was hi potted, and then connected to its power supply.  An attempted turn-on revealed a false water supply fault to the power supply. The power supply folks are fixing it.

Dipoles

Optical Chicane Dipoles (GW)

•	No progress.

Injector Dipoles (DU/DV)

•	No progress.

Arc 180 Degree Dipoles (GY)

•	The Purcell Gap Shims for the upper core were glued in place passed inspection and the magnet is being put together today.

•	Wang NMR postponed potting on this magnet to concentrate on the replacement coil for the GX below.

Arc Bend & Reverse Bend Dipoles (GQ, GX)

•	The first of the GQ magnets was placed on the test stand.  A temperature switch short to the main coil delayed further testing until Monday.

•	Wang NMR finished making the replacement GX coil for the #2 GX Dipole.  We will attempt to air freight it today.

Quadrupoles

Trim Quad (QT)

•	The additional coils to modify the remaining two quadrupoles for the second arc to add the vertical corrector function were received from Milhous Co.

Sextupole (SF)

•	No news.

Octupole (OT)

•	The order is ready to be placed anticipating the availability of funding.

Correctors

•	The parts for the horizontal optical chicane corrector  (GZ) are being made in the shop.

•	Robin Wines found a 0.5% solution for a saddle shaped, air core vertical corrector in the optical chicane. Specification is 1 %.  She is sketching the magnet and its holder for the shop to fabricate and they are ordering the tooling material.  We have the #14 square conductor.

Beam Line and Vacuum

•	Hiroyuki checked polarity on a number of the quadrupoles and correctors after the cryomodule and in the return leg.

WBS 11 (Optics):

We continued to address some contamination issues that were discussed in last week's WBS 4 report.  We saw evidence of contamination in the electron beamline we installed, and in the pump cart we were using, so we initiated a hot nitrogen purge on the former and a bake of the latter.  Both activities were successful in removing the contamination, so we intend to pump the beamline down so we can make progress with optics system commissioning.  It will have to be let back up to install "paddle viewers" in the optical chicane, but that will not be a lengthy activity.  The HR pump down continues, sampling with the RGA shows water vapor as the primary residual gas.  We will continue to let the ion pumps work.  Meanwhile, the OC vacuum vessel has been hot nitrogen purging for the entire week.  As we are installing the insertable mirror assembly in a first light configuration today, we plan to let it up to 760 Torr, connect it to the insertable mirror assembly, then begin re-pumping the entire system down.

One OCMMS optical assembly is being aligned and should be ready for installation next week.  We determined the lens parameters to mode match the ultrafast laser into the optical cavity, and have begun to assemble the optical hardware.  We plan to begin alignment next week.

Both ultraviewer assemblies have been upgraded with central apertures, motion control on the mirrors, and remote controlled attenuators.  They will be installed next week.  Work continues to clean and paint the grout for the optical cavity vacuum vessels and the diagnostics platforms to minimize dust.  Working with the I&C group, we resolved some hardware connections and a software problem to get the ultraviewers operating under remote control.  They are making progress on getting the laser safety shutter and diagnostic viewer connected as well.  Both the enclosure and the optical hardware for the THz diagnostic for the injector are assembled and ready for integration.

The impeller on our facility chiller was replaced and we once again have chilled water for the user labs.  We plan to have the service engineer back to complete the installation the week of the 24th.