MEMORANDUM

To:		Distribution

From:		F. Dylla

Subject:	FEL Upgrade Project Weekly Brief –May 10-14, 2004

Date:		May 14, 2004

Highlights:

This week we completed the second week of our 3-week shut down prior to starting up with the newly installed third cryomodule in the FEL Upgrade linac and a new photocathode.  By tonight we will have completed all of the items we had planned for this week and are on track for starting up operations on or about Monday May 24th. Significant accomplishments this week include:

- Improvement of the vacuum and diagnostic hardware in the beamline between

the photogun and the injector cryounit (this included replacing  an ion pump and getter pump; installing a new beam tube with an internally evaporated getter coating, and replacing a beam position monitor). This hardware along with the photogun will all be baked at 250C starting later today.

- A new photocathode was prepared with an anodized ring around the outer circumference in order to minimize halo production. The cathode was installed

in the gun vacuum chamber. The bakeout of the gun chamber starts today. This is typically a week long process.

- We modified an important connection on the Machine Protection System (MPS), that shortens the time constant between the detection of an arc in the injector rf window assembly to the drive laser EO modulators from 500 microseconds to 32 microseconds. This should significantly lower the potential for arcs in the injector to initiate arcs and possible cathode damage in the photogun. (Thanks to Todd Smith for this suggestion).

- The injector cryounit was cycled to 20k and desorbed gases from the both the beamline and waveguide vacuum systems were monitored. We observed only minor amounts of He and H2 which confirms that we do not have any significant He leaks in this system.  A similar 20k cycling of the first linac cryomodule is planned for today.

- We have completed the modifications (including adding extra coils) to the sextupoles in the first recirculation to allow operation at 150 MeV (the new energy limit with the 3rd cryomodule).  Modifications on the sextupoles in the second arc started yesterday and will be completed by early next week.

- New high power shunts were installed in the arc magnet power supplies to allow operation at 150 MeV.

- Dave Douglas and George Biallas designed a skew quad system that can be installed in the existing back-leg with no interference as a new hardware system for dealing with potential “beam-break-up” (BBU) instabilities if low current thresholds are observed with the third cryomodule. This system was designed using existing spare quadrupoles that will eventually be used in the UV chicane.

- Couplers and RF diodes were installed on the HOM load terminations on the third cryomodule to allow us to observe HOM power for planned studies of BBU thresholds and amelioration methods.

- The final alignment was completed on the quadrupole assemblies upstream and downstream of the third cryomodule.  This module is now ready for hot check-out procedures scheduled for next week.

- The first 3 micron outcoupling (OC) optic was installed in the OC assembly along with completion of some housekeeping items. On Monday new high reflector (HR) optics at both 6 and 3 microns will be installed in the HR assembly

- The largest vacuum pipe in the THz beamline from the optical chicane to User Lab 3 was successfully installed this week.

Finally, we spent considerable effort this week preparing a detailed plan for re-start of operations with the hardware described above and the 3rd cryomodule.  This plan along with two reports which further describe our FEL modeling results and emittance measurements were forwarded today to our Navy program managers and FEL steering committee for their review and comments.

I would like to thank all the troops who contributed to a very successful week of completed shut-down activities and spirited discussions on our start-up plans.  I apologize for my omission last week of the Mechanical Engineering Group for their efforts which insured that last week’s installation of the 3rd module went smoothly and for this week’s machine modification tasks.

If next week goes as smoothly with the gun bake-out, completion of the optics installation in the HR assembly and the numerous “hot check-out” procedures on all the FEL systems, we will be re-starting our campaign for 10 kW on May 24th.

Management:

We compiled several reports responding to action items from the May 6th Navy review (noted above) and distributed this to our Navy program managers and FEL steering committee.

We sent the bimonthly FEL Upgrade financial report to the DOE and ONR Program Offices.  The project monthly report for April for the Army funded THz project was sent to the DOE and Army Program Offices. With the initiation of the Phase 4 (FY04) UV FEL project last month, a new monthly report series is being prepared.

On Weds. May 12th we had visitors from Dahlgren and NAVSEA to discuss the NAVSEA/JTO funded laser-materials lethality experiments planned for initial user operations of the FEL Upgrade. The progress in the design of the interim optical transport system was discussed.

WBS 3 (Beam Physics):

Evaluation of recommended BBU suppression methods has led to implementation schemes for two likely candidates. The first, point-to-point imaging, uses a phase trombone in the backleg (3F) region to independently vary horizontal and vertical phase advances without significantly altering the betatron match. This allows steering of a "BBU-driven kick" so as to null the resulting displacement at the second pass through the offending cavity. It requires only a software script to alter operating excitations of existing quads.  The method has been documented in a JLAB-TN available at http://www.jlab.org/~douglas/FELupgrade/technote/JLABTN04017.pdf

The second, H/V phase space rotation, was determined as noninvasively tractable using a 5 quad rotator built out of available components. This can be turned on and off at will, and can thus be rolled back to the nominal operating configuration without difficulty.  It is documented in a JLAB-TN at www.jlab.org/~douglas/FELupgrade/technote/JLABTN04016.pdf .

WBS 4 (Injector):

As noted in the highlights section above, a new cathode was prepared including an anodized ring to suppress halo formation.  After hydrogen cleaning and a pre-bake the cathode assembly was installed in the gun chamber today and the chamber is currently being prepared for a week long vacuum bake at 250C.  We also made the planned modifications to the vacuum pumping and instrumentation in the beamline between the gun and the cryounit.  This area will be baked at the same time as the gun chamber.

Gun HVPS - The current measuring amplifiers were modified to reduce noise and adjusted to minimize their errors between -200 kV to -500 kV to 0.01 ma.  The maximum current readback error is -0.1 ma at 0 kV.  This will allow better current monitoring during high voltage processing of the Gun.  The HVPS Tank was opened and the stacks inspected and wiped.  There were no visible particles on the stacks.  Very minor amounts of dust were wiped off the bottom of the tank.  The Conditioning Resistor and Mechanism were inspected, several screws tightened, and the Mechanism was reinstalled.

WBS 6 (RF):

Zone 1 - The Quarter was cryo-cycled to remove any trapped helium and hydrogen gases.  Little of either gas was found.  The power supply for the cavity waveguide ion pump was found defective and replaced.

Zone 2 - The cryomodule for this zone is being cryo-cycled today.

Zone 3 - This zone is ready for its final operational testing.

Zone 4 - This zone is operational.

WBS 8 (Instrumentation):

Well another screamer of a week has passed by. The I&C team is grateful that proper bakeouts of the gun region takes more than a couple days; the time has been put to very good use. All optics and parts were ordered for the streak camera installation at ISM2F06.  The camera will be taken down next week and setup prior to resuming operations. Spare channels from the cryo diode were rerouted to the quarter and to the module in zone 2 for monitoring the warmup and pump out.

New BPM electronics are being installed for the BPM in the injector line. The BPM is a short stripline, the electronics will be the Switched Electrode Electronics(SEE) type.  We will also run a single heliax cable directly above to Zone 1 as an experiment to look at the longitudinal distribution on our sampling scope (7 picosecond rise time). An initial plan has been devised to look at both beams in the linac BPMs. We purchased fast RF switches (10 nsec), initially these will be used to run at the beam frequency and turn on and off for each individual micropulse of the (accelerating beam) and off for the all of the other micropulses (decelerating beam or vice versa).  Step two will then use two sets of BPM electronics and the switch will route every other pulse to same electronics giving a live display of both the accelerated and the energy recovered beam simultaneously. The frequency response of the dump BPM (IPM1G03) was measured in preparation for the HOM studies.  All four of the electrodes will be wired to the gallery for monitoring on the spectrum analyzer as the current is cranked up.

The Framegrabber's system for calibration of the beam viewers is progressing well.  The user interface dynamically adjusts itself depending on what type of viewer needs to be calibrated. Testing on the different features has been completed as they are finished. Once the interface is finalized the instructions for use will be written; then a walk-through will be performed testing the whole system.

Re-installation of the magnet, BPM, Viewer and vacuum power/signal leads was completed for the 1F03, 1F04 region. The other 2 modified high voltage shunt modules and load resistors for the GY dipoles were received from EES and installed.  Check out of the box supplies will begin early next week.  Wiring was completed for the add-on coils for the 1st Arc sextupoles and the 2nd Arc sextupoles wiring is in progress.

Modifications to the Beam viewer Chassis began in order to upgrade the EPICS interface with CAN-BUS.  The chassis have had mechanical modifications to accommodate the RJ-45 CAN connections and the associated wiring inside the chassis.  All of the modifications to the chassis can be reversed to the previous EPICS interface with relative ease.

SF6 pump plans were reviewed and final preparations are being conducted for pre installation. We continued support of the THz beam line installation.  Additional read backs were installed for the 1/4 cryomodule temperature diodes.  Repairs and/or assembly of 8 viewer cameras were completed.  Population of 2 Temperature diode back planes has begun.  A spare stepper motor chassis was completed and tested.

The new backplane for the Si Diode Temperature Control Crate was populated as were the Shield cards for the crate.  All parts are on order to complete the backplanes as well as those required to complete the upgrade of the video system.   Safety issues concerning conduct of the THz experiment were discussed and responsible parties designated in the areas of instrumentation, fire prevention, electrical power installation.

WBS 9 (Beam Transport):

Sextupole Lite Re-coiling to obtain higher field

•	In Magnet Test, the one sextupole lite with 50% greater coils tested well. A small amount of saturation was evident at the maximum current of 20 A. We also needed fans to keep the coils cool at the 20 A setting.

•	We are treating the first arc differently because it will run at about 14 A at 150 MeV/c while the second arc runs at half that current. Thus, only in the first arc, we are setting a software and power supply limit at 20 and installing a set of four fans to be running all the time.

•	In the second arc, we will set the power supply and software current limit to 15 A without fans.

•	The sextupole task is going slower than we originally scheduled, but it matches the pace of the down. Kevin Sullivan has shouldered the entire tedious task because Mike Beck and Don Bullard (gun work) can’t help. The sextupoles in the first arc were split from doubles in two positions to singles in four positions, one was tested, and all were recoiled and wired up and aligned. One of the four sextupoles in the second arc was recoiled and wired up without moving it. The magnets at this end will need no alignment work.

Skew Quadrupole Eigenvalue Exchange Module (SQEEM)

•	We laid out the positions for the seven quadrupoles of this beam rotator to intersperse between the 12 quadrupoles of the return leg before the optical chicane per David Douglas’ DIMAD. We are lucky that there is no interference with existing hardware such as beam tube bellows or girders.

•	We are also fortunate to have all seven quadrupoles and their power supply, trim card circuits available (borrowed from the UV line) plus two of the seven stands. The remaining stands and the 7 simple girder plates will be here by June 1. Five of the quadrupoles will need additional work to make them skew quads. They need taps in their cores to mount them at the 45 degrees to their normal orientation and they may require some refiducialization by the alignment group.

Wiggler

Electromagnetic Wiggler for 2.8µ

•	We hoped to start assembly on Wednesday. A last minute glitch of the water jet cutter not being accurate at the .036 inch over 8 feet level halted production of the Kapton insulation strips. All other parts are in tolerance. The water jet vendor recalibrated the encoders on the machine and made the insulation strip correctly. This was proven with some trial fits of the first parts from the new calibration. Assembly will start on Monday.

Sextupole (SF)

•	Procurement on hold, pending 10 kW efforts

WBS 10 (Wiggler):

The wiggler poles have all been mounted on the magbases and one magbase has been pinned to its strongback.  The measured height of the poles is uniform to ±0.001".  This should produce acceptable field variations.  The special end correction magnets arrive today.  The magnet test facility is ready to accept the wiggler.  STI Optronics hopes to start permanent magnet block installation by next Tuesday.  So far they are holding the original schedule.

WBS 11 (Optics):

Plan A is to obtain low loss 6 um optics.

Plan A is to obtain low loss 6 um optics.

The flaws in the coating's of both HRs was more carefully documented with our noncontact profilometer and photomicrographs.  We will send the optic with the worst flaw back for rework. The other is being installed.

Our three Plan B's had the following progress:

Cryomirror (with G. Biallas input):

- The inner perimeter of the cryogenic mirror mount was successfully indium plated.  The indium annulus still needs to be prepared, we've been delayed due to competing work required for the accelerator.

- We tested a new cooling setup where the output cryogen is subcooling before it is brought to vapor.  We were able to double the flow rate (to ~ 2 grams/sec) before vibration became too severe to take interferometer data.  We will carry these tests forward once we get the mounted cryomirror.

- Based on this positive result, we re did the drawings for the exhaust line being vacuum insulated and restarted the task in the shop. The shop received the lengths of flex hose for this modification.

2.8 micron mirrors:

3" dia OC mirrors are in fabrication.  Metrology for the mirrors in hand continues.

Scraper outcoupler:

A requisition was placed for new substrates.  We'll have them coated with low loss coatings.

Other activities:

Work on the HR assembly this week mirrored (pun intended) what occurred in the OC last week.  RTDs were added to better understand the amount of power being absorbed by the mirror mounts.  The ion pump was removed and baked.  Installation of the HR mirrors has been delayed into next week, as we had problems getting them bonded with low aberrations.  We received a new OCMMS (HR side) viewport assembly, which will be installed next week.  On Tuesday we had a representative from Veeco Metrology here to optimize the noncontact profilometer and give us more training.  On Wednesday we met with representatives from NAVSEA.

Terahertz:

We took advantage of the FEL vault being open all week.  The beamline support structures were installed after the sprinkler system had been moved.  The large 13 foot pipe that will carry the beam from the vault to lab 3 was installed. Mirror boxes M2 and M3 were hung from the ceiling support and connected to the long pipe.  M1 arrived on site this week, and will be sent to Brookhaven for metrology.  A second meeting was held to discuss safety and operational issues.  The THz beam will be treated as a class 4 laser.  A follow-up meeting was held with radiation control and installation of the requisite shielding modifications was started. These will replace those that had to be removed for the installation of the beamline.  Beamline viewers and shutters were also discussed and work commenced on their design.  These are based on modifications to existing FEL viewers which are in-house.