MEMORANDUM

To:		Distribution

From:		F. Dylla

Subject:	FEL Upgrade Project Weekly Brief –May 24-28, 2004

Date:		May 28, 2004

Highlights:

We had a very productive week for the start-up of the FEL Upgrade after the completion of the three week shut down for the third cryomodule installation and photogun cathode replacement.  To ensure start-up at the earliest time this week, we devoted last Saturday to checking out the new or modified magnet systems and Sunday to high voltage processing of the gun.  For the week we have accomplished the following:

- Completed the gun set-up with a new GaAs cathode that showed an initial quantum efficiency of 6.2% (the highest we have recorded).

- Set up the injector (the vacuum improvements we incorporated appear to be worthwhile-we see no vacuum activity with 3.6mA operation).

- Accelerated e-beam through all 3 cryomodules.

- Matched and recovered 88 MeV e-beam.

- Measured 1st BBU threshold (~ 3 mA @ 88 MeV) which is remarkably close to the prediction (within ~10%) of the TDBBU code based on the HOM measurements of the 3rd module cavities.  Kudos to the CASA BBU team!

- With only a brief attempt we were able to raise the BBU threshold to ~3.6 mA by phase advance.

- Lased at 2.2 kW with the above 88 MeV configuration at ~3 mA.

- Measured losses in the new 6 micron HR optic (5x less than previous HR).

- Set-up initial 145 MeV beam with the 3rd cryomodule fully powered, successfully re-circulated and recovered beam at 1 mA cw, (matching activities are planned next week to optimize and push current).

At press time we have successfully completed Steps 1-10 of the 10 kW Commissioning Plan (shown below) that we sent to the Navy and FEL Steering Committee on May 14th.  Of particular note is this important result:

- We now know that the 3rd FEL module carries sufficient current that it will remain in the accelerator. The models indicate the BBU threshold should scale up conservatively with the square root of the energy ratio, so that the present threshold observed at ~3.6mA at 88 MeV should scale by ~1.3x 3.6mA = 4.7 mA (taking credit for none of the planned amelioration techniques).  We remind our readers that Dr. Benson’s models are predicting 10kW at either 6 or 3 microns with the linac operating at 145 MeV and 5 mA.

Commissioning Summary (Steve Benson):

This was a short but productive week of beam operations  Problems with cryounit trips and drive laser software freezes threw some tacks in the road but we were still able to make significant progress.  Monday and Tuesday were dedicated to dealing with punch list items from the shut down and in bringing up the gun.  Since this is a new wafer we proceeded slowly and carefully in high voltage processing. The high voltage processing with the cathode withdrawn was completed on Monday afternoon and we set up for a cathode heat clean.  On Tuesday we made a good cathode (highest quantum efficiency seen to date in this gun) and high voltage processed with the cathode in place.  This went slowly due to a noisy current signal that worried us.  We finished the processing, shorted out the conditioning resistor, and brought the gun back up with the running resistor.  The current noise was gone.  We then did the drive laser alignment.  The aperture for this wafer is smaller than the last so we are exploring the use of smaller spot to reduce scatter and give us more maneuvering room. 
   Wednesday we started beam operations.  After tuning up the injector, we phased up the linac and set the energy to 88 MeV.  We then threaded the beam through the beam transport and to the energy recovery dump.  When we got clean transmission we increased the macropulse current up to 5 mA while looking at the loss monitors.  We had evidence of halo loss at a few points around the machine but nothing in the vicinity of the new module.  This showed that we could transport high current beam through the new module without loss and did not have to pull the module out.  There was no conclusion on the BBU except that the threshold was probably higher than 1 mA. 
On Thursday we recovered the configuration from Wednesday and started to carefully match the beam around the machine.  We also turned on two families of sextupoles in the first arc.  This eliminated the halo loss at two points that we thought were due to transverse beam blowup due to non-linear dispersion.  We managed to minimize both the linear and non-linear dispersion in the first arc.  We had some difficulties in matching because the frame grabber (the WesCam) was not working properly.  We did manage to get a decent match through the machine however and the losses were low.   We then got the laser lasing at 5.75 MHz and roughly setup the energy recovery with lasing.  Finally we tried to run up the CW current and found a hard limit of 0.7 mA regardless of duty cycle.  No evidence was seen for BBU during the trips.  We realized that the current limit in the gun high voltage power supply was still set to its high voltage processing setting.  When it was raised to 10 mA we immediately managed to get 135 pC at 18.7 MHz

(2.5 mA).  We switched to 75 MHz and found a BBU current limit of 3 mA.  This time there was a clear signature on the HOM diodes for the cavity with the lowest threshold.  We then switched to 37.5 MHz so that we could lase and see the effect of lasing on the threshold.  Lasing raised the threshold only slightly from 3 to 3.2 mA.  Finally we changed the betatron phase advance to see if we could raise the threshold that way.  We raised the threshold to 3.6 using this technique.  Problems with the injector cryounit tripping off and the drive laser attenuator freezing up slowed us down in this effort and we finally decided to shut down so that some work could be done to fix these problems. 
   The plan for Friday was to try 145 MeV operation to see if there were any big problems.  If we could operate easily there we would work on BBU suppression at that energy.  So far we have been able to operate relatively easily at the higher energy and we are optimizing the system so that we can ramp up the current. 
During high current running we noticed that beam loss was still significant after the cryounit but was just about non-existent before the cryounit.  The reduction in the diameter of the active area seems to have been quite effective at reducing halo loss before the cryounit. Halo loss is concentrated at two locations in the machine--the injection chicane and the extraction chicane.  Neither showed much vacuum pressure changes when we ran 3 mA CW beam.

Management:

Everyone’s attention was devoted this week to making the start-up from the shut down go as smoothly as possible.

On Monday, May 24th, George Neil and Fred Dylla gave a presentation on the Navy funded  FEL program at JLab to DoD’s Office of Force Transformation in Arlington,Va.

On Wednesday, our new ONR Program Officer, Quentin Saulter made a site visit and witnessed the machine start-up.

WBS 3 (Beam Physics) Lia Merminga:

Beam breakup instability was observed in the FEL Upgrade operating at 88 MeV at ~3 mA of average current.  Signals from the Schottky diodes placed on all 16 HOM ports (2 per cavity) of the CM3 were observed on oscilloscopes, as the average current ramped up. At approximately

3 mA of beam current, both diode signals from cavity 4 grew exponentially from 0 power level, while signal levels from all other cavities remained unchanged. At the same time the beam tripped.  The growth rate was measured to be ~ 5 msec (see attached).  Growth rate, threshold current and mode with the lowest threshold are all in agreement with simulation results.

Further, lasing was initiated and the phase advance of the recirculator was changed by a fraction of betatron wavelength (no systematic search was conducted) resulting in threshold current increase to 3.6 mA.

WBS 4 (Injector):

After three weeks of gun and beamline work, we successfully completed the gun HV conditioning at 424 kV (20% higher than the nominal operating voltage) on Monday afternoon. Shortly after that, we started a heat clean cycle on the newly installed anodized GaAs wafer. On Tuesday morning, we made the first cathode and achieved 6% QE. The QE obtained on first cathode made one year ago after installing a new wafer was 0.6%. We experienced some current noise in the transmission line during HV processing the new cathode with the conditioning resistor. There was no evidence of field emission in the vacuum side. The noise went away once we switched to the running resistor. We will check the conditioning resistor once we have a chance.

On Wednesday morning the new cathode was delivering beam, although halo was observed despite the anodized wafer. Because of the smaller active area, the positioning of the drive laser spot on the cathode is very limited. The laser beam is very close to the edge of the mirror and to the aperture of the window beam pipe, generating significant amount of scattered light. Halo loss used to be a limiting factor while running high CW current because of vacuum rise in the beamline between the gun and the quarter cryo unit. Running 3 mA CW beam used to raise the vacuum from 2 to 3 times in that region.  There is almost no vacuum rise now when running the same CW current, indicating the success of the added pumping in reducing halo loss.

WBS 6 (RF):

Report next week.  (writer devoted to hardware at press time).

WBS 8 (Instrumentation):

Ditto.

WBS 9 (Beam Transport):

Ditto.

WBS 10 (Wiggler):

Ditto.

WBS 11 (Optics):

Plan A is to obtain low loss 6 um optics

While lasing at reasonably high power, ~ 2.2 kW at 3 mA, we used the opportunity to check the loss in the new HR.  Our first measurement, made at a predicted lasing wavelength of 5.75 um, is 450ppm +/- 175 ppm.  In speaking with the vendor, ~ 100 ppm is due to transmission through the coating and substrate into the backplane cooler.  This is ~ at least 5X lower than the mirror we removed.

Our three Plan B's had the following progress:
Cryomirror:
Producing a uniform indium annulus continues to stump our braze expert.  In part, this is due to the tolerance of the fixtures that provide a base for the solidifying indium.  New fixtures are being made.

2.8 micron mirrors:  
3" dia OC mirrors are in fabrication.  We did metrology on one that was fabricated but uncoated.  It surpasses the rms roughness spec of 1 nm by 3X.  Metrology for the mirrors in hand continues.  Mirrors checked so far meet specifications.
Scraper outcoupler: 
No progress since the last report.

Other activities:
A new Nd:YLF laser rod was mounted and installed, resulting in significant improvement in performance.  We now produce 5 W of SHG with ~ 1 deg of phase noise.  SHG powers over

7 W are easily in reach.  Kudos to Shukui and David for their weekend efforts.  We have been bedeviled with the software for the attenuator suspending, and causing headaches for the commissioning team. I&C is working on it.  A lot of work is going on in User Lab 2 to organize hardware more efficiently.  The loaner streak camera's minimum resolution was checked, and found to be long, 18 ps.  The vendor had given us a unit with a total sweep aperture of ~ 1ns.  (Guess you get what you pay for.)  We'll probably install it in the vault to wring out the matching optics and remote control.  New fixtures to hold the PbS and pyroelectric arrays arrived.  The PbS array will be installed on the spectrometer when we have some time.  The pyroelectric array is working on the benchtop.  New PIC-based readout electronics are being designed.  It will be used in the further IR.  We held planning and coordination meetings on the optical transport procurement and installation, with the goal to install vault hardware during the early August down period.

Terahertz:

Additional shielding was placed adjacent to the long vertical beam tube in the vault.  The alignment laser at the backward tangent point was aligned to generate a beam exiting the M1 chamber, which now has a 20mm clear aperture diamond window so that we can carry out tests prior to the installation of M1, and at the same time provide machine beam diagnostics.  The Nicolet Impact-400 FTIR THz Michelson interferometer was re-aligned on this port.  Meanwhile, the mirror mount components were identified and parts sent for cleaning prior to assembly.