MEMORANDUM

To:		Distribution

From:		F. Dylla

Subject:	FEL Upgrade Project Weekly Brief –May 3-7, 2004

Date:		May 7, 2004

Highlights:

This week we were occupied with the installation of the 3rd FEL cryomodule in the FEL linac and with the Navy review of the FEL commissioning progress.  The cryomodule installation went very well. Final preparations were made last Saturday as soon as we stopped beam operations on Friday. By Tuesday the module was in position, rough aligned and cool-down to 4k was initiated. On Wednesday morning the module was successfully cooled to the operational temperature of 2k.  On Thursday the RF waveguides were hooked up and today we completed the vacuum connections for the upstream and downstream linac beam-line.  Sometime next week a final alignment check will be done and all the rf and interlock connections will be checked out as part of the pre-operations check. We thank all the staff that made the installation of this important addition to the FEL Upgrade proceed so smoothly. We required essential and coordinated support from the Accelerator Division installation, alignment, vacuum, SRF, RF, cryo groups to make this happen.

As noted in last week’s report, we discovered a crack in GaAs photocathode. In spite of the ability of the cathode to still provide useable beam, we decided it was best to replace the cathode prior to re-commencing operations.  So we prepared for this change-out along with some related maintenance and upgrades to the beam-line between the gun and the injector cryounit.  We have been running the machine every week but one since the middle of November, so we have accumulated a number of fixes.  For the beam-line, a new ion pump, getter pump and getter–coated beam-line were prepared to increase the differential pumping.  Prior to opening up the gun next week for the cathode change-out we prepared two new cathodes from a GaAs material that has shown higher quantum efficiencies (thanks to testing by the CEBAF Source Group), and anodized a concentric ring on the outer circumference of this material to help cut down on halo production.  (We noted in the review this week that subtle improvements made by Steve Benson on the drive laser transport to the cathode had dropped our halo beam production from the 10-4 to the 10-5 level. We are hopeful that this masking procedure on the cathode will also have incremental benefit on the halo production.  Halo can cause undesired gas desorption from and activation of beamline components).   Also during this maintenance period we are upgrading the sextupoles so that these correction magnets can operate at the new linac energy (~150 MeV) provided by the addition of the 3rd cryomodule.

In addition to our Navy program managers, we were fortunate to have most of the members of our peer review panel at Thursday’s review of our commissioning progress.  We found the opportunity of preparing for the review useful for a self assessment of our progress-and as always- we get useful feedback from our panel. In general the panel agreed with our assessment that we had accumulated a reasonable understanding of the current 2-cryomdule (88 MeV) configuration, and the time was right for exploring the parameter space with the 3rd cryomdule which completes the original hardware specification of the Upgrade.  We share concerns with the current carrying capability of the new module because of possible low damped, higher order modes (HOMs). Several useful suggestions were made to help us plan our beam commissioning with the new module. We thank Todd Smith for a useful suggestion on the use of quad focusing to counteract the deflection of one possible deflection mode if encountered. (You will note that Dave Douglas has already tested our ability to use this option with his lattice model-see below). Also Todd had a useful suggestion for helping us minimize the potential damage due to gas burst induced arcs in the photogun by routing a signal from our injector rf window arc detector to the gun HV control. Kevin Jordan’s I&C team started to implement this change in our machine protection system today. (See below).  A third action item from the review concerns sharing of our FEL modeling parameters with Henry Freund so that code comparisons can be made.  Steve Benson’s predictions of our performance with the current 2 cryomodule and new 3-cryomdule configuration using his spreadsheet and pulse propagation codes were discussed at the review and related results are quoted below.

I thank the entire team and our panel members for all their efforts which contributed to a useful review this week.

We congratulate our colleagues at Rossendorf who demonstrated first lasing with FEL system today.

Commissioning Summary (Steve Benson and Dave Douglas):

Pulse propagation simulations were run this week to check out expected performance with the latest electron beam measurements with both the third cryomodule operated at 5 mA and the new permanent magnet wiggler operated at 85 MeV and 10 mA.  Simulations were also done for 5.75 micron operation at 88 MeV and compared with measured lasing results.  All the pulse propagation results were compared to the spreadsheet results to benchmark the spreadsheet some more.  Good agreement was seen for the predicted efficiency for the spreadsheet, pulse propagation code, and experiment.  The spreadsheet and pulse propagation code agreed with each other on gain but were a bit higher than the measured gain.  The turn on time and detuning curve lengths agreed well with experiment.  Performance at 2.8 microns indicates that, with the current electron beam setup, we can get about 9 kW at 85 MeV with the present bunch length.  If we shortened the bunch this goes up to over 10 kW in the spreadsheet.  Pulse propagation simulations of the shorter bunch will be done soon.  The three cryomodules run at 5 mA produces approximately 10 kW for 5 mA for both the spreadsheet and the pulse propagation code.  Both predict about 9.5 kW.  The gain is about 50% for the new wiggler and 30% for the optical klystron and three cryomodules.

During preparation for the review, we did some reduction of difference orbit data taken during the final day of running. A couple sample first pass orbits (data and modeled) are attached.  We found that consistent agreement amongst the data could be achieved in the usual fashion - by adjusting the transport quad gradient integrals by ~100 g rms - once again confirming the excitation resolution lies at the 1% level. Assuming a reasonably good match to the wiggler, forward- and back- propagation of beam envelopes suggests the machine was not particularly well matched towards the end of the run (Figure 2); this could contribute to some of the largish emittances observed and reported on at the review.

Given the restricted apertures imposed by the installation of Zone 3, we are working toward more robust second pass orbit control. The data taken at the end of the run include both first and second pass configuration; we are trying to deconvolve the second pass positions from the measured first pass behavior. As is evident from the orbit figures, we have implemented HV coupling in the model.

Figure 1: Samples of 1st pass difference orbit data. Notice H/V coupling on second pass through linac.

Figure 2: Beam envelopes. Some mismatch is apparent from the asymmetry of the envelopes in the recirculator arcs, the ringing in the backleg, and the large envelopes in the linac back end.

As discussed in the Review, the following is the basic outline of our commissioning plans when we come back up after this down time is completed.  We are working out the details and will have a complete plan by close of business next Tuesday.

- Turn on FL03 at modest excitation and correspondingly turn down FL02 and FL04, so accelerated e-beam is close to the configuration (energy) when we last ran with 2 cryomodules, & see how well the 3 cryomodule configuration works under near identical conditions.

- Spool up beam power (current), in pulsed mode, and search for BBU.

- If not observed at, say, 5 mA, raise energy, retune, and iterate.

- If observed, start working though BBU suppression methods. (See L. Merminga's presentation at Review).

At either of steps 2 or 3, recovery of lasing can be added as appropriate.

Details of this plan will be fleshed out by C.O.B. Tuesday.

Management:

The focus of the week was preparing for and executing this week’s Navy review.  We thank Gil Graff and the NAVSEA staff for taking the time during a very busy time of the year for attending the review.

In addition to the review, we had folks traveling to and fro to cover several other venues.

F. Dylla gave an invited talk on the JLab FELs on Sunday at the Division of Physics of Beams session for the spring APS meeting in Denver.  On Tuesday, G. Neil presented progress reports on our JTO funded projects at the JTO Project Office in Albuquerque.  On Thursday and Friday, Gwyn Williams and George Neil tag teamed our representation at a meeting at the National Magnet Lab in Tallahassee concerning their plans to incorporate a next generation light source.

WBS 4 (Injector):

Preparations are under way for the installation of the new wafer and for adding more pumping to the beamline between the gun and the cryounit.

Gun: The stalk we had already cleaned and ready to accept the new wafer had the wrong wall thickness tube, so it was cut and re-welded yesterday.  Today it will be cleaned with solvents and later heat-cleaned under vacuum before mounting the new wafer. A new wafer has been anodized and is ready to be mounted once the stalk is clean.

Beamline: The BPM to be installed will be leak checked today. The ion pump and the NEG pump are ready for installation. A beampipe to be installed between the buncher and the cryounit is in the process of being NEG coated.

WBS 6 (RF):

Zone 1 - Work is progressing on the Gun's HVPS.  The HVPS tank is being opened to clean the stacks and remove the Gun Resistor mechanism in preparing for high voltage testing and zero adjustment.  The Quarter cryomodule is to be cryo-cycled next week to remove any helium or hydrogen gases.

Zone 2 - The cryomodule in this zone is also to be cryo-cycled next week for the same reason.

Zone 3 - The cryomodule is in place with all operational cables connected.  Additional test cables will be connected as needed.  It is planned to test this zone on swing shift next week.

Zone 4 - This zone is fully operational.

WBS 8 (Instrumentation):

We are responding to another crazy idea that makes quite good sense; during this week’s review there was a short discussion of the beating the gun has been taking to which Todd Smith responded "Why don't you turn off the gun (close shutter) prior to an arc in the RF." Looking at things closer there was a delay added to the quarter arc detector trip circuit to prevent false trips. This delay is >100 microseconds which is about the right time to potentially cause the problems we have. Detailed measurements are underway and a direct connection from the arc detectors to the Machine Protection System (MPS) shutter is being implemented. BTW this is very easy to do because of the "hooks" available in the system. The MPS firmware was upgraded to incorporate the additional RF zone (3rd cryomodule). The RF FSD (P1) module was checked out successfully and the permissive signal hooked up. Screen changes were upgraded and the mask set for the FSD card was downloaded and checked.

All magnet leads and wiring along with ITV1F04 were removed from the beam line prior to installation of the new cryomodule. Re-installation of the 1F region power and signal leads is in progress. ITV0F02, the cathode camera, correctors and solenoid power/signal leads were removed from the Injector region in preparation for the gun bake. FELTECH1 was replaced by FEL-SALLY in Lab 5, FEL-SALLY and FELTECH15 were upgraded. Progress was made on the Convectron card test fixture and fabrication of the SCL FSD/ MPS test fixture is complete and wiring is in progress.

Final preparations are being made to the optical holder, cryomodule electronic cover, and camera table. All finished products should be returned to the FEL the week of 5/10/04. Continued support of the THz beam line installation in Lab 3 and the 4F region. Additional stepper motor cables were installed, terminated, and tested for the High Reflector I & C rack to support the THz experiments. In order to accommodate future requirements for the third cryomodule a Baratron Power Supply was fabricated and installed.  This will provide operational power and read back from the five Baratron Pressure Transducers as well as provide an interface for remote EPICS read backs.   The pre-fabricated jumpers were installed on the test sextupole with the new "add on" coils for the Poles. All the magnet shunt modules have been either upgraded or checked for correct scaling and re-installed. The high voltage shunt for 4F00 was also installed. This module has had their transzorbs removed and replaced with 450V FET's with the read back scaled for 0-300 V. New 10 ohm water cooled load resistors were installed for the Optical Chicane region. A test plan is the works from D. Douglas to run the magnet strings with the new excitation curves early next week. 
   The stepper motor controls for the drive laser's variable attenuator began crashing repeatedly shortly after the installation of a new VME board into iocfel10 for the drive laser's automatic switch to internal RF (by auto switching with loss of master oscillator).After a few days of careful inspection and troubleshooting, the problem was found. The VME crate (iocfel10) for the drive laser controls requires that a jumper be placed on the backplane if a card is inserted that does not handle interrupts. 
   Progress is being made to enumerate and organize all of the process/applications running on each of the iocs in the FEL as well as all of the embedded controllers running in the field. As many of our systems requirements have evolved over the years, we have grown overly dependant on the 'expert' knowledge of those few who are familiar with the systems as they have been installed. For obvious reasons, the software running the FEL and its related documentation is being included into FEL configuration control.  As part of the completion of the Framegrabber manual, a system is being designed to simplify the process of calibrating beam viewers and SLM's. Along with the intent of making this procedure easier, it is being established to help eliminate potential errors by the person performing the calibration. A user friendly interface is being implemented that will present different interfaces depending on the type of viewer being calibrated. The instructions will also be specific to the viewer type. Backups will be saved in order to provide a rollback in the event of an untimely miss calibration. A log will also be kept to keep track of the changes have been made and what the changes were. 
   Revision A to the Video Crosspoint Switcher board is on order and parts are being purchased to complete the video upgrade.  The new backplane boards for the Si Diode Thermometer Crate have been received and are in the testing phase.  Parts are on order to complete this project once the modifications to the circuit board are completed.  Front and rear panels to complete the 4 Channel PreAmp Chassis are on order and expected early next week. 
We have purchased two industrial oscillating fans for use in the vault during maintenance. 
   The equipment in the conference room will be moved and covered today. If there is other computer equipment in the areas that will be affected, please let me know as soon as possible.

WBS 9 (Beam Transport):

Sextupole Lite Re-coiling to obtain higher field

•	We split the magnets of the first arc, added coils and wired one up for up for measurement in Magnet Test. Next week we will add coils to the remainder of the magnets.

Wiggler

Electromagnetic Wiggler for 2.8µ

• 	Sixteen of 48 cooling plate halves have their brazing complete and are being coated with clear coat.

• 	A first batch of 6 Kapton insulation layers is cut and being test fit on the completed cores.

•	 Core machining is complete and it will be covered in clear coat.

• 	PECo is making two installation fixtures of bent lexan to handle the conductors and insulation. The entire outline of the fingered fixture is being made by water jet cutting.

• 	We shipped the second batch of Jlab supplied ancillary fabricated parts and hardware for arrival at PECo on next Tuesday.

• 	We plan to visit PECo for start of assembly next Wednesday.

• 	We reached agreement on the additional costs of the wiggler associated with details of assembly that were not available in the documents when the contract was signed. These include mounting trim coils and manifolds and combining the two units into one wiggler for shipping.

Sextupole (SF)

•	Procurement on hold, pending 10 kW efforts

WBS 10 (Wiggler):

STI is assembling the poles onto the backing beams this week in preparation for magnet installation next week.  The magnet measurement setup is ready to go.  Final magnetic measurements are on schedule for June 15.

WBS 11 (Optics):

Plan A is to obtain low loss 6 um optics.

Additional metrology was done to confirm the new HR mirrors met figure, ROC, and roughness specs.  A small flaw has appeared in both optics since they were received last week.  So we can continue our progress, one is being prepared for installation, the other will be sent back for rework.

Our three Plan B's had the following progress:
Cryomirror:
We have more delays in the cryogenic mirror mount, in part due to furnace problems

• 	We have a new cooling setup where the output cryogen is subcooling before it is brought vapor.  We plan to test it later today or early next week.

2.8 micron mirrors:

3" dia OC mirrors for use with the 2.8 um wiggler are in fabrication.  We now have on hand the 2" dia HRs and OCs, as well as the 3" dia HRs for this configuration.  We mounted a 2" OC mirror that is figured to be used with our existing cavity and wiggler configuration, checked to confirm it still met specs, then installed it yesterday.

Scraper outcoupler:

No additional work scheduled in the near future.  We are devoting time to analyze the results, and compare them with theory.

Other activities:

With the down period extended, we slightly expanded our scope of activities and split work in the vault across two weeks.  This week we concentrated on the OC assembly.  The unused 2" mirror is now occupied, and so it's LVDT wiring was fixed.  RTDs were added to better understand the amount of power being absorbed by the mirror mounts.  The ion pump was removed, baked, and reinstalled.  Next week we concentrate on the HR assembly, which receives two new mirrors (6 um and 2.8 um), the RTDs, and the ion pump maintenance.  We also plan to install a new OCMMS (HR side) viewport assembly.

We checked out the loaner streak camera by using the pulsed (~ 50 ps) output of the drive laser. We prepared updated slides for Thursday's Navy  review .  G. Neil gave presentations of our JTO projects at a review held in Albuquerque.

Terahertz:

With the opening of the vault, the beamline support structure anchors were installed.  There is minor interference between the ceiling support structure and some water and sprinkler pipes.  Plans were made to move the pipes to the side.  M1 has finished initial machining and is ready for polishing at the vendor.  An initial meeting took place to determine the safety requirements for operations of the beamline.  A number of beam profile calculations were performed in preparation for a follow-up meeting.  It is, however clear, that a second beam shutter will be required and that this will require an additional port close to the second diamond window.  A further minor change to the beamline that is required is the addition of spreaders to the first bellows assembly to take the vacuum force.