# MEMORANDUM

To:		Distribution

From:		F. Dylla

Subject:	FEL Upgrade Project Weekly Brief – November 8-12, 2004

Date:		November 12, 2004

Highlights:

We continue to make progress toward re-establishing high power lasing at short wavelengths:

-	we established a good injector setup and verified a procedure for checking and re-establishing performance on a daily basis

-we established recirculated beam in the with good orbits to the dump; matching of the transverse beam is reasonably good up to the wiggler

-we briefly ran CW beam to verify low losses

-we began characterizing beam transport in the new wiggler

-as we performed operational checks several minor issues were uncovered including wiring issues with the 2nd arc and wiggler trim magnets (short and polarity problem, respectively), and a vacuum interlock problem with the optical transport line which inadvertently let the beamline up to dry nitrogen.  These systems issues will be resolved by mid next week and we will finalize the orbit setup for lasing.

We also continued out preparations for bringing high power beam upstairs by completing that portion of the Optical Transport System.

During a second shift activity, a new low level RF system designed by collaborators at Cornell University was successfully tested without beam. The system shows a much faster time response than the original CEBAF system. Beam tests will follow

Management:

We released the August and September UV Monthly Reports.

Carlos Hernandez-Garcia and Robert Rimmer participated in the High Average Brightness Workshop at UCLA.

We have been working the action items from our meeting last week with AES on the plan for the cryounit assembly and Injector Test Stand construction and tests.

December 8 and 9 has been chosen for a Project Status Review of our THz program with Army Night Vision Laboratory.

Commissioning (Steve Benson):

On Friday we performed quadrupole centering in the machine and found a good orbit.  The design match was reasonable and, with the THz chicane powered, low loss transport to the dump was possible. 
   Monday was spent certifying the personnel safety system (this keeps people out of the vault during machine operations), and the Laser Personnel Safety System for the optical control room (this keeps all but FEL Operators out of the optics control room during laser operations). Both systems passed their certifications. 
   Tuesday was devoted to matching the beam around the machine and doing an initial test of the emittance software recently developed by Nobuyuki Nishimori, visiting from JAERI.  The first data indicated a few problems that need to be ironed out but also was consistent with a 10 mm-mrad emittance.  The match was completed up to the optical chicane.  The shunt in this chicane was not working so it did not make sense to match beyond that point. 
   Wednesday, with the optical chicane shunt repaired, the match was completed through the rest of the machine.  A problem was discovered with the path-length magnets.  It was found that the second arc steered when the path length corrector was changed and a very large change in the path length supply was necessary to set the path length. This was due to two problems, one a wiring problem, one an internal short in one of the four coils.  With the THz chicane off it was possible to get a decent longitudinal match and cleanly energy recover the beam.  The beam was run CW for a brief run.  The beam loss monitoring system must be re-calibrated before running significant amounts of CW beam.  Wiggler commissioning with beam we then started.  The DC field compensation field was set and it was found that the trim coils at either end of the wiggler were wired backwards.  We reversed them and were set to test out the new configuration when we had a vacuum incident that shut us down for the rest of the day.  That evening we determined that the first cryomodule and the cryounit would have to be warmed up to get rid of nitrogen gas frozen onto the cavities.  We are using the time while we get the cryomodule and cryounit temperature-cycled and pumped down to verify vacuum interlocking, establish proper field polarities in the arcs and wiggler trims, repair the shorted path length coil and finalize procedures for several activities.  We expect to restart commissioning on Wednesday next week. 
   Evenings this week were spent very profitably testing a new RF control system being developed at Cornell.  The tests were very successful and will be reported more fully in the RF section.

WBS 4 (Injector):

The gun continued to provide beam for FEL ops this week. We observe improved cathode lifetime. The present cathode QE is around 4%. 

Continued to polish the ball cathode and support tube electrode for the second gun assembly. 

Two successful implant runs have been completed on a test tube in the William and Mary's plasma-source ion-implant chamber. This test tube is being implanted with a field emission suppression coating. After completing three implant runs, the tube will be mounted and tested in the high voltage test stand (this is a small, dedicated chamber with a high voltage power supply capable of delivering up to 125 kV) at 25 MV/m (the highest gradient in the gun support tube is 12.5 mV/m at 500 kV operations). In this new implant mode and at this lower pressure (1 mtorr instead of 4 mtorr), the plasma barely enters into the sidearm.  Plasma entering the side arm used to cause instabilities that led to arcing when nucleation of SiO2 occurred at higher pressures. Thus, the coating doesn't extend as far onto the tube as the previous runs even though the tube is roughly at the same location in the chamber.  We estimate that the thickness of the coating is ~0.28 - 0.3 μm thick after 7 hours (according to the color chart).  Even though the coating is thinner, we were successful.  No arcs.  No SiON dust (a little ambient dust falls on the tube when the chamber is opened). The procedure is 3.5 hours in the plasma (no GDC since the floating potential is roughly 35V),  then 0.5 hours at 2.5-3 kV, followed by 3 hours at 5 kV.  

Carlos Hernandez chaired the "Materials, Fabrication and Integrations Group" at the High Average Power and High Brightness Beams Workshop organized by UCLA. The Workshop opened with plenary talks by R. Nguyen (USN), D. Sutter (DOE), D. Nguyen (LANL), J. Rosenzweig (UCLA), J. Lewellen (ANL), and S. Biedron (ANL) (http://home.physics.ucla.edu/calendar/conferences/powerworkshop/). 
Two other working groups focused on diagnostics and injector design/modeling.  D. Nguyen from Los Alamos summarized the status, projections and challenges of the three present technologies towards high average power injectors, DC+SRF booster (JLAB 10 kW Upgrade IR FEL Injector and JLAB+AES injector), Normal Conducting RF (Los Alamos) and SRF Guns (ELBE). The JLAB 10 kW Upgrade IR FEL Injector, being the only present technology to demonstrate high average current operation at 9 mA CW.  Issues at projected high average currents at the 100 mA level and beyond were also addressed during the Workshop like transverse halo control, measurement, and modeling, cathode heating by the drive laser at the 1 Amp average current regime, RF power handling, etc.  Major challenges like cathode R&D (new concepts, materials, robustness, QE, etc.), drive laser R&D (average power, time structure and pulse shaping), and thermal management (in RF guns) were also extensively discussed.

Gun HVPS - This equipment is ready for operations.

WBS 6 (RF):

RF - A vacuum event this week put dry nitrogen gas into the Quarter cryounit and the cryomodule FL02 and as a result they are not able to make any voltage gradient without a degassing to ~200K.  Vacuum interlocks and  a fastvalve downstream of the linac protected FL03 and FL04 from getting this gas also.  Additional fast valves are being ordered to better protect the Quarter and FL02 upstream of the linac.

The Quarter and FL02 are being warmed-up to 200K this weekend to remove the frozen nitrogen gas and they will be cooled back down to 4K on Monday and 2°K on Tuesday.  RF testing is scheduled for Wednesday.

Preliminary testing of a new low level RF system was done this week by Cornell and JLab.  The results were promising with this system able to turn-on and tune the cavity to a 12MV gradient in 8 ms.  Our existing low level RF system takes many minutes to establish full gradient.

WBS 8 (Instrumentation):

Progress continues on the Multi-pass BPM (MPBPM) configuration. Our initial testing last week showed us that we have one addition requirement in timing that was not addressed in the set-up. Although the 1 MHz signal is phase locked to the 37.425 MHz signal, it was still jumping around with respect to beam sync. To solve this problem, we have implemented another programmable timer card in IOCFEL03. Trying to implement all of the systems timing signals with just one card was good exercise, as we have designed them to do some pretty fancy tricks, and we have never really played with the card in this manner. It is clear now that we need one timer card to generate a 'beam-sync triggered' burst of 1.17MHz which is then delayed to match the BPM pulses. Implementing another timer card was straight-forward but took a few days to get everything right. Currently, we are cabling the system together. A software issue that was discovered during testing caused unneeded features.  This was repaired by Al Grippo and both sets of software controls were tested and verified.
    After having some difficulties with beam profile measurements produced by the WesCam, a bug was found in the software and easily fixed.  The results following the change provided users with the correct data they needed and scaled the calculations to mm according to the calibrations setup last week.  The Photocathode Gun Coulomb Archiver underwent changes in its EPICS channel access after creating a very slow memory leak on IOCFEL10.  The IOC has been monitored extensively and its memory resources have stabilized after the correction to the Coulomb Archiver.  The new Laser Personnel Safety System was demonstrated and is being fine tuned for testing to begin next week.  The logic for correct communication with the PLC user lab door locks is being tested.  The documentation/manual for the new LPSS is on-going.
    DEVLORE FLOG READER (http://laser.jlab.org) - In lieu of all of the recent activities, and the increase in use of the system by the whole group, we have identified some of the strengths and weaknesses of the configuration control database and what our daily needs are for a system like this. To this end, we are preparing an update to the system that will better present the daily difference between the current status and the ideal status of the machines configurations.
    The complete OPTICAL CAVITY system diagram is nearly complete. With the continued input from the optics team, we have completed a 'working' requirements document for all of the instrumentation and controls required to operate the optical cavity and optical transport systems that are not explicitly covered by any other major accelerator system (i.e. the vacuum system). This document mostly consists of the stepper motors, thermocouples, and water flow instrumentation as well as the various hooks into the beam viewer systems and the LPSS. Additional RTD's were also installed for the re-located upstream and downstream OCMMS Cross. 
    Assembly continued on the UV Beam viewer frames with the internal mirrors being assembled and mounted to the frames.   Certification of the LPSS Master was completed this week.  Progress continued on the new User Lab LPSS.  The first enclosure and PLC will be used as a test bed for programming and testing. The GPIB controls for the Analog Monitoring System (AMS)scopes have been implemented. Testing is in progress.

The floating GC power supply regulator design is now complete, the schematics are being updated and PCBs will be produced. An additional GC Magnet Control Chassis is being fabricated by the EES Group and should be in hand for testing early next week. Design drawings for the Beam Current Monitor upgraded circuit board went back to EECAD for final revision and new boards will be in house soon for populating and testing.  Testing continues on the Optical Mirror Heater Control Chassis.  This chassis should be available for installation early next week.  The 32:32 Video/AMS Crosspoint circuit boards, populated by FSI Systems, have been received and are being inspected and tested.  Assembly and Wiring diagrams for the AMS Chassis are being reviewed.  The Video chassis are very similar and assembly of the chassis for the video upgrade will be beginning very soon. 
    Additional training was held on the Lab's Electrical Safety Policy following the incident at SLAC.  This training further emphasized the procedures to use when testing electrical/electronic equipment and clarified some work definitions.  Posters have been made to be posted in areas where electrical/electronic testing is performed to serve as a ready reminder for technicians performing this function.  An additional portable tool/extension test cabinet has been received and is being installed.  Training will be held early next week on the use of this extremely helpful device.

WBS 9 (Beam Transport):

Sextupole (SF)

•	Procurement package is out to vendors for bid.

Replacement Chicane Dipoles GW)

•	Procurement package is out to vendors for bid.

UV Line

•	David Douglas issued the latest DIMAD for the UV Line. It is being laid out to check for interferences.

• We have identified 18 girders from the IR Demo that we can use for the UV Line. We have a modification drawing that converts the original QG quadrupole girder to the larger QX girder.

Variable Jaw Mechanism for the Permanent Magnet IR Wiggler (W55)

•	The Engineering Group is refining the reference drawings and a keep-out-zone drawing that will be part of the Specification for the procurement of the mechanism.

Operations

•	We discovered that the upper left coil of the four path length corrector coils (GG coils) built into the pole edges is internally shorted. At this writing, we are trying to remove the short without having to open up the magnet. It may take months to get another coil made. David Douglas says we may be able to use just the path length correctors of the first arc as a fall-back method of adjusting path length.

WBS 10 (Wiggler):

The specification for the variable gap permanent magnet wiggler was completed and sent to the potential vendor for comments and a cost estimate.  We are now awaiting comments from that vendor before placing the order.

WBS 11 (Optics):

2.8 and 1.06 micron mirrors: 
No changes since last week's report.  Procurement of the 1.06 micron mirrors is holding to schedule.  After the vacuum event described below, we used the alignment HeNe to check the OC mirror surfaces for dust and they appear to be fine.

Other activities:
   We spent the first part of the week readying for the LPSS certification in the OCR, and then we completed the OTS Lite configuration by installing the diagnostics mirror (a silver-plated Si mirror with a small hole in the center).  Pump down tests were scheduled when a vacuum event occurred.  Given the incomplete condition of the OTS, valves, ion pumps, and interlocks were not in proper states and we dumped the majority of the dry nitrogen atmosphere (~ 390 liters) into the accelerator.  A review of all vacuum interlocks on both the FEL and OTS systems is in progress. We have split the remaining time this week between checks of the OTS, review of procedures, and alignment of the matching optics into the optical diagnostics.  So far we continue to be pleased with the performance of the OTS as evidenced by the alignment HeNe.

Progress continues on the new optical diagnostics.  Parts were received to complete the fast scanning autocorrelator.  The LabView program for the PbSe array has been modified to make it more robust.  The program will run on a mini-ITX computer mounted under the optical table in the OCR.

The drive laser continues to be a workhorse (hope this doesn't jinx it) but our cavity length optimization routing needs an input from the autocorrelator to make this happen.  I&C is working on providing this.

We held a videoconference with our first off-site user group from Dahlgren and generated a list of action items.

Terahertz Project:

This week we hosted Oleg Chubar and the team developed code to calculate integrated power loading from 0.1 to 10 THz, and its distribution on a screen.  In addition we set up the code to work with beams of much lower energy, down to 1 MeV, so that we can investigate optimal transportable sources in the tens of watts range.