# MEMORANDUM

To:		Distribution

From:		F. Dylla

Subject:	FEL Upgrade Project Weekly Brief  - October 4-8, 2004

Date:		October 8, 2004

Highlights:

This week we hosted a major review of the Navy funded FEL program at Jefferson Lab on Wednesday and Thursday.
   The review topics included a summary of the 10 kW campaign and the planned three year program for the Navy (FY05-07) for performance testing and operation of the 10 kW FEL and development of key hardware for 100 kW FELs. 
   We were pleased that all but one of our external review panel members could attend the review, in addition to our program officers from ONR and NAVSEA.  We would like to take this opportunity to thank our review panel members who have devoted considerable time and effort to advising us on the design, fabrication and commissioning of the 10 kW Upgrade over the past four years since the project was initiated in June 2000. 
   Despite all the activities of this review week, installation and check-out activities continued at a high level as we near the end of this shut-down period. 
   Highlights of the week's accomplishments include:

- installation of the new short wavelength (1-3 micron) electromagnetic wiggler 
 	- successful hot check-out of all the RF systems for both the injector and linac

- successful heat clean ,cesiation, and HV conditioning of the photogun

- continued progress on the installation of the optical transport system

Management:

We completed preparations for, made presentations at, and survived the drama of our third Navy panel review in the last 9 months. 
Five white paper proposals were submitted to the JTO for FEL technology development on Monday.   We are also collaborating on a couple of proposals by other institutions.
The project monthly report for August for the Army funded THz project was submitted to the DOE and Army program offices.  The project monthly financial report for September was prepared for ONR.

WBS 4 (Injector):

The DC Photocathode gun is ready to provide beam for FEL ops. The anodized GaAs wafer was heat cleaned on Monday. On Tuesday we made a cathode with 6.5% QE. On Thursday we performed cathode high voltage conditioning successfully. No evidence of field emission from the cathode was observed.

This is the second cathode we made on the anodized wafer installed under vacuum back on May of this year. The first cathode delivered 940 Coulombs of charge with 6 re-cesiations. We expect longer lifetime for this second cathode after fixing a very hard to detect leak in the gun gate valve flange.

Gun HVPS - Is operational with some drift observed in the current readings.  The Conditioning Resistor was cleaned again without much change in the current drift.  The electronic boards will be cleaned next week to try to improve the drift.

WBS 6 (RF)

RF - Hot checkout of all RF systems continued this week.  Several small problems have been found and corrected.  The Quarter was RF processed to Drive High gradients.  Window and waveguide "washing" was performed for several hours to improve the vacuum and load handling capabilities.  This process will continue next week also to improve all zones.

WBS 8 (Instrumentation):

The new valves for the 0G diagnostics development station and the additional 4F valve to aid in optics work were connected and tested through the control system to the Machine Protection System. There is still more work to be done but the connections that prevent burning large holes in things has been done. Test fixtures to readily test these were also built. 
   Continued work on the beam viewer system.  An additional control box was built for VBV3F00 to aid in beam viewer alignment for the 3F region viewers   Much time was spent in the 0F, 1F, 2F region in final focusing and aligning viewer cameras and repairing air lines due to other installations. The cameras in the 1G Dump have been exchanged for new ones, and those viewers have also been re-aligned.   Final alignment of 3F06, 3F07, 3F09 and 3F04 will commence next week. Additional camera lenses have been ordered. 
   Both Arc string 165 kW box supplies along with the Injection, Extraction 5kW string box supplies were powered on earlier in the week to begin shake out.  A punch list is being complied as we started to turn on the magnetic transport system. The Injector (FL05B13) trim rack was also powered up and debugged successfully in order to support the Gun group. 
   Considerable progress was made on the new LPSS.  The vendor spent a couple of days here assisting us in configuring the new LPSS Master LC CPU, Ethernet and Control Bus modules. Connection to the additional safety viewer will be made next week. The new IClass card readers are here and work continues in converting the data base to work with the new system. The tentative date for LPSS certification is Oct. 21.

WBS 9 (Beam Transport):

## W80 Wiggler

• 	We use two probes to get a complete characterization of the wiggler. One of the probes had developed a 12 Gauss offset, spoiling our proof runs. We calibrated the offset, subtracted it from the data and were able to continue with all six proof runs. Steve certified the wiggler for use. It was installed Wednesday.

Installing the EM Wiggler and Decompression Chicane to Reduce Downstream THz

•    The wiggler and its chamber was installed and aligned

• 	We started the process of taking the “tops” off the 4 GW dipoles in the chicane in order to install the chamber.

• 	The Vacuum Group leak checked the chamber and we installed the Synchrotron Light Port and its internal mirror, which will provide a check on the position of the beam when setting the strength of the chicane. The chamber will be baked over the weekend.

•	Installation of low conductivity water piping was completed.

Sextupole (SF)

•   The requisition was generated for signature, the specification/statement of work was signed and the final numbers were put on all the drawings.

UV Branch Line

•	The specifications for ordering the replacement GW Dipoles remain in checking.

WBS 11 (Optics):

Progress occurred in the following areas:
Cryomirror:
We did a verification of the LN2 flow rate with the setup we've been using.  The flow rate over 23 min was just over 1 L/min.  The dewars, subcoolers, cryolines and mirror were removed in preparation for the installation of the 2.8 micron mirrors next week.

2.8 and 1.06 micron mirrors: 
 We've received our 2.8 micron mirrors.  We are rapidly putting them through our metrology checks.  So far, so good.  We received a quote from a vendor of known low-loss coatings and are proceeding with the procurement.
Scraper outcoupler: 
No news since the last report.  
Other activities:
Optical power meter readouts we no longer need downstairs were removed from that region.  The turning mirror cans to the OCR have been mechanically aligned.  We received our turning mirrors (minus the one with the hole in it) and they are going through metrology.  Mounting them to the cooling plates starts next week.  The collimator lite has been mechanically assembled.  The stand for it arrived and we will install it early next week.  Shield covers for the optical components have been fabricated.  Progress continues on the OBPM system, and on a fast scanning autocorrelator.

Terahertz Project:

This week we assembled one of the safety shutter/viewer assemblies.  We received the re-polished mirrors (M2, M3 and M4) back from the vendor. We received the conditioning mirror vacuum chamber and 2 of the 5 polarizing grids.  Work commenced on assembling the beamline components in Lab 3.