MEMORANDUM

To:		Distribution

From:		F. Dylla

Subject:	FEL Upgrade Project Weekly Brief – February 14-18, 2005

Date:		February 18, 2005

Highlights:

Effort this week concentrated in two major areas:  installing high power 1 micron and broadband mirrors and recovering operation of the middle cryomodule by warming it to room temperature.  A leak was found in a rf window braze on cavity 4.  It is impractical to replace it in situ so we are taking that cavity off-line for now and will raise the gradient in the other cavities to compensate. We are cooling the module back down today and plan on re-establishing rf operation over the holiday weekend.

We have placed with STI the purchase requisition for the gap mechanism for the PM wiggler.

We also put the PR in the system for 80 kW IOTs to power the AES cryounit in the injector test stand.  An advance copy of the spec is already on the street.

Management:

ONR has signed and delivered to DoE the 3-year MOA for JLab operations and maintenance activities.

We have received the signed MIPR THz contract from the Army NVL and are in the process of completing the Work for Others subcontract with AES for their activity.

We released the January monthly JTO reports.

WBS 3 Beam Physics (David Douglas):

Absent actual electrons, we contemplated the problem of recovering a high current beam in a small space for the next version FEL. Several notions floated up [deranged ravings qualified by square brackets]:

1.	It is likely that a high-power driver's footprint will be defined by optical cavity and accelerator, not transport system. This is because a) you can't make the machine shorter than the linac, and b) if the optical cavity is not much longer than the linac, and you have to get the electron beam into and out of the optical cavity, it'll take a additional little space to do that as well.

2. As working parameters [we asked some people that will remain nameless but have actually built this kind of stuff, gotten it to work to spec, and therefore qualify in our sick little mind as reliable sources], we have adopted a linac length of 11 m and an optical cavity length of 16 m. With these numbers, there's really not space to bring the beam around from the linac to a symmetrically located optical cavity without embedding the cavity in a much longer transport system (as in the IR Demo or the IR Upgrade, as opposed to embedding the transport system within the cavity footprint, as in the UV upgrade).

3. You need to bend RIGHT after the wiggler. Or, as a novel alternative technology, you can splatter THz radiation all over the downstream end of the optical cavity if you want, but you'll be really unhappy in that case. So plan on bending RIGHT after the wiggler.

4. This suggests the machine might best be [oh no, I've been absorbed by the south! I see kudzu everywhere...] asymmetric, with the energy recovery transport starting with a right stout deflection [more kudzu] IMMEDIATELY after the wiggler so as to direct the THz away from the downstream mirror from as far away as possible (but, after all, you can't get farther away than the wiggler, at least not without a negative length drift).

5. After an extensive study [consisting of an evening with the laptop while watching CSI reruns and killing a bottle of Chateau St. Jean chardonnay (hey, it’s the south. It was that or Jack Daniels. We make do. If you want me to drink better wine, get me a job someplace that makes better wine or at least imports better wine...)], we have concluded that a viable energy recovery solution might be derived  through use of a THz deflection chicane followed by a simple mirror bend. As the mirror bend compaction is completely linear, the RF curvature correction is imposed by the chicane T_566; the mirror radii are then selected to compensate the M_56. By juggling the various free parameters of chicane angle, spacing, and bend radii (chicane and mirror), you seem to be able to get to a place in parameter space with appropriate longitudinal properties (at least to second order, which may be enough at 750 MHz) and transverse properties that are not totally untoward.

6. We have djinned up a notional design based on this concept. It is quite compact (figure 1). The business end of the optical cavity would hang past the end of the machine by 4 m or more (for our assumed 16 m cavity), and there'd likely be space back upstream to do all sorts of matching, reflecting, rotating, and avoiding of other ends of the optical cavity. By playing with the chicane radii, angle, and spacing, we controlled the T566 and the focusing properties. By playing with the mirror bend radii, we control the M56 in a parametric region with rational transverse behavior. By messing with chicane and mirror external pole faces (ones at dispersion free points) we fine-tune the betatron behavior through the system  [okay, okay, theres a skinny little quad between the chicane and the mirror. I thought I had gotten it out of there, but turns out I left in a bit of it. I'm working on it. So sue me]. The final edge of the last dipole and a quad triplet are used to match to reinjection envelopes appropriate for energy recovery  through a 100 MeV/750 MHz accelerator. Figure 2 shows the beam envelopes; they're not wild. The chromatic behavior is most charitably characterized as "maybe not fatal" but needs some work, though if you believe the hole is big in the linac it might fit...

7. Machines of this ilk are NOT going to be very flexible. So, if some real bright FEL weenie decides - "oh, gee, this other Rayleigh range with attendant different betatron match looks waaaayyyyy better and by the way I wanna use this other wiggler" half way through construction - TOO BAD. You get what you get, and if you build it right, you might even get it. But you're not going to be able to change it once you start cutting metal, and you need to know pretty much what it’s going to be before you start doing the transport system design. So speak now, or forever hold your peace. And plan on building the dipoles with pole faces you can machine after the fact. Because you'll want to.

On the topic of general studies of the IR and UV machines: Max and Kevin have made considerable progress on the Elegant model of the IR system. Once this is running, we'll merge the UV into it and start examining the modeled performance of both sides of the machine.

WBS 4 (Injector):

It has been exactly two months without the need to re-cesiate the cathode since it was made back in December 17, 2004. This cathode has delivered over 425 Coulombs at

135 pC/bunch (at least) of CW (typically 5-6 mA) and pulse beam for FEL ops since then. The previous cathode also lasted two months without a re-cesiation, but delivered only around 50 Coulombs. I remind our readers that a new cathode is made without need to break vacuum (a new cathode is made on the same GaAs wafer each time by heating the wafer in vacuum, removing the old Cs layer, and depositing a new one). 
   A flat electrode coated in the W&M's plasma chamber has been coated and mounted in our high voltage test stand (125 kV) for testing. The high voltage test stand chamber is being baked. The electrode will be tested under voltage next week. 
   The drawings for the new-concept segmented tube that supports the ball cathode on the second gun assembly have been signed-off. It was decided to cut the ball cathode support tube in three sections to eliminate arcing during the plasma-deposition of the field emission suppression coating. The original one-piece tube (about 34inches long) suffered unipolar arcing in the transition region from plasma to vacuum during the processing. By cutting the tube, each piece will fit entirely inside the plasma. 
   The ball cathode for our second gun assembly is being mounted today in the W&M's plasma chamber. The ball will be coated in two 8 hr-long runs (bottom first, then top) next week. 
   PARMELA modeling of the UV injector (operating at 7 MeV) for 67 pC/bunch is in progress.

Gun HVPS - is fully operational.  The specification for an upgraded Gun HVPS has been written, reviewed by prospective vendors and is awaiting funding.

WBS 5 (SRF):

- AES is planning to ship the completed 750 MHz cavities at the end of this week.  They are expected to arrive at JLab by the middle next week.  QA will be the first priority.

- End can fabrication continues.

- AES/JLab coordination meeting is expected to be held in March.

- A meeting is scheduled to clarify operational parameters for CASA analysis.

- Plans have started regarding a project status presentation at the May FEL Conference/Workshop.

WBS 6 (RF):

RF - A small leak was found around the window of FL03 cavity 4.  This cavity's window was sealed with a gasket and a blanked off flange.  The cryomodule's capability is thus reduced by 10.5 MeV.  The plan is to cool FL03 this afternoon and pump it down to 2 K this evening.  It will be tuned this weekend and ready for start-up operations on Monday.

The RFP to purchase two 80 kW IOT's and their HVPS for a new Injector Test Stand was released and is "on the street."   Advanced copies of the technical specifications were made available and are in the hands of many prospective vendors.  The RFP has a

6 month option to purchase the required 3rd IOT & HVPS when additional funds are available.

WBS 8 (Instrumentation):

The I&C group again took advantage of the down period to perform some minor maintenance activities. Realignment, replacement of lenses and lamp rings took place in the 3F and 5F region along with adjustment of the image quality on ITV1G01 in order to make it useful for the beam operations crew. Control Room Operator patch panel FL07B2 was replaced with a panel located under the workstation as part of the control room upgrades. Cables have been rerouted and new cable hangers installed to reduce the clutter on the floor.  This is the first station to be modified.  The other stations will be modified when the new monitors are installed.  A new patch panel was added in FL07B09 for the AMS upgrade cables. There was a small leak at the 1G dump, we coated the ceramic with Vacseal and the pressure recovered an order of magnitude in couple hours, this is the second time. We plan to replace the ceramic during the next down (~April). Since the steel shielding was removed we re-terminated and recalibrated the Dump Current monitor. We raised the external termination resistor from 33 ohms to

100 ohms to see if that changes the discrepancy between the dump current and the high voltage power supply at the higher currents. 
   With being down we are addressing UV installation and operational issues as well as being involved in a number of maintenance and repair items. The major source of tune time for this machine has been the irreproducibility of the magnetic fields in the quadrupoles. Operation of the UV leg will make this problem even worse. Each of the quads are mapped in the magnet test area and these field maps are entered into the magnet control software, the problem is that the trim power supplies that we use are not capable of making the hysteresis loop (not enough volts), multiple proposals have been floated including to JTO but all have been denied. We have decided on a plan to quantify the discrepancies and to look for systematic affects that might be compensated for. This work will go on for the next few weeks in magnet test, thanks to Tommy, Ken and the gang for trying to fit this extra work into their tight schedule! 
   The software focus this week was put into the epics-to-devlore project. The system is being tested and will perform a test run over the weekend.  The software will be submitting several EPICS records from the control system to the web server to be recorded.  The trigger for submitting data is time-based (e.g. once a minute) and/or event-based (e.g. button press).  We continue to support Carlos on the calibration of viewers ITV0F06 and SLM2F08.  The calibration is based on the change in position with respect to the change in the energy spread.  Visit: http://laser.jlab.org/status to see in real-time what the status of the machine is. We have slapped together a quick page to 'show-off' the incoming data stream from EPICS. The presentation of the page is undeniably crude at the moment, but it does provide the latest operational numbers for our voyeuristic fanbase.  :-)   We have included the Gun voltage to be used to 'qualify' most of the other values. When the gun is off, the other numbers are not meaningful. These are the EPICS values we are currently archiving: 
       Injector gun voltage (kV), 
       eBeam current at the 1G Dump(mA), 
       eBeam Micropulse Frequency (MHz), 
       eBeam Energy (MeV), 
       eBeam Charge/Bunch (pC/), 
       FEL Duty Factor (%), 
       FEL Power (W), 
       FEL wavelength (microns) 
   The next values that we will be archiving will be all RF phases and gradients, quad, sextupole & octupole fields. The page will improve as time permits, but the important thing now is that we are archiving the data. <http://laser.jlab.org/devlore/devlore.asp?List=UV> 
   The MPS was updated to include the logic for Laser Alignment Mode. Somehow this had been forgotten, when we did the lab certification last week, it was just not there... Extra care was taken to ensure the fail-safe implementation of the system. We are now testing the inputs to be sure they respond correctly, but the MPS logic is tested and ready. The MPS Summation Chassis located in the Control Room was modified to increase the channel capacity from 12 to 24 channels.  The sketches of the modifications were submitted to EECAD for proper documentation records.  The drawings are currently being reviewed for accuracy.  Four more signals were connected to the MPS Summation Chassis to provide status and protection for the Lab Optical Transport System.  We now have MPS status for "Laser Permit", "Alignment Mode Key", "Lab Lockout Key", and "Lab 1 Harmonic Filter".  All of the cables for the current signals have been installed, labeled, and terminated. 
   Installation effort continued on the new DC power rack (to support full sex IR & UV) in FL07.  The 480 volt, 300 Amp breaker box and 20 Amp plugs and receptacles have been received.  The electricians will begin installation as soon as work winds down on the main machine. The extruded aluminum parts were delivered from the machine shop for the Lab 3 THz hutch and fabrication continues. Check prints of the OC Fail-safe Solenoid Interlock were received from EECAD, revised and re-submitted along with the FEL High Power Dump Multiplexer Box. 
   The RF-DC Linear Converter PCBs are making progress.  The documentation has been completed, the order for the PCB manufacturing has been sent out, and completed PCBs should be received middle of next week.  The check prints of the modifications to the Charge Totalizer PCB are under review as part of the Charge/Dump Current Monitor Chassis upgrade.  The CAN BUS test cable used on the Charge/Dump Current Monitor Chassis was replaced with the proper final installation cable. 
   All of the elements shown on the latest mechanical drawing of the UV line have been added to the database. The Devlore interface to the controls database is sufficiently power enough to generate component lists of any level of complexity for one who is savvy in using it, but for the convenience of all, we are preparing a set of custom element listings that can access by a simple link that can be bookmarked. Our first custom list link is for the UV line. Use the following link to directly list the beamline elements of the 6F, 7F, 8F and 2V regions: http://laser.jlab.org/devlore/devlore.asp?List=UV

WBS 9 (Beam Transport):

Sextupole (SF)

•   Fabrication is continuing at New England Techni-Coil. Conductor is being sent for insulation coating. Steel has arrived at NETC and is being prepared for machining into the blocks that reform into the cores.

Replacement Chicane Dipoles GW)

•     Fabrication is continuing at New England Techni-Coil. Unfortunately, a snowstorm cancelled the weekend’s only (because of long cool down) heat treatment. The steel for two of the four magnets will be heat-treated this weekend in anticipation of finish machining start next week. The first coil layer was complete. They are working on clamp bars that hold down the windings during the remainder of the windings.

UV Line

•   The latest changes were verified and the layout was broken into the sub regions and distributed to two other designers for detailed layout to expand the effort to three designers.

• 	Design of the three-inch differential Pump Station was complete and is ready for signature.

• 	We are holding a review of the goals and proposed solutions of the UV vacuum next Tuesday.

• 	Contrary to our account last week, the Vacuum Ion Pumps were not ordered; the requisition was stuck in a paper pile in Procurement – a rare event.

• 	With regard to our plan to regain our schedule slip, the ME Group is working its plan to concentrate a number of designers on getting the beam line designed.

•	We are reviewing a number of resumes with respect to our initiative to have a NASA design engineer spend a sabbatical at Jlab.

•	DULY Research has magnetically modeled the original sextupole to benchmark their code before they convert the model of the SC sextupole to the SS sextupole. They achieved the same field strength as was measured on the SC Sextupoles.

• 	The faster PC workstations are late by 2 weeks because the requisition got stuck between signature and Procurement.

• 	Tim Whitlatch’s vacuum analysis is taking a back seat to dealing with CEBAF problems during the 3 week CEBAF down period.

• 	The procurement to send the dipole chicane stands and vacuum chamber to an outside firm for design is out for bid.

•   Design of the upstream and downstream corner chambers (now being done as a pair) is almost complete. We solved restraint and downstream beam line space issues.

•  	DD requires QX Quads in the UV Line to meet specification of “part in 10^4” repeatability and “part in 10^3” setting accuracy. The original Trim Card I‘s don’t meet this specification using Bang- Bang ramp because it can’t supply the required voltage and control uncertainty leads to variable overshoot and ring. The new Trim Card II’s (which will be used in the new UV, 32 card Trim Rack) can have internal programmed hysteresis loop. We can cycle the quads with a precise ramp. We will measure one quad under differing ramp conditions to find out if we can reach David’s specifications. (All quads may need re-testing with programmed ramp rather than “Bang- Bang ramp”).

Injector Multi-slit upgrade

•	The fine slot paddle parts were checked for slot width and spacing and sent for UHV cleaning.

UV Wiggler Progress

•   The stay-out zone drawing was almost complete and awaits a final decision on the vacuum chamber and gap configuration before signature. We received the drawings of the Argonne wiggler chamber styles and will conference call to them this afternoon to firm up how to match our needs to their available designs and extrusions.

WBS 10 (Wiggler):

The order for the IR Upgrade permanent magnet wiggler gap mechanism was placed this week with STI Optronics.  We are working to schedule the kickoff review and shipment of the permanent magnet wiggler jaws to them. 
   We continue to refine the vacuum chamber concept for the UV wiggler vacuum chamber in consultation with an engineer from Argonne National Lab.  We would like to use as much of their design as reasonable in our chamber design.  We are looking at the possibility of using a slightly larger chamber to make production easier.  This would limit operation at higher energies than we can now achieve but we may have a new wiggler by the time we get higher energy so this may be a moot point.

WBS 11 (Optics):

2.8 and 1.06 micron mirrors:

Given our current emphasis on 1.06 microns and lower power tunable operation elsewhere, we removed the 2.8 micron HRs and replaced them with a spare broadband and 2 inch dia 1.06 micron HRs.  We also removed the broadband outcoupler and remelted its braze to try to correct the astigmatism.  The result was that the axis of the astigmatism rotated about 60 degrees, but remained about the same in magnitude.  A spare mirror was installed with silver-doped vacuum grease used for thermal conduction.  With these changes we'll be able to better explore the relationship between astigmatism and lasing efficiency that was briefly discussed in last week's report.  Later we will replace the pasted versions with regular DMAs.

Other activities:
Late Friday we completed the low level certification of User Lab 1.  We did not have the opportunity to actually run beam into the lab, but hope to this coming week.  We've set up beam diagnostics hardware on the optical table in anticipation of characterizing the FEL.  We spent this week performing a series of tasks: installing cavity mirrors, upgraded OCMMS, upgrades to the hot nitrogen purge system, and a more permanent mount for the power meter that intercepts light directed to the diagnostics hutch located in the vault.  (Thanks to the Vacuum and Survey and Alignment Groups for their help.)  We repaired the exterior cable that connects the HR LVDTs to the Control Room.  We also fixed one of our windowed gate valves downstream of the OC assembly, and did some troubleshooting on the other one.  We also installed more ion pumps on the OTS, two in the vault and one upstairs.  We plan to install another in the OCR early next week, or when time frees up.  This will free up our pump carts for their primary purpose.  We fabricated holders that will accept GaAs wafers (for harmonic filters needed during alignment mode operation) and tested one of the IR Demo insertable mirror assemblies to check its leak rate.  We found that it doesn't leak, but bursts gas when actuated.  We'll see if that can be tolerated by the ion pumps in the OTS.  New optical transport systems were designed for transport of light from the 180 deg dipoles to the streak camera, and planning for installation has started.  We tried boosting the SHG power of the drive laser by installing a longer LBO crystal, but found the conversion was much less.  We have contacted the vendor to discuss this with them.

## UV FEL

The cryomirror modeling group met and finalized the baseline model, with follow on work to extend power handling capabilities.  We began researching options for in situ plasma discharge cleaning of the mirrors.  We held some meetings to resolve the very cramped area between the dipole magnet and the OC assembly.

Terahertz:

Planning work was done for the phase 2 part of the project.  Discussions continued with vendors concerning laboratory equipment, particularly spectrometers and detectors.

# Text boxes

Figure 2: Beam envelopes

Figure 1: Footprint of compact design.

Figure 3: Momentum scan. Needs work, [but I've seen worse after just one bottle

of wine].