# MEMORANDUM

To:		Distribution

From:		F. Dylla

Subject:	FEL Upgrade Project Weekly Brief  - November 14 - 18, 2005

Date:		November 18, 2005

Highlights:

This was a good week for the FEL Upgrade. The hard and careful work by the FEL staff and our JLab collaborators during this shut-down period is beginning to pay-off. As of this writing the SRF commissioning team headed by Mike Drury and Tom Powers is completing the re-commissioning of the 3rd cryomodule after its vacuum cycle and window replacement. As noted in the WBS 6 (RF) report below, the FEL 3 module is capable of delivering at least 46 MV. The entire linac (the injector cryounit) and the three linac cryomodules have now been re-commissioned. The linac should be capable of producing 125MV of acceleration (on crest) and 123MV at our usual acceleration conditions (10^o off crest). This should give us some head room for our planned 10 kW operation with the new wiggler which needs 115MV.

Other accomplishments include:

-check-out (by direct in-situ measurement) of all of our QX quadrupoles; they are settable within a range of ± 2.5 parts per 1000.

-check-out of all the vacuum interlocks

-check-out of 90% of the SRF interlocks

-the dump ceramic was replaced, electronics re-installed and shielding replaced

In addition, some operational time was put on the clock this week with continued injector set-up and analysis of our first signals from our new Beam Position Monitors (BPM)

We received notice of award for two JTO proposals having to do with high power optics design.

See the report under WBS 11 (Optics) for details.

Next week is a short week due the Thanksgiving break. In the first part of the week we will continue injector set-up, put additional run-time on the rf systems and continue the check-out of diagnostic systems.

There will no weekly report next week. We wish all of our readers and collaborators a healthy Thanksgiving dinner with friends and family.

Management:

Several members of the FEL team (Neil, Rode, and Jordan) attended this week’s DEPS symposium and reported on our developments with our photogun and FEL optics.

The ONR project financial report for October was completed and forwarded to the DOE and ONR program offices.

On Thursday we were visited by the CEO and Technical VP of the National Electrical Manufacturers Association to discuss technology transfer issues.

Gwyn Williams gave an invited talk at Teratech 2005 in Osaka Japan, and represented the USA in a joint USA/Japan/EU THz Network meeting.

WBS 3.0 (Beam Physics)

Continued flogging the MADMAN program. Cooked up machine recovery metaprocedure, which, with update of injector procedure and high current recovery procedure describes a path back to 10 kW.

WBS 4 (Injector):

Injector and DC Photocathode gun are both operational. PARMELA modeling of the injector continued this week.

WBS 5 (SRF):

100 mA 750 MHz FEL Injector Cryounit Progress

- The third harmonic cavity is assembled into a test stand and ready for VTA testing.  The testing of the cavity is scheduled for next week after the completion of our current VTA shutdown for scheduled maintenance.

- Cavity helium vessels are scheduled to be delivered to AES this week for QC/QA inspections.  Shipment to JLab is expected the last week of November.  A fundamental cavity will go back into the VTA next week in order to verify the warm-to-cold frequency shift. This information is needed to specify the warm tuning of the cavity prior to helium vessel welding.

- A confidential disclosure agreement is being put into place between JLab and the fundamental power coupler vendor in order to facilitate the exchange of information needed to properly inspect and process the FPC’s next month.

- The hardware for the bench top warm tuning modification is due in next week and will be installed and test fit with a cavity for functionality.  Engineering design continues on the remaining tooling modifications.

- In light of the Renascence HOM issues, we should revisit the plans for the 100mA HOM feed through and the coax cable thermal anchoring design.

WBS 6 (RF):

Commissioning effort on zone FEL3 took place this week.  We determined the maximum gradients and did a one hour run at this gradient.  By noon Friday we were testing the last cavity.  The cryomodule looks like it can produce about 46 MV of accelerating gradient on crest.  During the test the field probe calibrations were determined based on the values imbedded in the control system.  There seems to be a mismatch between the forward power and the accelerating and the loaded-Q on cavities 4 and 6.  Assuming that the field probe calibration in the control system is correct these two cavities could only produce about 4 MV/m each.  We will be spending Friday afternoon and early evening recalibrating the gradient on these two cavities.  Assuming the 8th cavity has a reasonable Qo value at high gradient it is expected that the zone will produce less than 200 W of RF heat load at maximum gradient.  This should be sufficiently low for operations.

We validated 90% of the cryomodule interlocks.  This includes the vacuum interlocks and all of the arc detector interlocks.  We have tested about half of the window temperature sensors.  The testing included functional tests, which also validated the cabling and controls interface for each channel.  Zones 2 and 4 were operated and the relative maximum gradients were determined.  We are investigating some minor hardware changes that will allow us to better optimize the control loops.  It looks like the on crest machine energy is about 125 MV (Possibly greater depending on the calibration issues relating to cavities FEL3-4 and 6).

Two potential cavity “interlock” problems were identified.  The first is that failure of an auto test of the arc detector system does not inhibit the operation of a cavity.  I have requested that the software group implement a change such that failure of an arc detector test will trip the cavity off and provide an indication on the operations screens.  The second is not a fault but still not a desired condition.  Typically when a cryomodule is turned on for the first time after a few days of being off, one or more of the cavities is detuned sufficiently that the cavity does not produce gradient.  On the cavities with better window vacuum or no window vacuum space, such as our new style cryomodules, the control loop tries to drive the cavity harder until the klystron is at it’s maximum power and there are no faults.  While this does not cause an immediate problem and windows are tested at twice the power capabilities of the installed klystrons, it is not a desirable operating point.  Until a software control algorithm can be developed, operators have been advised to watch for this condition and take appropriate action such at the cavity does not remain in this state for more than a few minutes.

Problems fixed during the week.

Buncher klystron water flow problem.

Arc detector on FEL3-2 failed and replaced.

SRF commissioning software improved.

Problems needing attention.

Two software changes for LLRF to address off normal conditions.

LLRF in zone 3 cavity 8 needs attention.

WBS 8 (Instrumentation):

Hot Check-out and System Readiness for the restart of regular beam operations has been our primary focus this week. Since we locked the machine up early each day, please note that all of the vault activity took place each day before 9:00. A special thanks to everyone who came in extra-early to make this week as productive as it has been.

** RF Instrumentation --- To support the commissioning of the Zone 3 cryomodule the RF interlocks for the cold cathode gauges were all installed.  The cold cathode gauges provide the Wave Guide Vacuum interlocks for the zone, since there are no wave guide vacuum interlocks on the zone.  The analog readbacks for the gauges have been patched into EPICS.  The logarithmic scaled output has been converted back to a linear scale so the ADC can give the accurate vacuum reading.

** Beam Current Diagnostics --- The 1G03 Dump Electronics have been installed at the 1G03 dump.  The new electronics have been calibrated through EPICS and verified that the scale of 1mA = 1V is consistent throughout the input range.  The shielding blocks for the dump have been reinstalled and the steel shielding will go in as soon as time in the vault is available.  The new User Beam Current Monitor electronics have been installed and the necessary cables installed.  Once the beam line hardware is installed the connections will be made and the readout should be available in EPICS with the other dump and BCM signals.

** Vacuum System "Hot Check-out" --- Every ion pump has been tested as well as well as all of the Convectron gauges. We verified that the vacuum system channel designation is truly the hardware being controlled. The channel connections are correct to the Vacuum System Crates in FL05. A few problems have been discovered in the vacuum crate.  VIP1V00F readback is just noise, VIP5F00 interlocks (in the vacuum crate) are not operating and have failed-safe. Once these issues are resolved, the vacuum system will be ready for operations.

** "NEW" BPM Electronics --- One of the new BPM Electronics was installed in the 0F region in order to take some data with the FEL injector beam.  This set of electronics has the updated code that uses the sPline interpolation.  Data will be taken as soon as injector operations begin today to get a feel for exactly how our system will behave.  Firmware files for the next revision of the board are being developed.  The board, brackets, and wiring have all been installed for the sextuple reversing switch.  The enclosure wiring will be documented so all switches will be consistent. --- Also, The subrecord for sPline interpolation is programmed. The subrecord would call the function to initialize the sPline interpolation by using the data from calibration, and then it would call the Splint function to do the real-time calculation to obtain the beam X, Y position. A new application code and database were made and installed in a ColdFire BPM. The new BPM is running on FEL. We checked the result, and it matched with the calibration curve.

** Magnet Power Progress --- Another schematic has been submitted for a check print for the revisions on the GC power supply boards.  The GC power supply has been inserted into EPICS controls and is functioning properly.  A new print should be approved by next week, and work on fabrication of new boards should commence shortly. Also, we are populating 10 of the 6kW Reversing Switch circuit boards. We have assembled a new Charge/Dump Current Monitor Buffer Driver Box and we are setting up a test fixture for the Video/Crosspoint circuit boards for trouble shooting.

** Wiggler Controls --- The ethernet communication to the wiggler has been problematic and we've spent a lot of time troubleshooting that. The serial communication seems to be fine. The issue was resolved just today.

** Emittance Monitoring --- Video interlacing is distorting the horizontal multislit measurements. Interpolating the image works well for normal beam, but is failing for the small beamlets.  We are working through this during beam operations.

** Miscellaneous Activities --- The Happek (Interferometer) was aligned with help from the optics team (Thanks Joe!). The Fresnel lens and insertion track were secured in place and aligned. We still need to connect the air to the Happek stage and connect the control line to the control system upstairs. --- The viewers in the vault have all been basically hooked up and just need a little aligning here and there.  Currently, each viewer is at least hooked in and 95% aligned. --- Cable was also run for the wiggler control box from the control room in order to provide basic control over the box so programming and controlling can begin in EPICS. --- The lab 2 cables for the LPSS system have also been moved/run. The shutter lockout box cables have been run from the LPSS box to the other side of the lab and excess cable is in place for placement of the lockout box. The other cables for the CAN and Mirror cassette have also been rerun to the new location of the can. --- Support for the completion of the optical beamline in the back of the labs was begun also. Cables were run for the Ion pumps and Convectron Gauges in labs 5 and 3a. Beamline valve cables were also run for the valves in labs 5 and 3. The cables for the Ion Pumps and Convectron Gauges have been appropriately dressed in with black flex.

Lastly, a "System Readiness" page at: http://laser.jlab.org has been set-up to provide a definitive list of the various systems of the FEL.  It will take a few weeks to get the list filled out completely and to have the information listed correctly. But this page will be referred to regularly from now on.

- rich (on behalf of the I&C group)

View "fel_ctrls" archive at:

http://www.jlab.org/ccc/mail_archives/ACCELERATOR/fel_ctrls/CURRENT/

# WBS 9 (Beam Transport):

# Sextupole (SF)

•	Over the next week the magnet test stand will be off the project, devoted to a 12 GeV dipole magnet test.

•	We mechanically measured the #11, the magnet that was giving us sideways fields.  Results show that it doesn’t have any gross mechanical errors.  This convinces us that we may be looking for very subtle causes of our out-of-specification readings.  There may be some probe in the right position problems.

•	Basically the quadrupole term went away at the high and low currents and remained at intermediate currents after we tightened the bolts.  This may indicate non uniform residual fields are the cause.  In our proposed tests the week after next, we will try splitting the operating range into two or three zones with lower maximum hysteresis cycle currents for the lower ranges.  This technique worked on the GX dipoles. We also plan a series of magnet measurements to assess the sensitivity of various pole movements and field clamp movements to field quality.

Replacement Chicane Dipoles (GW)

•	The remaining two units in at Magnet Test, awaiting the testing of Sextupoles before the GWs get measured.

QX Quadrupole Measurement

•	The folks at Argonne APS had a similar problem measuring their quadrupoles, They get relative strengths of parts in 10,000 on a rotating coil stand but can only get absolute strength at the parts in 1000 level.  We will not be using their facilities.

•	With this finding (that according to Tommy Hiatt is echoed by the measurement folks at other labs) David Douglas writes: “Methinks a rethink of philosophy is in order.  I suspect that we should map a standard and a few references as well as possible, and then characterize the whole lot relative to the standard and scale on the machine.”

# UV Line

•	Meanwhile, quads are not tested and girder assembly remains on hold until UV funding is secured

•	The NEG Pump cartridge holder design for the second corner UV chamber is also on hold.

# UV Wiggler Progress

•     	No progress on the new Wiggler vacuum chamber.

# IR Machine Quadrupole Operations

•     	Lots of folks did a lot during this down period to address the causes of David Douglas’ discontent with quadrupoles and their power supplies.  Several of the 5F quadrupoles had low loss cables installed so they could reliably not trip during hysteresis loops.  All trim cards were modified so they would not trip upon turn-on.  The entire trim rack system was given a tune-up; connections were tightened and faulty elements discovered and replaced.

•	Of even more importance, contact with the folks who repair the system were solidified.  With the tune-up accomplished, the failures of the trim racks and cards will be reduced so that it will not overwhelm the system.  Rather, we are determined to use the formal paperwork tracking systems that are already in place so we will not let failures go un-resolved.

•	We made a big increase in our ability to diagnose problems with the QX quadrupoles as detected by beam operations. After the tune-up, we used the field measuring probe fixture, so ably developed by the shop.  We found that it gets reproducible readings, to the gauss level, for 3 or 4 pole gaps in the QX quadrupoles.  It enabled us to detect one trim card that was 5% out of calibration.  After recording field values for the QX Set at half maximum field, we have a baseline to track drift or calibration problems in trim cards and changes in the quadrupoles. In addition, using the fixture and probe enables us to qualify or reject exchanged trim cards when the installed cards fail.

WBS 11 (Optics):

FEL mirrors

The HR and OC assembly's leadscrews were conditioned to allow for a faster mirror changeout.  Mirror alignment will commence today.  We are procuring witness samples of our mirror substrates to send to several coating vendors.  The output of the master oscillator for the advanced drive laser was realigned through the amplifier chain.  We are making 48W of IR with the MO configured for low phase noise, compared to 50W when in the high phase noise regime.  We can make up the necessary delta, if needed, by slightly raising the pump diode power. We need the advanced drive laser as a surrogate for calorimetry and laser damage testing.

Other Activities

A vexing leak in the optical transport system (OTS) section in User Lab 1 (UL1) was found and fixed.  We should be able to pump that section to the point that the vacuum interlocks will permit the valve to be opened.   Work continues on the THz pump probe system.  The plan is to measure the phase noise of the electronics this weekend. (the only time we can have the new phase noise measuring system). The ultrafast laser system, now situated in the THz hutch, is coming back to life.  The pump laser was successfully run.  The oscillator is out of alignment, so some work there is required, as well as a safety shutter added.  The extinction ratio of the EO cells for the drive laser were measured individually, and each found to be ~ 100:1.  This should be sufficient for operations.  The first EO cell had a damage spot that scattered light, and was replaced with the spare.  A new one needs to be purchased.  A shorter work table was moved into the drive laser Clean Room to complete an action item submitted by EH&S.   The vacuum vessel for the DIRUP-funded (to the College of William and Mary) "pulse stacker", an external cavity for the FEL, was assembled, aligned, and is under roughing vacuum.  We welcome Michael Klopf, a postdoc working on the THz project, to our trailer.  We were pleased to learn that we are being awarded contracts by the JTO for two projects entitled "Short Rayleigh Range FEL Operation" and "Advanced Figure Control".  We will also be subcontracted to work with Dr. H. Freund (SAIC) for his contract " Modeling and Simulation of the Effect of Mirror Distortion on High-Power FEL Oscillators".Measurements started on the flow-induced vibration of our mirror geometry.  We need this to determine the limits to the flow of ~50K helium, a Navy priority.

Terahertz:

This week we welcome Michael Klopf to the FEL group, with special responsibility for the THz laboratory.

We received the critical Picarin lens for our next imaging experiments.  The specifications for an ultrafast hot-electron bolometric detector were finalized.