# MEMORANDUM

To:		Distribution

From:		Gwyn Williams for George R. Neil

Subject:	FEL Upgrade Project Weekly Brief – October 15-19, 2007

Date:		October 19, 2007

Highlights:

Admiral Landay signed the MOU contract extension that provides our base funding. 

The gun test stand beamline is now complete and awaiting pump-down. 

The new regenerative amplifier for the GTS drive laser is working in Lab 6 and producing 60 ps IR pulses at 10 Hz with an energy of 1mJ.  This surpasses the design specifications, giving comfortable headroom.

We completed the upgrade to the safety system in user Lab 3, which means that the upgrades to all user labs are now complete.

Management:

Jim Boyce attended the Industrial Physics Forum of the American Institute of Physics (AIP) and, as JLab’s representative, participated in the Corporate Associates Advisory Committee (CAAC) of the AIP.  Both meetings were held in conjunction with the annual American Vacuum Society conference in Seattle, Washington. 

George Neil gave a presentation at the 13th International Workshop on RF Superconductivity in Beijing. 

Gwyn Williams presented the FEL Annual Work Plan to JLab management. 

Michael Kelley presented a paper at the annual AVS meeting in Seattle about surface studies to improve the performance of SRF accelerators, such as the FEL driver.

Injector:

From Monday through Wednesday we hosted Philippe Piot, Daniel Mihalcea, and Nikolai Vinogradov, from the Physics and Astrophysics Group, Department of Physics, Northern Illinois Center for Accelerator & Detector Development, Northern Illinois University, and Accelerator Physics Center, Fermi National Accelerator Laboratory. We had a very productive agenda and discussed possibilities for using the Gun Test Stand for halo detector development as well as for starting a collaboration on injector modeling. 

The vacuum group finished the installation of the GTS beam line, which is ready to be leak check.  We expect to start the beam line vacuum bake early next week.  C. Hernandez-Garcia attended as thesis advisor to Deepesh Kumar's M. Sc. oral defense at ODU, concluding one year mentoring Deepesh on the thesis entitled: "PARMELA-based simulations of the Jefferson Lab Free Electron Laser Injector ". We continued refurbishing the FEL gun.

RF:

RF – All LCW lines in the RF system were checked for flow.  All small orifices were opened with a 0.055 finger drill to ensure the acid flush would work next week.  Several small lines were completely blocked for 2 klystrons and a heat sink with four 5 watt amplifiers.  Zone 4 has the LCW by-passed to its circulators.  So it is ready for the acid flush.  Zone 3 will be ready also by the end of today.

There are 48 LCW channels in parallel in the collector of the linac klystrons.  The channels are 0.047” x 0.070”.  If the flow through these channels is restricted, hot spots in the collector develop and the channel will soon be blocked completely.  If too many channels are blocked, the klystron will have to be replaced.  The LCW flows in each zone need to be closely monitored and acid flush the klystrons when the flow starts to fall-off.

GTS HVPS – When the SF6 system is finished, the HVPS is ready for testing at high voltage (585 kV).  The Running/Conditioning Resistor is ready for installation when the Gun Tank is installed.

Instrumentation and Controls:

This week we spent some time this week testing the Drive Laser Timing and Synchronization system with the Antares Laser setup in Lab 6.  We were successful in locking the Coherent RF and the repetition rate timing signal's phases.  Once we were able to establish phase lock we continued to add the required triggers with the proper delays.  We were successful with the first couple of steps in these timing tests and then found that the system was breaking down and going in and out of phase lock as more triggers were added.  Currently we are testing these timing signals and trying to maintain phase locked signals throughout the timing system.  The first problem that we found and temporarily fixed was the amplitude of the 37 MHz drive lacks the amplitude to effectively trigger the timing system.  Currently we have several amplifiers in the system to bring the signal to acceptable TTL trigger levels.  We are currently looking into developing a high speed amplifier to properly drive the 50 ohm timing circuit.

We also managed this week to get the RS-485 communication established between the IOC and the Varian Dual Ion Pumps.  Currently we have successfully tested the digital I/O portions of the serial communication.  We are currently assembling some required I/O jumpers to enable to pumps HV.  Once we have the HV cables terminated or an appropriate load to connect to the pumps we will test the analog readback portions of the I/O.  First signs show that this system is ready for operation and should be fully functional next week.

This week we were successful in placing the FLog book onto the main page of the Wiki through a PHP script.  This is just the first step in the process so we began to debug this script in order to make the FLog book more readable/user friendly.  This week we've discovered some issues with the fella account and how it affects the devlore server.  The server appears to have a process using the incorrect password for the fella, this causes the account to lock.  We are working to identify the process in question and correct it.

Efforts continued on the LPSS wiring in User Lab 5.  The master control lines, mirror cassette, hutch interface and  status panel were all completed this week.  We've also managed to complete the required safety modifications to User Lab 3.  Currently the safety committee is reviewing this work.

In order to have digital I/O easily and readily available for applications a four port I/O panel was fabricated with four Burndy connections for six 8-bit banks of digital I/O.  The IP-48 Digital IP pack was installed in the carrier card in IOCFEL11 and the ribbon conversion cabling to convert the 50-pin ribbon to a 64-pin schroff connection was installed as well.  We've begun testing the hardware and the software for these 48 signals and currently have identified some required modifications in software.  Once these modifications are completed we will resume testing of this system.

The GTS House Air Line Extension analysis and associated TOSP for pressure and leak testing is nearing completion.  The final documents are missing schematic diagrams (currently in George Biallas' possession) and calibration data from the operational checks of the relief valves.  The operational checks of the pressure relief valves can be completed as soon as the 200psi bottled gas regulator comes in.  The threaded adapter that allows installation of the final relief valve has been installed and is ready once the valve arrives.  The compressor bleed line has been hooked up to the outlet line of the compressor for the Gas Transfer system.  Two inch rubber hose has been installed connecting the SF6 system to the bladder bag.  Two hose clamps were used at each termination end to secure the connections.  The connections for the GTS gas tank transducer have been established and tested.

Other accomplishments this week included repairing a Mini ITX computer by replacing the power supply board and some burnt wires.  Check out of a new style camera lens and documenting the performance on the Wiki for further reference.  Selecting the drive laser hutch hepa filter and revising the hutch design to accept the filter.  Connecting and debugging a new stepper motor and encoder required for the magnet test stand linear stage test setup.

Electron Beam Transport:

Improvements and Upgrades

Gun Test Stand (GTS)

•	In building the SF6 Gun Tank system, the JLab Shop completed final machining of the o-ring surfaces on all the flanges on the two large vessels (see protected surfaces in the 1st photo).  The shop is now working on completing the tubular extension (see second photo).  Unfortunately, qualified welder, machinist and weld inspector are on vacation next week.  Pressure test will be the week of the 29th of October.

•	The tubing run for the House Air Line to the SF6 system is physically complete. I reviewed the analysis and asked for the inclusion of some additional items in the boundary of the system. Those need documentation.  In addition, the TOSP for the pressure test took some time to write and iterate and now we need a regulator to match the pressure of the test’s relief valve for its calibration.  A safe system is in the details.  The pressure test is now slated for early next week.

•	In work on the GTS Beam Line, the Vacuum Group installed the complete line and is about to start pumping. (See third photo)

•	Matt Marchlik continues work on the hutch for the drive laser.

•	Shukui Zhang, Carlos and I reached accord that the breadboards on the new gun drive laser and cesiation optics can be most effective if they are mounted vertically.

SF Sextupole Magnet Testing

•	Magnet Test continued with the second magnet on the test stand where a failed “x” drive motor prevented completing the measurement.  Scheduled crane safety training will prevent starting a third magnet until the week after next.

High Power Optics Risk Reduction

Work resumed this week on the cw laser tester.  With Pavel Evtushenko's assistance, the CCD camera used to determine the mode size on the mirrors under test was calibrated.  We can now be certain that the mirrors are subjected to high irradiances.  With the ability to scan the mode across the optic, we can approximate larger mode area testing.  I am now starting to calibrate the IR camera to collect thermographic data that will later be converted to absorption values.

A teleconference was held with the team at Colo. State Univ. to discuss results obtained at JLab earlier this month, and to plan our activities for the next few weeks.

The documentation required for a proposal to the JTO was completed and submitted.

Optics

With the high reflector cavity work complete we are now focusing on the output coupler (OC) end of the machine. Unfortunately the vacuum furnace needed to braze the OC mirrors has been down for two weeks. We understand that the furnace was fixed yesterday but its usage schedule has had to slide till today. We are now scheduled to begin brazing next Wednesday with an anticipated completion on the following Wednesday. We should be able to complete the OC installation on the first week of November. The Cryo-Group has removed the “U-Tube” supply line from the OC helium distribution can. We can now work on the OC vessel with the conventional cooling setup. The modifications to the low power mirror cassette were completed this week. We should receive those parts in two weeks. We took advantage of the rearranging of the stored Helios components to palletize four 440l/s ion pumps. If the weather permits, they should be delivered today. We will check them out and install them in the Labs next week. The stands to support the harmonic block filter and hutch shutter has been assembled. These will be installed after the ion pumps are in place.

Lasers and Optical Diagnostics: 
We preformed a successful laser certification for operating the amplifier in lab 6. We are now focusing on the amplification experiment. This is the most important part of the whole GTS drive laser. The test shows great system performance, surpassing the designed specifications. We are expecting to finish the remaining work soon.  The EPICS DLPC was also tested and we found a few improvements are needed for stable operation. We have been also working with GUN group and I&C group on other projects related to the optical diagnostics for GTS.

Terahertz:

The 16 T superconducting magnet from Cryogenic, Ltd. was moved to the FEL lobby this week.  We have made plans to setup the magnet and perform the acceptance tests in mid November.

In preparation for that, we have begun to work on the analysis of the cryogenic/ODH, magnetic field, and electrical hazards. 

Also this week, we were notified of the publication of our manuscript describing the THz beamline design in Nuclear Instruments and Methods A. 

J. M. Klopf, A. Greer, J. Gubeli, G. R. Neil, M. Shinn, T. Siggins, D. Waldman, G. P. Williams, A. Todd, V. Christina and O. Chubar, The Jefferson Lab High Power THz User Facility, Nucl. Instrum. Methods A, 582, 114-116, (2007).

Word version:  FEL Upgrade Project Weekly Brief – October 15-19, 2007