Jan 2 – Jan 16 	: Source & Laser Table setup

Jan 17 – Jan 21 	: G0 Laser Table setup

Jan 21 – Jan 25 	: Machine checkout & PSS Certifications

Jan 26 – Jan 28 	: Injector & machine restoration

Jan 29 – Feb 4   	: G0 beam studies & setup

Feb. 5 		: Machine setup for Physics Program

Feb. 6 		: Hall B commissioning begins

Feb. 24 		: Hall A commissioning begins

Mar 17 		: Hall C commissioning begins

Accelerator Tasks Jan. 1 – Feb. 5

| Done | ATLIS | Author | Schedule | Title | Status |
| --- | --- | --- | --- | --- | --- |
| x | 4157 | Suleiman | Dec. ‘05 | Merging G0 Injector DAQ with the Main G0 DAQ | Hardware & ioc complete. Analysis (G0) in progress. |
|  | 3496 | Gaskell | Jan. ‘05 | Install Moller kicker at 3C15 | Kicker+ceramic installed Survey TBD |
|  | - | Poelker | ‘til 16th | January 2006 laser setup | BTeam Update |
|  | TBD-1 | Grames | ‘til 21st | Install high resolution HM DAC | Dickson wrote software. Cable fab. + install TBD |
|  | 4305 | Suleiman | 17-21 (4 Days) | G0 Backward Angle Laser Table Setup | Hardware ready. Software in progress. |
|  | 4223 | Kazimi | No time | Alignment survey of the elements around 0L02 spectrometer | Survey/alignment cannot do until next downtime |
|  | TBD-2 | Kazimi | Setup | Set “5 MeV region” to T=5 MeV using 0L07 | ATLIS to be written |
|  | TBD-3 | CASA | Setup | Set G0 energy : I=36.6 MeV, NL=SL=325 MeV (650 MeV/pass setup) | ATLIS to be written |
|  | 4306 | Suleiman | Setup 16 hours | G0 Backward Angle Injector Beam Studies | Follows ATLIS 4305 |
|  | 4347 | Chao | Setup 4h,2D,8h | G0 PQB Injector Match | Follows ATLIS TBD-2 |
|  | TBD-4 | Spata | Setup | ½ pass setup at G0 energy 362 MeV | Follows ATLIS TBD-3 |
|  | TBD-5 | CASA | Setup | Set Hall A/B Program 738 MeV/pass (I=41.5 MeV, NL=SL=369 MeV) while retaining G0 injector (I=36.6 MeV) | Follows Setup |

Accelerator Tasks Jan. 1 – March 16

| Done | ATLIS | Author | Schedule | Title | Status |
| --- | --- | --- | --- | --- | --- |
|  | TBD-A | Chao, Yves, Erb |  | PZTBooster Testing & Commissioning | Discussion complete. Action Item 1/9 Test during setup or BS |
|  | 3510 | Benesch | February | Hall C Moller system mod for G0 (placeholder) | Awaiting MEG signoff |
|  | 3825 | Benesch | February | Rearrange end of Hall C line for G0 and beyond | Awaiting MEG signoff |
|  | TBD-B | MEG | February | Install beampipe w/ magnetic shielding between Hall C pivot and G0 girders | Awaiting MEG signoff |
|  | TBD-C | MEG | February | Reinstall Halo and G0 diagnostics girder | Awaiting MEG signoff |