## Slide 1
Allison Lung
DOE Accelerator Safety Workshop, August 15, 2017
12 GeV Project Status

## Slide 2: 12 GeV CEBAF Upgrade
Total Project Cost = $338M
ETC << $1M
Double maximum Accelerator energy to 12 GeV
  Ten new high gradient cryomodules
  Double Helium refrigerator plant capacity
  Civil construction and upgraded utilities
Add 10th arc of magnets for 5.5 pass machine
Add 4th experimental Hall D
New experimental equipment in Halls B, C, D
2004: CD-0
2006: CD-1
2007: CD-2
2008: CD-3
2014: CD-4A
2017: CD-4B
Maintain capability to deliver lower pass beam energies: 2.2, 4.4, 6.6….

## Slide 3: 12 GeV Scientific Capabilities
Hall D – exploring origin of confinement by studying
exotic mesons
Hall B – understanding nucleon structure via generalized parton distributions and transverse momentum distributions
Hall C – precision determination of valence quark properties
in nucleons and nuclei
Hall A – short range correlations,
form factors, hyper-nuclear physics,
future new experiments (e.g., MOLLER and SoLID)
Notes: 3

## Slide 4: Status @ 2016 Accelerator Safety Workshop
Conventional Facilities: DONE
  Hall D Complex ~10,080 ft2
  Additions to existing facilities ~8,400 ft2
  Utilities expansion
Hall D Experimental Equipment: DONE
  GlueX spectrometer; electronics; target
  Hall infrastructure; Tagger area
  Commissioning
Accelerator: DONE
  Cryomodules ; Cryogenics ; Beam Transport
  Beam Transport ; Extraction
  Project Commissioning
Key Performance Parameters – demonstration through beam runs

## Slide 5: Highlights Since Summer 2016
All about Hall B and Hall C experimental equipment: DONE
  Detectors and Electronics
  DAQ/Computing (software/firmware)
  Beamline and Infrastructure
  Magnets:
    Hall C – 3 (of 5) delivered, 5 installed and tested
    Hall B Torus – tested
    Hall B – Solenoid delivered, installed and tested
Key Performance Parameters – demonstration through beam runs

## Slide 6
  Accelerator Readiness Reviews (ARRs):
  Modular approach for machine and beamlines to Halls
    Phase 1a/b - CEBAF commissioning with 12 GeV tune beam (Aug/Oct 2013)
    Phase 2 - Commission Hall D Tagger with tune beam, full commission & operate Hall A (Jan 2014)
    Phase 3 - Commission & operate Hall D; Deliver beam to Hall B for HPS experiment (Aug 2014)
    Phase 4 – Commission & operate Halls B & C (Jan 2017)
      see Bob May's talk on Wed morning
Readiness to Operate: Accelerator

## Slide 7: Readiness to Operate: Exp. Equipment
Experiment Readiness Reviews (ERRS):
  Objective: safe and efficient operation of equipment (and/or an entire experiment)
  Hall C ERRs:
    Q1 magnet (Jan 2015) ; HB magnet (Mar 2015)
    Spectrometers, beamline, targets, early experiments (Aug 2016)
    Q2/Q3/D magnets (Oct 2016)
  Hall B ERRs:
    Ancillary detectors (Jun 2016)
    Torus magnet (Apr/Jun/Jul 2016)
    CLAS12 Detectors (Dec 2016)
    Solenoid magnet (Jul 2017)

## Slide 8: Hall C: SHMS Magnets Delivered
D: OCT-2016
Q1: JAN-2015
HB: MAR-2015
Q2: OCT-2016
Q3: DEC-2016
Dipole Rigging
NOV-2016
Dipole CCR

## Slide 9: Hall C: 12 GeV Detectors All Installed
Noble-Gas Cerenkov (NGC)
Drift Chambers
S1XY Hodoscope
Heavy-Gas Cerenkov (HGC)
S2XY Hodoscope
Shower Counter
(within wall)
Pre-Shower Counter

## Slide 10
Hall C: KPP Beam Run
March 7–10, 2017
Beam ~ 5 mA CW
Target BeO, Carbon
Q3
D
Q2
Q1
HB
Installation complete Feb 2017

## Slide 11
Hall C: KPP Demonstrated
Accepted by DOE March 14, 2017
Detector operational: events recorded with a > 2nA electron beam at > 6 GeV beam energy (3 pass).
Detector performance: charged-particle tracks from position-sensitive detectors.
Preshower
S1x
S1y
S2x
S2y
Wire Chambers
Shower
Tracking / Event Display
Two perspectives on the same event:
  Red track generated by Wire Chamber data only
  Visual confirmation that the other detector elements along the track do indeed see the same particle

## Slide 12: Hall B: Torus
Installation completed in May 2016
Testing completed in Nov-2016

## Slide 13
Hall B: Detector Configuration – KPP Run
Beamline
CTOF and SVT
Forward Carriage
Tagger Shielding

## Slide 14: HALL B KPP Demonstrated
Accepted by DOE February 7, 2017
Detector operational: events recorded with a > 2nA electron beam at > 6 GeV beam energy (3 pass).
Detector performance:
reconstructed particle trajectories.
<s>=1.2 cm

## Slide 15: Hall B Solenoid – Arrival (27-Jun-2017)
Tarp-covered magnet on truck at JLab's back gate.
Tarp removed; Solenoid on shipping frame.

## Slide 16
Magnet on CLAS12 carriage next to Drift Chambers.
Solenoid Installation (28-Jun-2017)

## Slide 17: Solenoid Effort at JLab after Arrival
Arrival Checks
  Receiving inspection (vacuum, electrical, instrument), place on stand
  Remove shipping restraints, survey
Cryogenics SST Attachment
  Place SST, weld SST cryostat bottom plate to solenoid, add lower thermal shield plate, splice power leads, complete piping
  Radiation shield MLI, hook-up pumping system
Pump-down
Cool-down Starts Today
Energize in September

## Slide 18: 12 GeV Project: Summary
All superconducting magnets delivered, installed, tested
All detectors, electronics, beamline, infrastructure complete
All Key Performance Parameters demonstrated
All Level-2 Milestones Complete
All Project Scope COMPLETE
  Additional Solenoid commissioning in progress
Project Ready for CD-4B

## Slide 19: APPENDIX

## Slide 20
Hall C #3: Detector Performance
3. Data showing relative timing of trigger, tracking, and particle identification in detector subsystems.
Time [ns]
PreShower Left Side Timing
HGC Timing
PMT Number
PMT Number
PMT Number
Time [ns]
Time [ns]
Time [ns]
Time [ns]
NGC Timing
Shower Timing
PreShower Right Timing
HGC, NGC Timing
  Horizontal axis is PMT #
Shower Timing
  Horizontal axis is PMT #
Pre-shower Timing
  Horizontal axis is PMT #
PMT Number
PMT Number

## Slide 21
Hall C #3: Detector Performance
Wire Drift Chambers
  2 wire drift chambers provide tracks for charged particles
    6 wire planes per chamber
Figure shows time distribution histograms of particles passing by the wires in all 6 planes
  All planes have similar timing structure, minimal background
  All planes have similar counts indicating equal detection efficiencies
3. Data showing relative timing of trigger, tracking, and particle identification in detector subsystems.
Timing relative to Trigger [ns]
Wire Drift Chamber Timing

## Slide 22
Electrons
Hall C : Particle ID
Preshower Energy (arb. units)
NGC Signal (arb. units)
Pions
Preshower Energy (arb. units)
HGC Signal (arb. units)
5. Particle identification plots using signals from calorimetry and Cerenkov detectors.
HGC vs PSh
NGC vs PSh
arb. = arbitrary