## Slide 1: ESS licensing process and Readiness Reviews
Peter Frisk Johan Waldeck
Project Manager SSM Licensing Project Manager ESS

## Slide 2: Presentation Outline
SSM perspective of the licensing process and planned inspection program -Peter Frisk SSM
ESS perspective of the licensing process and planned readiness reviews -Johan Waldeck ESS

## Slide 3: The Swedish Radiation Safety Authority (SSM) reviews of the ESS facility
The SSM reviews are performed according to the EU Basic Safety Standard (EU-directive), the Swedish Radiation Protection Act, the SSM regulations and the specific SSM conditions given to ESS
The SSM reviews only include safety ralated to radiation (not chemical safety, electrical safety etc.)
The SSM review team consists of about 30 reviewers, a mix of engineers, PhDs, etc. from different specialities, all based at SSM.
There will be no SSM site office at ESS but SSM will perform regular site inspections.
The SSM reviews will be stepwise and verifications of fulfilment of SSM requirements will be performed by site inspections.
The SSM site inspections will be separated from the ESS readiness reviews both in time and in content.

## Slide 4: The SSM reviews of the ESS facility
The SSM document reviews will be based on the ESS safety analysis report including areas described below and a self assessments from ESS describing how they fulfil/are going to fulfil requirements given by SSM.
Review areas:
  Organisation and Management of the Activities
  Protection of Workers
  Protection of Public and Environment
  Planned Emergency Preparedness
  Construction and Safety Analysis
  Mechanical Devices
  Physical Protection
  Cyber security
  Operation
For each trial operation application ESS has to present a trial operation plan. SSM will review the plan and, thereafter, create an appropriate inspection program.
ESS has to present operation limits and conditions for each trial operation application.

## Slide 5: Licensing managed as a project
Core Team composed of central resources and project representatives
Team meets every week
  Coordinate work to be performed across ESS projects
Licensing not a separate thread
  integrated part of “normal“ project activities
Licensing project core team
One member from each Project/division
Johan
Project manager
Per N
Target Sub-project
Peter S
NSS Sub-project
Peter
ESH Sub-project
Lali
Acc Sub-project
Mikael J
Admin & Proj. Man. Sub-project
Henrik C
ICS Sub-project
Francois
Systems engineering
Carl
Q Sub-project
Michael
CF Sub-project

## Slide 6: Alignment of ESS project phases to SSM licensing steps
Permissibility
Permit
Installation
Permit
Trial operation
Permit
Routine operation
Permit
Detailed design & Construction
Procurement and Installation
Commissioning
Operation
Preliminary Design
ESS project phases
SSM stepwise licensing process

## Slide 7: Key events in next trial operation permits
ESS Application
SSM Request
ESS Response
SSM Conditional permit
ESS readiness review
SSM Inspection
Beam on
Use this time to develop evidence

## Slide 8: Split permit in parts to optimize overall schedule
Warm LINAC
Trial operation permit
SC LINAC
Trial operation permit
Neutron production
Trial operation permit

## Slide 9: Within a permit, split commissioning into conditional steps
Warm LINAC commissioning
IoS-RFQ
Commissioning
IoS-DTL2 Commissioning
IoS-DTL4 Commissioning
ESS Readiness review
SSM Inspection

## Slide 10: Thank You!