## Slide 1: HPS Budget and Schedule
Marco Oriunno, June 18, 2014

## Slide 2: Schedule and Manpower

## Slide 3: HPS Master Planning V810
Alcove ready: 5/30/2014
On Schedule
SVT Ready to Ship: 9/25/2014
6 weeks delay
ECAL Assembled: 9/22/2014
6 weeks delay
Slow Control ready: 9/30
4 weeks delay
Installation & Commissioning:
From September to November 2014

## Slide 4: Installation and Commissioning
ECAL Ready for the Beam
10/20/2014
SVT Installed
< 11/14/2014
SVT Ready for the Beam
< 11/18/2014
Engineering Runs
> 12/19/2014
Complete Beamline
9/15/2014

## Slide 5: Manpower (Scientific)
 |  | PM | Beamline | SVT | SVT DAQ | ECAL | TDAQ | Slow Control | Software | I&C | FTE
M. Battaglieri | INFN |  |  |  |  | 0.21 |  |  |  | 0.02 | 0.23
A. Celentano | INFN |  |  |  |  | 0.21 |  |  | 0.12 |  | 0.33
Stuart Fegan | INFN |  |  |  |  |  |  |  | 0.3 |  | 0.30
A.D'Angelo | INFN |  |  |  |  | 0.21 |  |  |  |  | 0.21
A.Rizzo | INFN |  |  |  |  | 0.21 |  |  | 0.12 |  | 0.33
L.Colaneri | INFN |  |  |  |  | 0.21 |  |  | 0.52 |  | 0.73
G.Simi | INFN |  |  |  |  |  |  |  | 0.3 |  | 0.30
N.Randazzo | INFN |  |  |  |  | 0.2 |  |  |  |  | 0.20
M.DeNapoli | INFN |  |  |  |  | 0.2 |  |  |  |  | 0.20
R.Devita | INFN |  |  |  |  | 0.1 |  |  | 0.12 |  | 0.22
M.Carpinelli | INFN |  |  |  |  | 0.4 |  |  | 0.1 |  | 0.50
V.Sipala | INFN |  |  |  |  | 0.3 |  |  |  |  | 0.30
M.Osipenko | INFN |  |  |  |  |  |  |  | 0.2 |  | 0.20
S.Aiello | INFN |  |  |  |  | 0.2 |  |  |  |  | 0.20
E.Leonora | INFN |  |  |  |  | 0.2 |  |  |  |  | 0.20
D.Calvo | INFN |  |  |  |  | 0.2 |  |  |  |  | 0.20
A.Filippi | INFN |  |  |  |  |  |  |  | 0.3 |  | 0.30
C.Ventura | INFN |  |  |  |  | 0.2 |  |  |  |  | 0.20
Raphael Dupre | IPNO |  |  |  |  | 0.63 |  |  | 0.08 | 0.02 | 0.74
Gabriel Charles | IPNO |  |  |  |  | 0.50 |  |  | 0.50 |  | 1.00
Stepan Stepanian | JLAB | 0.05 | 0.10 |  |  | 0.10 |  |  |  | 0.10 | 0.35
Arne Freyberg | JLAB |  | 0.05 |  |  |  |  |  |  |  | 0.05
Hovanes Hegiyan | JLAB |  |  |  |  |  |  | 0.21 |  | 0.02 | 0.23
Serguei Boyarinov | JLAB |  |  |  |  |  | 0.25 |  |  |  | 0.25
Maurizio Ungaro | JLAB |  |  |  |  |  |  |  | 0.10 |  | 0.10
FX Girod | JLAB |  | 0.40 |  |  |  |  |  |  |  | 0.40
Yuri Gernstein | Rutgers |  |  |  |  |  |  |  | 0.21 |  | 0.21
Tim Nelson | SLAC |  |  | 0.70 | 0.25 |  |  |  |  | 0.05 | 1.00
Per Hansson | SLAC |  |  | 0.35 | 0.40 |  |  |  | 0.20 | 0.05 | 1.00
Sho Uemura | SLAC |  |  | 0.20 | 0.20 |  |  |  | 0.20 | 0.02 | 0.62
Matt Graham | SLAC |  |  |  |  |  |  |  | 0.50 |  | 0.50
Jeremy McCormick | SLAC |  |  |  |  |  |  |  | 0.20 |  | 0.20
Norman Graf | SLAC |  |  |  |  |  |  |  | 0.50 |  | 0.50
John Jaros | SLAC | 1 |  |  |  |  |  |  |  |  | 1.00
Homer Neal | SLAC |  |  |  |  |  |  |  | 0.08 |  | 0.08
Takashi Maruyama | SLAC |  | 0.40 | 0.35 |  |  |  |  | 0.20 | 0.05 | 1.00
Ken Moffeit | SLAC |  | 1.00 |  |  |  |  |  |  |  | 1.00
Clive Field | SLAC |  | 0.17 |  |  |  |  |  |  |  | 0.17
Vitaliy Fadeyev | UCSC |  |  | 0.12 | 0.04 |  |  |  |  |  | 0.15
Forest McKinney | UCSC |  |  | 0.18 |  |  |  |  |  |  | 0.18
Omar Moreno | UCSC |  |  | 0.13 | 0.15 |  |  |  | 0.21 | 0.02 | 0.51
Kyle McCarthy | UNH |  |  |  |  | 0.25 |  |  | 0.25 |  | 0.50
Maurik Holtrop | UNH |  |  |  |  |  |  |  | 0.21 | 0.02 | 0.23
Annie Simonyan | Yerevan |  |  |  |  |  |  | 0.50 |  |  | 0.50
Nerses Gevorgyan | Yerevan |  |  |  |  |  |  | 0.50 |  |  | 0.50
Holly Szumila-Vance | W&M |  | 0.25 |  |  | 0.50 |  |  | 0.25 |  | 1.00
Total FTE by Subsytem |  | 1.05 | 2.37 | 2.02 | 1.04 | 5.04 | 0.25 | 1.21 | 5.78 | 0.37 | 19.13

## Slide 6: New Manpower (Engineering)
Mechanical Engineering |  | PM | Beamline | SVT | SVT DAQ | ECAL | TDAQ | Slow Control | Software | I&C | Total
Marco Oriunno | SLAC | 0.40 | 0.10 | 0.40 |  |  |  |  |  | 0.12 | 1.02
Shawn Osier | SLAC |  |  | 0.71 |  |  |  |  |  |  | 0.71
Matt McCulloch | SLAC |  | 0.02 | 0.60 |  |  |  |  |  |  | 0.62
Bob Connelly | SLAC |  |  | 0.15 |  |  |  |  |  |  | 0.15
Reggie Rogers | SLAC |  |  | 0.15 |  |  |  |  |  |  | 0.15
MD | JLAB |  | 0.46 |  |  |  |  |  |  |  | 0.46
ME | JLAB |  | 0.09 |  |  |  |  |  |  |  | 0.09
ME Accelerator JLAB | JLAB |  | 0.10 |  |  |  |  |  |  |  | 0.10
MT Accelerator JLAB | JLAB |  | 0.70 |  |  |  |  |  |  |  | 0.70
P. Rosier | IPNO |  |  |  |  | 0.04 |  |  |  | 0.02 | 0.06
E. Rindel | IPNO |  |  |  |  | 0.17 |  |  |  | 0.02 | 0.19
F. Pratolongo | INFN |  |  |  |  | 0.13 |  |  |  |  | 0.13
G. Mini | INFN |  |  |  |  | 0.13 |  |  |  |  | 0.13
MT Hall-B | JLAB |  |  |  |  | 0.06 |  |  |  |  | 0.06
Electrical Engineering |  |  |  |  |  |  |  |  |  |  | 
Ryan Herbst | SLAC |  |  |  | 0.56 |  |  |  |  | 0.13 | 0.69
Ben Reese | SLAC |  |  |  | 0.85 |  |  |  |  |  | 0.85
Dave Nelson | SLAC |  |  |  | 0.15 |  |  |  |  |  | 0.15
ET SLAC | SLAC |  |  | 0.30 |  |  |  |  |  |  | 0.30
Ben Raydo (EE) | JLAB |  |  |  |  |  | 0.50 |  |  |  | 0.50
EE Hall-B JLAB | JLAB |  | 0.16 |  |  |  |  |  |  | 0.04 | 0.20
ET Hall-B JLAB | JLAB |  | 0.28 |  |  |  |  |  |  | 0.04 | 0.32
CS JLAB |  |  | 0.25 |  |  |  |  |  |  |  | 0.25
EE Accelerator JLAB | JLAB |  |  |  |  |  |  | 0.23 |  |  | 0.23
Emmanuel Rauly | IPNO |  |  |  |  |  |  |  |  | 0.02 | 0.02
 |  |  |  |  |  | 0.13 |  |  |  |  | 0.13
Total FTE by Subsytem |  | 0.40 | 2.16 | 2.31 | 1.56 | 0.52 | 0.50 | 0.23 |  | 0.38 | 8.07
Baseline Manpower, 4.78 FTE

## Slide 7: Budget

## Slide 8: Beamline Supplemental Funding
 | M&S/Labor | Actual | Budgeted | Difference
Beamline Elements | $51.7k / $137.6k | $189.4k | $134.6k | - $54.8
Alcove Installation | $62.9k / $76.0k | $138.9k | $84.5k | - $54.4
Magnet | $33.3k / $7.5k | $40.8k | $26.6k | - $14.2k
TOTAL | $147.9k / $221.1k | $369.1k | $245.7k | - $123.4k
The missing $125k were requested and agreed by DOEon 4/25, as part of the contingency held by DOE.

## Slide 9: JLAB Budget (May 2014)
Chart: 
Monthly Incurred expenses | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.9808 | 0 | -8.3733 | -38.9384 | -34.1251 | -131.2253 | -60.9913
Total Incurred expenses | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1.9808 | -1.9808 | 6.3926 | 45.3309 | 79.456 | 210.6813 | 271.6726
Net Asset | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -540 | -541.9808 | -541.9808 | -533.6074 | -494.6691 | -460.544 | -329.3187 | -393.3274
Monthly Spending Baseline | -0.94147 | -0.9863 | -1.0311 | -0.89664 | -1.0311 | -2.0317 | -21.5874 | -46.6613 | -45.4897 | -11.1818 | -7.6837 | -16.9428 | -22.0968 | -54.1635 | -87.6029
Total Spending baseline | 0.94147 | 1.9278 | 2.9589 | 3.8556 | 4.8867 | 6.9184 | 28.5058 | 75.1671 | 120.6568 | 131.8386 | 139.5223 | 156.4651 | 178.5618 | 232.7253 | 320.3282
$393k
$271k

## Slide 10: SVT Supplemental Funding
Some delays required an increased Engineering Manpower efforts in order to maintain our ability to install HPS this fall at JLAB.
Discussion started with DOE on 6/12.
Funds Required to Complete Project | 
Projected Costs | $ 676.6
Balance thru May 31, 2014 | $ 143.3
Net Funds Required | $ 533.2
Funds Requested | 
Total Contingency Available | $ 384.1

## Slide 11: SLAC Budget (May 2014)
$143k
$1.17M
Chart: 
Monthly Incurred expenses | -6.252 | -39.798 | -56.565 | -47.691 | -54.648 | -60.903 | -53.523 | -56.448 | -42.561 | -50.381 | -79.109 | -62.838 | -178.475 | -166.026 | -214.308
Total Incurred expenses | 6.252 | 46.05 | 102.615 | 150.306 | 204.954 | 265.857 | 319.38 | 375.828 | 418.389 | 468.77 | 547.879 | 610.717 | 789.192 | 955.218 | 1169.526
Net Asset | -406.748 | -366.95 | -310.385 | -262.694 | -208.046 | -147.143 | -93.62 | -888.572 | -846.011 | -798.23 | -721.721 | -658.883 | -482.708 | -331.382 | -117.074
Monthly Spending Baseline | -5.1016 | -7.4824 | -7.8225 | -104.7379 | -121.7966 | -66.1421 | -61.4634 | -238.9605 | -231.3321 | -78.6344 | -97.9644 | -67.3087 | -61.4178 | -65.1258 | -33.9407
Total Spending baseline | 5.1016 | 12.584 | 20.4064 | 125.1443 | 246.9409 | 313.083 | 374.5464 | 613.5069 | 844.8391 | 923.4735 | 1021.4379 | 1088.7466 | 1150.1644 | 1215.2902 | 1249.2309

## Slide 12: TOTAL (SLAC+JLAB) Budget (May 2014)
Chart: 
Monthly Incurred expenses | -6.252 | -39.798 | -56.565 | -47.691 | -54.648 | -60.903 | -53.523 | -56.448 | -40.5802 | -50.381 | -87.4823 | -101.7764 | -212.6001 | -297.2513 | -275.2993
Total Incurred expenses | 6.252 | 46.05 | 102.615 | 150.306 | 204.954 | 265.857 | 319.38 | 375.828 | 416.4082 | 466.7892 | 554.2716 | 656.0479 | 868.648 | 1165.8993 | 1441.1986
Net asset (-1) | -406.748 | -366.95 | -310.385 | -262.694 | -208.046 | -147.143 | -93.62 | -1428.572 | -1387.9918 | -1340.2108 | -1255.3284 | -1153.5521 | -943.252 | -660.7007 | -510.4014
Monthly Spending Baseline | -6.0431 | -8.4687 | -8.8536 | -105.6345 | -122.8277 | -68.1738 | -83.0508 | -285.6218 | -276.8218 | -89.8162 | -105.6481 | -84.2515 | -83.5146 | -119.2892 | -121.5436
Total Spending baseline (-1) | 6.0431 | 14.5117 | 23.3653 | 128.9998 | 251.8276 | 320.0014 | 403.0522 | 688.674 | 965.4958 | 1055.312 | 1160.9602 | 1245.2117 | 1328.7263 | 1448.0155 | 1569.5591
$510k
$1.44M

## Slide 13: Readiness Review

## Slide 14: Readiness Review, Charge
Are the HPS specific equipment, documentation and procedures to run the experiment in place and adequate? This includes demonstrated readiness for full rate capability and expedient analysis of the data.
Are the formal documentation requirements and reporting (run coordinator  shift leaders) procedures for running the experiment adequate, appropriate and complete (COO, ESAD, RSAD, ERG, OSP’s, general equipment operation manuals, etc.)?
Has the entire beamline, target, detector configuration been defined (including ownership, maintenance and control during beam operations)? Is all the necessary equipment installed and operable? If not, what are the completion/commissioning schedule and procedures?
Has transmission of the primary beam and generated secondaries been evaluated for unexpected beam restrictions (e.g. too small of a beam pipe acting as a secondary target), background sources (e.g. large number of produced photons hitting the beam line) or paths (e.g. primary and/or secondary steering from a magnet fringe field)?
Are the radiation levels expected to be generated in the hall acceptable? Is any local shielding required to minimize the effects of radiation in the hall equipment?
Are the local shielding and the machine protection system required to minimize the effects of radiation in the HPS detector in place?
Have all the jobs that need to be done to mount the experiment/s been identified and defined adequately?
Have conflicts with the 12 GeV Upgrade in Hall B been examined and resolved?
Are the responsibilities for carrying out each job identified, and are the manpower and other resources necessary to complete them on time in place?

## Slide 15: Installation and Commissioning Schedule at JLAB, Summary Tasks

## Slide 16: Hall B beamline Installation, 7/15 through 9/15

## Slide 17: ECAL Installation and Commissioning, 9/8 through 9/22

## Slide 18: Receive SVT at JLAB, 10/7 through 10/28

## Slide 19: Beamline Commissioning, 10/10 through 11/10

## Slide 20: SVT Installation and Commissioning, 11/13 through 11/18

## Slide 21: SVT Installation
Run Position: 85”
Move 15” upstream

## Slide 22: Complete HPS Checkout – Electron Beam commissioning and Running, 11/24 through 12/19

## Slide 23: HPS in the Alcove

## Slide 24: Potential sonflicts with the 12 GeV Upgrade in Hall B

## Slide 25: Manpower (Preliminary)
Mechanical Engineering |  | I&C | 
Marco Oriunno | SLAC | 0.12 | SVT
Shawn Osier | SLAC |  | 
Matt McCulloch | SLAC |  | 
Bob Connelly | SLAC |  | 
Reggie Rogers | SLAC |  | 
MD | JLAB |  | 
ME | JLAB |  | 
ME Accelerator JLAB | JLAB |  | 
MT Accelerator JLAB | JLAB |  | 
P. Rosier | IPNO | 0.02 | ECAL
E. Rindel | IPNO | 0.02 | ECAL
Emmanuel Rauly | IPNO |  | 0.02
F. Pratolongo | INFN |  | 
G. Mini | INFN |  | 
MT Hall-B | JLAB |  | 
Electrical Engineering |  |  | 
Ryan Herbst | SLAC | 0.13 | SVT
Ben Reese | SLAC |  | 
Dave Nelson | SLAC |  | 
ET SLAC | SLAC |  | 
Ben Raydo (EE) | JLAB |  | 
EE Hall-B JLAB | JLAB | 0.04 | TDAQ, Slow Control
ET Hall-B JLAB | JLAB | 0.04 | TDAQ, Slow Control
CS JLAB |  |  | 
EE Accelerator JLAB | JLAB |  | 
Total FTE by Subsytem |  | 0.38 | 
 |  | I&C | 
M. Battaglieri | INFN | 0.02 | ECAL
A. Celentano | INFN |  | 
Stuart Fegan | INFN |  | 
A.D'Angelo | INFN |  | 
A.Rizzo | INFN |  | 
L.Colaneri | INFN |  | 
G.Simi | INFN |  | 
N.Randazzo | INFN |  | 
M.DeNapoli | INFN |  | 
R.Devita | INFN |  | 
M.Carpinelli | INFN |  | 
V.Sipala | INFN |  | 
M.Osipenko | INFN |  | 
S.Aiello | INFN |  | 
E.Leonora | INFN |  | 
D.Calvo | INFN |  | 
A.Filippi | INFN |  | 
C.Ventura | INFN |  | 
Raphael Dupre | IPNO | 0.02 | ECAL
Gabriel Charles | IPNO |  | 
Michel Garcon | CEA |  | 
Stepan Stepanian | JLAB | 0.10 | ECAL
Arne Freyberg | JLAB |  | 
Hovanes Hegiyan | JLAB | 0.02 | Slow Control
Serguei Boyarinov | JLAB |  | 
Maurizio Ungaro | JLAB |  | 
FX Girod | JLAB |  | 
Yuri Gernstein | Rutgers |  | 
Tim Nelson | SLAC | 0.05 | SVT
Per Hansson | SLAC | 0.05 | SVT
Sho Uemura | SLAC | 0.02 | SVT
Matt Graham | SLAC |  | 
Jeremy McCormick | SLAC |  | 
Norman Graf | SLAC |  | 
John Jaros | SLAC |  | 
Homer Neal | SLAC |  | 
Takashi Maruyama | SLAC | 0.05 | SVT, Beamline
Ken Moffeit | SLAC |  | 
Clive Field | SLAC |  | 
Vitaliy Fadeyev | UCSC |  | 
Forest McKinney | UCSC |  | 
Omar Moreno | UCSC | 0.02 | SVT
Kyle McCarthy | UNH |  | 
Maurik Holtrop | UNH | 0.02 | Software
Annie Simonyan | Yerevan |  | 
Nerses Gevorgyan | Yerevan |  | 
Holly Szumila-Vance | W&M |  | 
Total FTE by Subsytem |  | 0.37 | 

## Slide 26: Summary
Average delay of 4 weeks for SVT and ECAL
SVT on the Critical Path
Requested in April contingency for Beamline (more labor intensive than expected). Full funded
Started last week discussion with DOE to release contingency fro the SVT (delay and design changes require more Labor)
Refined Installation and Commissioning Schedule, probably sufficient for the Readiness Review.
Need to better estimate the manpower for the Installation and commissioning.