## Slide 1: RF Power for C75 - Resources
RF Power U[grade for C75
Richard Nelson

## Slide 2: Major Tasks
Major tasks (nearly identical to 0L04 mods)
  Procurement of materials
  Remove old parts from cathode power supply
    Transformer, choke, capacitors, HV deck, contactors…
  Modify enclosure to accommodate new components
  Place & installation new parts
    Transformer, choke, capacitors, HV deck, contactor, SCR controller, crowbar
  Wiring, cabling, interlocks
  Change controls & interface from analog and CAMAC to HPA controller & digital FCC
  Waveguide replacement (HPA – tuners & circulators)

## Slide 3: Tasks
  Bulk of the tasks accomplished by RF techs
    Installation, wiring, etc.
    Transformer move and welding with assistance
    Some software support to adapt digital controls
  Testing
    DC, controls, interlocks
    RF (into shorts first)
  Final waveguide connect to C75 CM followed by full-up testing

## Slide 4: Major Procurements
Klystrons will be purchased regardless and as ongoing spares & replacements
~77k for CPS upgrade components
  HV step-up transformer, choke, capacitor, contactor, crowbar, SCR controller
~80k for circulators (5kW to 8 kW capability)
  May be able to reuse existing units with load rebuild
~19k for waveguide tuners & misc. waveguide
Exact pricing depends on quantities
  Ideally multiple year contracts would be placed or larger buys up front
  Cost advantage for 1 time buys

## Slide 5: Labor & Procurements
Task/Milestone | Note | SE | EE/CS | ET | ED | Labor Total | Materials
HPA Controller |  | 0 | 1 | 0.4 | 0 |  | 
Network Modifications |  | 0.2 | 0.2 | 0.2 |  |  | 
Software Modifications |  | 0.2 | 0.4 |  |  |  | 
8 kW Klystrons/test/install | proc separate | 0.5 | 1 | 2 | 1 |  | 
8 kW Circulators * |  | 0.2 | 0.2 | 2 | 0.4 |  | 80,000
Waveguide (tuners) |  | 0.2 |  | 2 | 0.2 |  | 17,500
CPS Upgrade (rebuild) |  | 0.4 | 1 | 4 | 1 |  | 77,000
HPA Interlocks, CAMAC conversion |  | 0.2 | 1 | 2 | 0.4 |  | 2,500
HPA/CM Waveguide Installation |  | 0.4 | 1 | 3 | 1 |  | 2,000
Electrical Work (cable, conduit, breaker) |  |  | 0.4 | 2 | 0.6 |  | 2,000
AC Distribution& A/C (facilities) | separate |  |  |  |  |  | 
Commissioning, HV, shorts |  |  | 0.6 | 2 |  |  | 
RF Power Commissioning |  | 0.2 | 1 | 2 | 0.4 |  | 1,000
Total (weeks) |  | 3 | 7.2 | 18.4 | 5 | 33.6 | 182,000
* may be able to use existing circulators |  |  |  |  |  |  | 

## Slide 6: Non-optimized Draft Schedule

## Slide 7: Summary
Labor requirements well understood
  Quantities & talents
  This project should be familiar as it’s close to 0L04 upgrade
Dual work areas (HPA & CPS modifications) should allow parallel work with adequate staff to reduce completion time
  Could extend to working 2 zones in parallel
Actual labor pool will depend on staff size, work load, priorities