## Sheet1
Date | Weekday |  | Operations | Hall A | Hall A | Hall B | Hall B | Hall C | Hall C | Hall D | Hall D | Priority | Pass
|  | (GeV/pass) | Status | Experiment | GeV/mA/Pol/MHz | Experiment | GeV/nA/Pol/MHz | Experiment | GeV/mA/Pol/MHz | Experiment | GeV/nA/Pol/MHz | Hall | A/B/C/D
2023-10-01 | Sunday | 2.1 | Physics | E12-09-016 | 8.4/45/p/500 | Run Group D | 10.5/200/p/500 | NPS Group | 10.5/50/p/500 | OFF |  | C/B/A | 4/5/5/-
2023-10-02 | Monday | 2.1 | Physics | E12-09-016 | 8.4/45/p/500 | Run Group D | 10.5/200/p/500 | NPS Group | 10.5/50/p/500 | OFF |  | A/C/B | 4/5/5/-
2023-10-03 | Tuesday | 2.1 | Physics | E12-09-016 | 8.4/45/p/500 | Run Group D | 10.5/200/p/500 | NPS Group | 10.5/50/p/500 | OFF |  | A/C/B | 4/5/5/-
2023-10-04 | Wednesday | 2.1 | Physics | E12-09-016 | 8.4/45/p/500 | Run Group D | 10.5/200/p/500 | NPS Group | 10.5/50/p/500 | OFF |  | A/C/B | 4/5/5/-
2023-10-05 | Thursday | 2.1 | Physics | E12-09-016 | 8.4/45/p/500 | Run Group D | 10.5/200/p/500 | NPS Group | 10.5/50/p/500 | OFF |  | A/C/B | 4/5/5/-
2023-10-06 | Friday | 2.1 | Physics | E12-09-016 | 8.4/45/p/500 | Run Group D | 10.5/200/p/500 | NPS Group | 10.5/50/p/500 | OFF |  | A/C/B | 4/5/5/-
2023-10-07 | Saturday | 2.1 | Physics | E12-09-016 | 8.4/45/p/500 | Run Group D | 10.5/200/p/500 | NPS Group | 10.5/50/p/500 | OFF |  | A/C/B | 4/5/5/-
2023-10-08 | Sunday | 2.1 | Physics | E12-09-016 | 8.4/45/p/500 | Run Group D | 10.5/200/p/500 | NPS Group | 10.5/50/p/500 | OFF |  | A/C/B | 4/5/5/-
2023-10-09 | Monday | 2.1 | Physics | E12-09-016 | 8.4/45/p/500 | Run Group D | 10.5/200/p/500 | NPS Group | 10.5/50/p/500 | OFF |  | B/A/C | 4/5/5/-
2023-10-10 | Tuesday | 2.1 | Physics | E12-09-016 | 8.4/45/p/500 | Run Group D | 10.5/200/p/500 | NPS Group | 10.5/50/p/500 | OFF |  | B/A/C | 4/5/5/-
2023-10-11 | Wednesday | 2.1 | Physics | E12-09-016 | 8.4/45/p/500 | Run Group D | 10.5/200/p/500 | NPS Group | 10.5/50/p/500 | OFF |  | B/A/C | 4/5/5/-
2023-10-12 | Thursday | 2.1 | Physics | E12-09-016 | 8.4/45/p/500 | Run Group D | 10.5/200/p/500 | NPS Group | 10.5/50/p/500 | OFF |  | B/A/C | 4/5/5/-
2023-10-13 | Friday | 2.1 | Physics | E12-09-016 | 8.4/45/p/500 | Run Group D | 10.5/200/p/500 | NPS Group | 10.5/50/p/500 | OFF |  | B/A/C | 4/5/5/-
2023-10-14 | Saturday | 2.1 | Physics | E12-09-016 | 8.4/45/p/500 | Run Group D | 10.5/200/p/500 | NPS Group | 10.5/50/p/500 | OFF |  | B/A/C | 4/5/5/-
2023-10-15 | Sunday | 2.1 | Physics | E12-09-016 | 8.4/45/p/500 | Run Group D | 10.5/200/p/500 | NPS Group | 10.5/50/p/500 | OFF |  | B/A/C | 4/5/5/-
2023-10-16 | Monday | 2.1 | Physics | E12-09-016 | 8.4/45/p/500 | Run Group D | 10.5/200/p/500 | NPS Group | 10.5/50/p/500 | OFF |  | B/A/C | 4/5/5/-
2023-10-17 | Tuesday | 2.1 | Physics | E12-09-016 | 8.4/45/p/500 | Run Group D | 10.5/200/p/500 | NPS Group | 10.5/50/p/500 | OFF |  | C/B/A | 4/5/5/-
2023-10-18 | Wednesday | 2.1 | Physics | E12-09-016 | 8.4/45/p/500 | Run Group D | 10.5/200/p/500 | NPS Group | 10.5/50/p/500 | OFF |  | C/B/A | 4/5/5/-
2023-10-19 | Thursday | 2.1 | Physics | E12-09-016 | 8.4/45/p/500 | Run Group D | 10.5/200/p/500 | NPS Group | 10.5/50/p/500 | OFF |  | C/B/A | 4/5/5/-
2023-10-20 | Friday | 2.1 | Physics | E12-09-016 | 8.4/45/p/500 | Run Group D | 10.5/200/p/500 | NPS Group | 10.5/50/p/500 | OFF |  | A/B/C | 4/5/5/-
2023-10-21 | Saturday | 2.1 | Physics | E12-09-016 | 8.4/45/p/500 | Run Group D | 10.5/200/p/500 | NPS Group | 10.5/50/p/500 | OFF |  | A/B/C | 4/5/5/-
2023-10-22 | Sunday | 2.1 | Physics | E12-09-016 | 8.4/45/p/500 | Run Group D | 10.5/200/p/500 | NPS Group | 10.5/50/p/500 | OFF |  | A/B/C | 4/5/5/-
2023-10-23 | Monday | 2.1 | Physics | E12-09-016 | 8.4/45/p/500 | Run Group D | 10.5/200/p/500 | NPS Group | 10.5/50/p/500 | OFF |  | A/B/C | 4/5/5/-
2023-10-24 | Tuesday | 2.1 | Physics | E12-09-016 | 8.4/45/p/500 | Run Group D | 10.5/200/p/500 | NPS Group | 10.5/50/p/500 | OFF |  | B/C | 4/5/5/-
2023-10-25 | Wednesday | 2.1 | Physics | E12-09-016 | 8.4/45/p/500 | Run Group D | 10.5/200/p/500 | NPS Group | 10.5/50/p/500 | OFF |  | B/C | 4/5/5/-
2023-10-26 | Thursday | 2.1 | Physics | E12-09-016 | 8.4/45/p/500 | Run Group D | 10.5/200/p/500 | NPS Group | 10.5/50/p/500 | OFF |  | B/C | 4/5/5/-
2023-10-27 | Friday | 2.1 | Physics | E12-09-016 | 8.4/45/p/500 | Run Group D | 10.5/200/p/500 | NPS Group | 10.5/50/p/500 | OFF |  | A/B/C | 4/5/5/-
2023-10-28 | Saturday | 2.1 | Physics | E12-09-016 | 8.4/45/p/500 | Run Group D | 10.5/200/p/500 | NPS Group | 10.5/50/p/500 | OFF |  | A/B/C | 4/5/5/-
2023-10-29 | Sunday | 2.1 | Physics | E12-09-016 | 8.4/45/p/500 | Run Group D | 10.5/200/p/500 | NPS Group | 10.5/50/p/500 | OFF |  | A/B/C | 4/5/5/-
2023-10-30 | Monday | 2.1 | Physics | E12-09-016 | 8.4/45/p/500 | Run Group D | 10.5/200/p/500 | NPS Group | 10.5/50/p/500 | OFF |  | A/B/C | 4/5/5/-
2023-10-31 | Tuesday | 2.1 | Physics | Reconfigure |  | Run Group D | 10.5/200/p/500 | NPS Group | 10.5/50/p/500 | OFF |  | A/B/C | -/5/5/-
2023-11-01 | Wednesday | 2.1 | Physics | Reconfigure |  | Run Group D | 10.5/200/p/500 | NPS Group | 10.5/50/p/500 | OFF |  | A/B/C | -/5/5/-
2023-11-02 | Thursday | 2.1 | Physics | Reconfigure |  | Run Group D | 10.5/200/p/500 | NPS Group | 10.5/50/p/500 | OFF |  | A/B/C | -/5/5/-
2023-11-03 | Friday | 2.1 | Physics | Off |  | Run Group D | 10.5/200/p/500 | NPS Group | 10.5/50/p/500 | OFF |  | A/B/C | 3/5/5/-
2023-11-04 | Saturday | 2.1 | Physics | Off |  | Run Group D | 10.5/200/p/500 | NPS Group | 10.5/50/p/500 | OFF |  | A/B/C | 3/5/5/-
2023-11-05 | Sunday | 2.1 | Physics | Off |  | Run Group D | 10.5/200/p/500 | NPS Group | 10.5/50/p/500 | OFF |  | A/B/C | 3/5/5/-
2023-11-06 | Monday | 2.1 | Physics | Off |  | Run Group D | 10.5/200/p/500 | NPS Group | 10.5/50/p/500 | OFF |  | C/B | 3/5/5/-
2023-11-07 | Tuesday | 2.1 | Physics | Off |  | Run Group D | 10.5/200/p/500 | NPS Group | 10.5/50/p/500 | OFF |  | C/B | 3/5/5/-
2023-11-08 | Wednesday | 2.1 | Physics | Off |  | Run Group D | 10.5/200/p/500 | NPS Group | 10.5/50/p/500 | OFF |  | B/C | 3/5/5/-
2023-11-09 | Thursday | 2.1 | Physics | Off |  | Run Group D | 10.5/200/p/500 | NPS Group | 10.5/50/p/500 | OFF |  | B/C | 3/5/5/-
2023-11-10 | Friday | 2.1 | Physics | Off |  | Run Group D | 10.5/200/p/500 | NPS Group | 10.5/50/p/500 | OFF |  | B/C | 3/5/5/-
2023-11-11 | Saturday | 2.1 | Physics | Off |  | Run Group D | 10.5/200/p/500 | NPS Group | 10.5/50/p/500 | OFF |  | B/C | 3/5/5/-
2023-11-12 | Sunday | 2.1 | Physics | Off |  | Run Group D | 10.5/200/p/500 | NPS Group | 10.5/50/p/500 | OFF |  | B/C | 3/5/5/-
2023-11-13 | Monday | 2.1 | Physics | Off |  | Run Group D | 10.5/200/p/500 | Pass change |  | OFF |  | B/C | -/5/4/2
2023-11-14 | Tuesday | 2.1 | Physics | Off |  | Run Group D | 10.5/200/p/500 | NPS Group | 8.4/50/p/500 | OFF |  | B/C | -/5/4/2
2023-11-15 | Wednesday | 2.1 | Physics | Off |  | Run Group D | 10.5/200/p/500 | NPS Group | 8.4/50/p/500 | OFF |  | C/B | -/5/4/-
2023-11-16 | Thursday | 2.1 | Physics | Off |  | Run Group D | 10.5/200/p/500 | NPS Group | 8.4/50/p/500 | OFF |  | C/B | -/5/4/-
2023-11-17 | Friday | 2.1 | Physics | Off |  | Run Group D | 10.5/200/p/500 | NPS Group | 8.4/50/p/500 | OFF |  | C/B | -/5/4/-
2023-11-18 | Saturday | 2.1 | Physics | Off |  | Run Group D | 10.5/200/p/500 | NPS Group | 8.4/50/p/500 | OFF |  | C/B | -/5/4/-
2023-11-19 | Sunday | 2.1 | Physics | Off |  | Run Group D | 10.5/200/p/500 | NPS Group | 8.4/50/p/500 | OFF |  | C/B | -/5/4/-
2023-11-20 | Monday | 2.1 | Physics | Off |  | Run Group D | 10.5/200/p/500 | NPS Group | 8.4/50/p/500 | OFF |  | B/C | -/5/4/-
2023-11-21 | Tuesday | 2.1 | Physics | Off |  | Run Group D | 10.5/200/p/500 | NPS Group | 8.4/50/p/500 | OFF |  | B/C | -/5/4/-
2023-11-22 | Wednesday | 2.1 | Physics | Off |  | Run Group D | 10.5/200/p/500 | NPS Group | 8.4/50/p/500 | OFF |  | B/C | -/5/4/-
2023-11-23 | Thursday | 2.1 | Physics | Off |  | Run Group D | 10.5/200/p/500 | NPS Group | 8.4/50/p/500 | OFF |  | B/C | -/5/4/-
2023-11-24 | Friday | 2.1 | Physics | Off |  | Run Group D | 10.5/200/p/500 | NPS Group | 8.4/50/p/500 | OFF |  | B/C | -/5/4/-
2023-11-25 | Saturday | 2.1 | Physics | Off |  | Run Group D | 10.5/200/p/500 | NPS Group | 8.4/50/p/500 | OFF |  | B/C | -/5/4/-
2023-11-26 | Sunday | 2.1 | Physics | Off |  | Run Group D | 10.5/200/p/500 | NPS Group | 8.4/50/p/500 | OFF |  | B/C | -/5/4/-
2023-11-27 | Monday | 2.1 | Physics | Off |  | Run Group D | 10.5/200/p/500 | NPS Group | 8.4/50/p/500 | OFF |  | C/B | -/5/4/-
2023-11-28 | Tuesday | 2.1 | Physics | Off |  | Run Group D | 10.5/200/p/500 | NPS Group | 8.4/50/p/500 | OFF |  | C/B | -/5/4/-
2023-11-29 | Wednesday | 2.1 | Physics | Off |  | Run Group D | 10.5/200/p/500 | NPS Group | 8.4/50/p/500 | OFF |  | C/B | -/5/4/-
2023-11-30 | Thursday | 2.1 | Physics | Off |  | Run Group D | 10.5/200/p/500 | NPS Group | 8.4/50/p/500 | OFF |  | C/B | -/5/4/-
2023-12-01 | Friday | 2.1 | Physics | Off |  | Run Group D | 10.5/200/p/500 | NPS Group | 8.4/50/p/500 | OFF |  | C/B | -/5/4/-
2023-12-02 | Saturday | 2.1 | Physics | Off |  | Run Group D | 10.5/200/p/500 | NPS Group | 8.4/50/p/500 | OFF |  | C/B | -/5/4/-
2023-12-03 | Sunday | 2.1 | Physics | Off |  | Run Group D | 10.5/200/p/500 | NPS Group | 8.4/50/p/500 | OFF |  | C/B | -/5/4/-
2023-12-04 | Monday | 2.1 | Physics | Install |  | Run Group D | 10.5/200/p/500 | NPS Group | 8.4/50/p/500 | OFF |  | B/C | -/5/4/-
2023-12-05 | Tuesday | 2.1 | Physics | Install |  | Run Group D | 10.5/200/p/500 | NPS Group | 8.4/50/p/500 | OFF |  | B/C | -/5/4/-
2023-12-06 | Wednesday | 2.1 | Physics | Install |  | Run Group D | 10.5/200/p/500 | NPS Group | 8.4/50/p/500 | OFF |  | B/C | -/5/4/-
2023-12-07 | Thursday | 2.1 | Physics | Install |  | Run Group D | 10.5/200/p/500 | NPS Group | 8.4/50/p/500 | OFF |  | B/C | -/5/4/-
2023-12-08 | Friday | 2.1 | Physics | Install |  | Run Group D | 10.5/200/p/500 | NPS Group | 8.4/50/p/500 | OFF |  | B/C | -/5/4/-
2023-12-09 | Saturday | 2.1 | Physics | Install |  | Run Group D | 10.5/200/p/500 | NPS Group | 8.4/50/p/500 | OFF |  | B/C | -/5/4/-
2023-12-10 | Sunday | 2.1 | Physics | Install |  | Run Group D | 10.5/200/p/500 | NPS Group | 8.4/50/p/500 | OFF |  | B/C | -/5/4/-
2023-12-11 | Monday | 2.1 | Physics | Install |  | Run Group D | 10.5/200/p/500 | NPS Group | 8.4/50/p/500 | OFF |  | C/B | -/5/4/-
2023-12-12 | Tuesday | 2.1 | Physics | Install |  | Run Group D | 10.5/200/p/500 | NPS Group | 8.4/50/p/500 | OFF |  | C/B | -/5/4/-
2023-12-13 | Wednesday | 2.1 | Physics | Install |  | Run Group D | 10.5/200/p/500 | NPS Group | 8.4/50/p/500 | OFF |  | C/B | -/5/4/-
2023-12-14 | Thursday | 2.1 | Physics | Install |  | Run Group D | 10.5/200/p/500 | NPS Group | 8.4/50/p/500 | OFF |  | C/B | -/5/4/-
2023-12-15 | Friday | 2.1 | Physics | Install |  | Pass change |  | NPS Group | 8.4/50/p/500 | OFF |  | C/B | -/3/4/-
2023-12-16 | Saturday | 2.1 | Physics | Install |  | Run Group K | 6.4/200/p/500 | NPS Group | 8.4/50/p/500 | OFF |  | C/B | -/3/4/-
2023-12-17 | Sunday | 2.1 | Physics | Install |  | Run Group K | 6.4/200/p/500 | NPS Group | 8.4/50/p/500 | OFF |  | C/B | -/3/4/-
2023-12-18 | Monday | 2.1 | Physics | Install |  | Run Group K | 6.4/200/p/500 | NPS Group | 8.4/50/p/500 | OFF |  | C/B | -/3/4/-
2023-12-19 | Tuesday | 2.1 | Physics | Install |  | Run Group K | 6.4/200/p/500 | NPS Group | 8.4/50/p/500 | OFF |  | C/B | -/3/4/-
2023-12-20 | Wednesday
2023-12-21 | Thursday
2023-12-22 | Friday
2023-12-23 | Saturday
2023-12-24 | Sunday
2023-12-25 | Monday
2023-12-26 | Tuesday
2023-12-27 | Wednesday
2023-12-28 | Thursday
2023-12-29 | Friday
2023-12-30 | Saturday
2023-12-31 | Sunday
2024-01-01 | Monday
2024-01-02 | Tuesday
2024-01-03 | Wednesday
2024-01-04 | Thursday
2024-01-05 | Friday
2024-01-06 | Saturday |  | Restore
2024-01-07 | Sunday |  | Restore
2024-01-08 | Monday |  | Restore
2024-01-09 | Tuesday |  | Restore
2024-01-10 | Wednesday | 2.1 | Physics | Install |  | Run Group K | 6.4/200/p/500 |  |  | OFF |  | B | -/3/5/-
2024-01-11 | Thursday | 2.1 | Physics | Install |  | Run Group K | 6.4/200/p/500 |  |  | OFF |  | B | -/3/5/-
2024-01-12 | Friday | 2.1 | Physics | Install |  | Run Group K | 6.4/200/p/500 |  |  | OFF |  | B | -/3/5/-
2024-01-13 | Saturday | 2.1 | Physics | Install |  | Run Group K | 6.4/200/p/500 |  |  | OFF |  | B | -/3/5/-
2024-01-14 | Sunday | 2.1 | Physics | Install |  | Run Group K | 6.4/200/p/500 |  |  | OFF |  | B | -/3/5/-
2024-01-15 | Monday | 2.1 | Physics | Install |  | Run Group K | 6.4/200/p/500 |  |  | OFF |  | B | -/3/5/-
2024-01-16 | Tuesday | 2.1 | Physics | Install |  | Run Group K | 6.4/200/p/500 |  |  | OFF |  | B | -/3/5/-
2024-01-17 | Wednesday | 2.1 | Physics | Install |  | Run Group K | 6.4/200/p/500 |  |  | OFF |  | B | -/3/5/-
2024-01-18 | Thursday | 2.1 | Physics | Install |  | Run Group K | 6.4/200/p/500 |  |  | OFF |  | B | -/3/5/-
2024-01-19 | Friday | 2.1 | Physics | Install |  | Run Group K | 6.4/200/p/500 |  |  | OFF |  | B | -/3/5/-
2024-01-20 | Saturday | 2.1 | Physics | Install |  | Run Group K | 6.4/200/p/500 |  |  | OFF |  | B | -/3/5/-
2024-01-21 | Sunday | 2.1 | Physics | Install |  | Run Group K | 6.4/200/p/500 |  |  | OFF |  | B | -/3/5/-
2024-01-22 | Monday | 2.1 | Physics | Install |  | Run Group K | 6.4/200/p/500 | NPS Group | 10.5/50/p/500 | OFF |  | C | -/3/5/-
2024-01-23 | Tuesday | 2.1 | Physics | Install |  | Run Group K | 6.4/200/p/500 | NPS Group | 10.5/50/p/500 | OFF |  | C | -/3/5/-
2024-01-24 | Wednesday | 2.1 | Physics | Install |  | Run Group K | 6.4/200/p/500 | NPS Group | 10.5/50/p/500 | OFF |  | C | -/3/5/-
2024-01-25 | Thursday | 2.1 | Physics | Install |  | Run Group K | 6.4/200/p/500 | NPS Group | 10.5/50/p/500 | OFF |  | C | -/3/5/-
2024-01-26 | Friday | 2.1 | Physics | Install |  | Run Group K | 6.4/200/p/500 | NPS Group | 10.5/50/p/500 | OFF |  | C | -/3/5/-
2024-01-27 | Saturday | 2.1 | Physics | Install |  | Run Group K | 6.4/200/p/500 | NPS Group | 10.5/50/p/500 | OFF |  | C | -/3/5/-
2024-01-28 | Sunday | 2.1 | Physics | Install |  | Run Group K | 6.4/200/p/500 | NPS Group | 10.5/50/p/500 | OFF |  | C | -/3/5/-
2024-01-29 | Monday | 2.1 | Physics | Install |  | Run Group K | 6.4/200/p/500 | NPS Group | 10.5/50/p/500 | OFF |  | B | -/3/5/-
2024-01-30 | Tuesday | 2.1 | Physics | Install |  | Run Group K | 6.4/200/p/500 | NPS Group | 10.5/50/p/500 | OFF |  | B | -/3/5/-
2024-01-31 | Wednesday | 2.1 | Physics | Install |  | Run Group K | 6.4/200/p/500 | NPS Group | 10.5/50/p/500 | OFF |  | B | -/3/5/-
2024-02-01 | Thursday | 2.1 | Physics | Install |  | Run Group K | 6.4/200/p/500 | NPS Group | 10.5/50/p/500 | OFF |  | B | -/3/5/-
2024-02-02 | Friday | 2.1 | Physics | Install |  | Run Group K | 6.4/200/p/500 | NPS Group | 10.5/50/p/500 | OFF |  | B | -/3/5/-
2024-02-03 | Saturday | 2.1 | Physics | Install |  | Run Group K | 6.4/200/p/500 | NPS Group | 10.5/50/p/500 | OFF |  | B | -/3/5/-
2024-02-04 | Sunday | 2.1 | Physics | Install |  | Run Group K | 6.4/200/p/500 | NPS Group | 10.5/50/p/500 | OFF |  | B | -/3/5/-
2024-02-05 | Monday | 2.1 | Physics | Install |  | Run Group K | 6.4/200/p/500 | NPS Group | 10.5/50/p/500 | OFF |  | C | -/3/5/-
2024-02-06 | Tuesday | 2.1 | Physics | Install |  | Run Group K | 6.4/200/p/500 | NPS Group | 10.5/50/p/500 | OFF |  | C | -/3/5/-
2024-02-07 | Wednesday | 2.1 | Physics | Install |  | Run Group K | 6.4/200/p/500 | NPS Group | 10.5/50/p/500 | OFF |  | C | -/3/5/-
2024-02-08 | Thursday | 2.1 | Physics | Install |  | Run Group K | 6.4/200/p/500 | NPS Group | 10.5/50/p/500 | OFF |  | C | -/3/5/-
2024-02-09 | Friday | 2.1 | Physics | Install |  | Run Group K | 6.4/200/p/500 | NPS Group | 10.5/50/p/500 | OFF |  | C | -/3/5/-
2024-02-10 | Saturday | 2.1 | Physics | Install |  | Run Group K | 6.4/200/p/500 | NPS Group | 10.5/50/p/500 | OFF |  | C | -/3/5/-
2024-02-11 | Sunday | 2.1 | Physics | Install |  | Run Group K | 6.4/200/p/500 | NPS Group | 10.5/50/p/500 | OFF |  | C | -/3/5/-
2024-02-12 | Monday | 2.1 | Physics | Install |  | Run Group K | 6.4/200/p/500 | NPS Group | 10.5/50/p/500 | OFF |  | B | -/3/5/-
2024-02-13 | Tuesday | 2.1 | Physics | Install |  | Pass change |  | NPS Group | 10.5/50/p/500 | OFF |  | B | -/4/5/-
2024-02-14 | Wednesday | 2.1 | Physics | Install |  | Run Group K | 8.4/200/p/500 | NPS Group | 10.5/50/p/500 | OFF |  | B | -/4/5/-
2024-02-15 | Thursday | 2.1 | Physics | Install |  | Run Group K | 8.4/200/p/500 | NPS Group | 10.5/50/p/500 | OFF |  | B | -/4/5/-
2024-02-16 | Friday | 2.1 | Physics | Install |  | Run Group K | 8.4/200/p/500 | NPS Group | 10.5/50/p/500 | OFF |  | B | -/4/5/-
2024-02-17 | Saturday | 2.1 | Physics | Install |  | Run Group K | 8.4/200/p/500 | NPS Group | 10.5/50/p/500 | OFF |  | B | -/4/5/-
2024-02-18 | Sunday | 2.1 | Physics | Install |  | Run Group K | 8.4/200/p/500 | NPS Group | 10.5/50/p/500 | OFF |  | B | -/4/5/-
2024-02-19 | Monday | 2.1 | Physics | Install |  | Run Group K | 8.4/200/p/500 | NPS Group | 10.5/50/p/500 | OFF |  | C | -/4/5/-
2024-02-20 | Tuesday | 2.1 | Physics | Install |  | Run Group K | 8.4/200/p/500 | NPS Group | 10.5/50/p/500 | OFF |  | C | -/4/5/-
2024-02-21 | Wednesday | 2.1 | Physics | Install |  | Run Group K | 8.4/200/p/500 | NPS Group | 10.5/50/p/500 | OFF |  | C | -/4/5/-
2024-02-22 | Thursday | 2.1 | Physics | Install |  | Run Group K | 8.4/200/p/500 | NPS Group | 10.5/50/p/500 | OFF |  | C | -/4/5/-
2024-02-23 | Friday | 2.1 | Physics | Install |  | Run Group K | 8.4/200/p/500 | NPS Group | 10.5/50/p/500 | OFF |  | C | -/4/5/-
2024-02-24 | Saturday | 2.1 | Physics | Install |  | Run Group K | 8.4/200/p/500 | NPS Group | 10.5/50/p/500 | OFF |  | C | -/4/5/-
2024-02-25 | Sunday | 2.1 | Physics | Install |  | Run Group K | 8.4/200/p/500 | NPS Group | 10.5/50/p/500 | OFF |  | C | -/4/5/-
2024-02-26 | Monday | 2.1 | Physics | Install |  | Run Group K | 8.4/200/p/500 | NPS Group | 10.5/50/p/500 | OFF |  | B | -/4/5/-
2024-02-27 | Tuesday | 2.1 | Physics | Install |  | Run Group K | 8.4/200/p/500 | NPS Group | 10.5/50/p/500 | OFF |  | B | -/4/5/-
2024-02-28 | Wednesday | 2.1 | Physics | Install |  | Run Group K | 8.4/200/p/500 | NPS Group | 10.5/50/p/500 | OFF |  | B | -/4/5/-
2024-02-29 | Thursday | 2.1 | Physics | Install |  | Run Group K | 8.4/200/p/500 | NPS Group | 10.5/50/p/500 | OFF |  | B | -/4/5/-
2024-03-01 | Friday | 2.1 | Physics | Install |  | Run Group K | 8.4/200/p/500 | NPS Group | 10.5/50/p/500 | OFF |  | B | -/4/5/-
2024-03-02 | Saturday | 2.1 | Physics | Install |  | Run Group K | 8.4/200/p/500 | NPS Group | 10.5/50/p/500 | OFF |  | B | -/4/5/-
2024-03-03 | Sunday | 2.1 | Physics | Install |  | Run Group K | 8.4/200/p/500 | NPS Group | 10.5/50/p/500 | OFF |  | B | -/4/5/-
2024-03-04 | Monday | 2.1 | Physics | Install |  | Run Group K | 8.4/200/p/500 | NPS Group | 10.5/50/p/500 | OFF |  | B | -/4/5/-
2024-03-05 | Tuesday | 2.1 | Physics | Install |  | Run Group K | 8.4/200/p/500 | NPS Group | 10.5/50/p/500 | OFF |  | B | -/4/5/-
2024-03-06 | Wednesday | 2.1 | Physics | Install |  | Run Group K | 8.4/200/p/500 | NPS Group | 10.5/50/p/500 | OFF |  | B | -/4/5/-
2024-03-07 | Thursday | 2.1 | Physics | Install |  | Run Group K | 8.4/200/p/500 | NPS Group | 10.5/50/p/500 | OFF |  | B | -/4/5/-
2024-03-08 | Friday | 2.1 | Physics | Install |  | Run Group K | 8.4/200/p/500 | NPS Group | 10.5/50/p/500 | OFF |  | B | -/4/5/-
2024-03-09 | Saturday | 2.1 | Physics | Install |  | Run Group K | 8.4/200/p/500 | NPS Group | 10.5/50/p/500 | OFF |  | B | -/4/5/-
2024-03-10 | Sunday | 2.1 | Physics | Install |  | Run Group K | 8.4/200/p/500 | NPS Group | 10.5/50/p/500 | OFF |  | B | -/4/5/-
2024-03-11 | Monday | 2.1 | Physics | Install |  | Reconfigure |  | Pass change |  | GlueX Test | 11.6/200/-/500 | C | -/-/4/5.5
2024-03-12 | Tuesday | 2.1 | Physics | Install |  | Reconfigure |  | NPS Group | 6.3/50/p/500 | GlueX Test | 11.6/200/-/500 | C | -/-/4/5.5
2024-03-13 | Wednesday | 2.1 | Physics | Install |  | Reconfigure |  | NPS Group | 6.3/50/p/500 | GlueX Test | 11.6/200/-/500 | C | -/-/4/5.5
2024-03-14 | Thursday | 2.1 | Physics | Install |  | Reconfigure |  | NPS Group | 6.3/50/p/500 | GlueX Test | 11.6/200/-/500 | C | -/-/4/5.5
2024-03-15 | Friday | 2.1 | Physics | Install |  | Run Group E | 10.5/200/-/500 | NPS Group | 6.3/50/p/500 | OFF |  | C | -/-/4/5.5
2024-03-16 | Saturday | 2.1 | Physics | Install |  | Run Group E | 10.5/200/-/500 | NPS Group | 6.3/50/p/500 | OFF |  | C | -/-/4/5.5
2024-03-17 | Sunday | 2.1 | Physics | Install |  | Run Group E | 10.5/200/-/500 | NPS Group | 6.3/50/p/500 | OFF |  | C | -/-/4/5.5
2024-03-18 | Monday | 2.1 | Physics | Install |  | Run Group E | 10.5/200/-/500 | NPS Group | 6.3/50/p/500 | OFF |  | C | -/-/4/5.5
2024-03-19 | Tuesday | 2.1 | Physics | Install |  | Run Group E | 10.5/200/-/500 | NPS Group | 6.3/50/p/500 | OFF |  | C | -/-/4/5.5
2024-03-20 | Wednesday | 2.1 | Physics | Install |  | Run Group E | 10.5/200/-/500 | NPS Group | 6.3/50/p/500 | OFF |  | B | -/-/4/5.5
2024-03-21 | Thursday | 2.1 | Physics | Install |  | Run Group E | 10.5/200/-/500 | NPS Group | 6.3/50/p/500 | OFF |  | B | -/-/4/5.5
2024-03-22 | Friday | 2.1 | Physics | Install |  | Run Group E | 10.5/200/-/500 | NPS Group | 6.3/50/p/500 | OFF |  | B | -/-/4/5.5
2024-03-23 | Saturday | 2.1 | Physics | Install |  | Run Group E | 10.5/200/-/500 | NPS Group | 6.3/50/p/500 | OFF |  | B | -/-/4/5.5
2024-03-24 | Sunday | 2.1 | Physics | Install |  | Run Group E | 10.5/200/-/500 | NPS Group | 6.3/50/p/500 | OFF |  | B | -/-/4/5.5
2024-03-25 | Monday | 2.1 | Physics | Install |  | Run Group E | 10.5/200/-/500 | NPS Group | 6.3/50/p/500 | OFF |  | B | -/-/4/5.5
2024-03-26 | Tuesday | 2.1 | Physics | Install |  | Run Group E | 10.5/200/-/500 | NPS Group | 6.3/50/p/500 | OFF |  | B | -/-/4/5.5
2024-03-27 | Wednesday | 2.1 | Physics | Install |  | Run Group E | 10.5/200/-/500 | NPS Group | 6.3/50/p/500 | OFF |  | C | -/-/4/5.5
2024-03-28 | Thursday | 2.1 | Physics | Install |  | Run Group E | 10.5/200/-/500 | NPS Group | 6.3/50/p/500 | OFF |  | C | -/-/4/5.5
2024-03-29 | Friday | 2.1 | Physics | Install |  | Run Group E | 10.5/200/-/500 | NPS Group | 6.3/50/p/500 | OFF |  | C | -/-/4/5.5
2024-03-30 | Saturday | 2.1 | Physics | Install |  | Run Group E | 10.5/200/-/500 | NPS Group | 6.3/50/p/500 | OFF |  | C | -/-/4/5.5
2024-03-31 | Sunday | 2.1 | Physics | Install |  | Run Group E | 10.5/200/-/500 | NPS Group | 6.3/50/p/500 | OFF |  | C | -/-/4/5.5
2024-04-01 | Monday | 2.1 | Physics | Install |  | Run Group E | 10.5/200/-/500 | NPS Group | 6.3/50/p/500 | OFF |  | C | -/-/4/5.5
2024-04-02 | Tuesday | 2.1 | Physics | Install |  | Run Group E | 10.5/200/-/500 | NPS Group | 6.3/50/p/500 | OFF |  | C | -/-/4/5.5
2024-04-03 | Wednesday | 2.1 | Physics | Install |  | Run Group E | 10.5/200/-/500 | NPS Group | 6.3/50/p/500 | OFF |  | C | -/-/4/5.5
2024-04-04 | Thursday | 2.1 | Physics | Install |  | Run Group E | 10.5/200/-/500 | NPS Group | 6.3/50/p/500 | OFF |  | C | -/-/4/5.5
2024-04-05 | Friday | 2.1 | Physics | E12-17-004 | 4.3/40/p/500 | Run Group E | 10.5/200/-/500 | Pass change |  | OFF |  | A | 2/5/4/-
2024-04-06 | Saturday | 2.1 | Physics | E12-17-004 | 4.3/40/p/500 | Run Group E | 10.5/200/-/500 | NPS Group | 8.4/50/p/500 | OFF |  | A | 2/5/4/-
2024-04-07 | Sunday | 2.1 | Physics | E12-17-004 | 4.3/40/p/500 | Run Group E | 10.5/200/-/500 | NPS Group | 8.4/50/p/500 | OFF |  | A | 2/5/4/-
2024-04-08 | Monday | 2.1 | Physics | E12-17-004 | 4.3/40/p/500 | Run Group E | 10.5/200/-/500 | NPS Group | 8.4/50/p/500 | OFF |  | A | 2/5/4/-
2024-04-09 | Tuesday | 2.1 | Physics | E12-17-004 | 4.3/40/p/500 | Run Group E | 10.5/200/-/500 | NPS Group | 8.4/50/p/500 | OFF |  | A | 2/5/4/-
2024-04-10 | Wednesday | 2.1 | Physics | E12-17-004 | 4.3/40/p/500 | Run Group E | 10.5/200/-/500 | NPS Group | 8.4/50/p/500 | OFF |  | A | 2/5/4/-
2024-04-11 | Thursday | 2.1 | Physics | E12-17-004 | 4.3/40/p/500 | Run Group E | 10.5/200/-/500 | NPS Group | 8.4/50/p/500 | OFF |  | A | 2/5/4/-
2024-04-12 | Friday | 2.1 | Physics | E12-17-004 | 4.3/40/p/500 | Run Group E | 10.5/200/-/500 | NPS Group | 8.4/50/p/500 | OFF |  | A | 2/5/4/-
2024-04-13 | Saturday | 2.1 | Physics | E12-17-004 | 4.3/40/p/500 | Run Group E | 10.5/200/-/500 | NPS Group | 8.4/50/p/500 | OFF |  | A | 2/5/4/-
2024-04-14 | Sunday | 2.1 | Physics | E12-17-004 | 4.3/40/p/500 | Run Group E | 10.5/200/-/500 | NPS Group | 8.4/50/p/500 | OFF |  | A | 2/5/4/-
2024-04-15 | Monday | 2.1 | Physics | E12-17-004 | 4.3/40/p/500 | Run Group E | 10.5/200/-/500 | NPS Group | 8.4/50/p/500 | OFF |  | A | 2/5/4/-
2024-04-16 | Tuesday | 2.1 | Physics | E12-17-004 | 4.3/40/p/500 | Run Group E | 10.5/200/-/500 | NPS Group | 8.4/50/p/500 | OFF |  | A | 2/5/4/-
2024-04-17 | Wednesday | 2.1 | Physics | E12-17-004 | 4.3/40/p/500 | Run Group E | 10.5/200/-/500 | NPS Group | 8.4/50/p/500 | OFF |  | A | 2/5/4/-
2024-04-18 | Thursday | 2.1 | Physics | E12-17-004 | 4.3/40/p/500 | Run Group E | 10.5/200/-/500 | NPS Group | 8.4/50/p/500 | OFF |  | A | 2/5/4/-
2024-04-19 | Friday | 2.1 | Physics | E12-17-004 | 4.3/40/p/500 | Run Group E | 10.5/200/-/500 | NPS Group | 8.4/50/p/500 | OFF |  | A | 2/5/4/-
2024-04-20 | Saturday | 2.1 | Physics | E12-17-004 | 4.3/40/p/500 | Run Group E | 10.5/200/-/500 | NPS Group | 8.4/50/p/500 | OFF |  | A | 2/5/4/-
2024-04-21 | Sunday | 2.1 | Physics | E12-17-004 | 4.3/40/p/500 | Run Group E | 10.5/200/-/500 | NPS Group | 8.4/50/p/500 | OFF |  | A | 2/5/4/-
2024-04-22 | Monday | 2.1 | Physics | E12-17-004 | 4.3/40/p/500 | Run Group E | 10.5/200/-/500 | NPS Group | 8.4/50/p/500 | OFF |  | A | 2/5/4/-
2024-04-23 | Tuesday | 2.1 | Physics | E12-17-004 | 4.3/40/p/500 | Run Group E | 10.5/200/-/500 | NPS Group | 8.4/50/p/500 | OFF |  | A | 2/5/4/-
2024-04-24 | Wednesday | 2.1 | Physics | E12-17-004 | 4.3/40/p/500 | Run Group E | 10.5/200/-/500 | NPS Group | 8.4/50/p/500 | OFF |  | A | 2/5/4/-
2024-04-25 | Thursday | 2.1 | Physics | E12-17-004 | 4.3/40/p/500 | Run Group E | 10.5/200/-/500 | NPS Group | 8.4/50/p/500 | OFF |  | A | 2/5/4/-
2024-04-26 | Friday | 2.1 | Physics | Commissioning | 4.3/40/p/500 | Run Group E | 10.5/200/-/500 | NPS Group | 8.4/50/p/500 | OFF |  | A | 2/5/4/-
2024-04-27 | Saturday | 2.1 | Physics | Commissioning | 4.3/40/p/500 | Run Group E | 10.5/200/-/500 | NPS Group | 8.4/50/p/500 | OFF |  | A | 2/5/4/-
2024-04-28 | Sunday | 2.1 | Physics | Commissioning | 4.3/40/p/500 | Run Group E | 10.5/200/-/500 | NPS Group | 8.4/50/p/500 | OFF |  | A | 2/5/4/-
2024-04-29 | Monday | 2.1 | Physics | Pass change |  | Run Group E | 10.5/200/-/500 |  |  | OFF |  | A | 3/5/4/-
2024-04-30 | Tuesday | 2.1 | Physics | E12-20-008 | 6.4/10/p/500 | Run Group E | 10.5/200/-/500 |  |  | OFF |  | A | 3/5/4/-
2024-05-01 | Wednesday | 2.1 | Physics | E12-20-008 | 6.4/10/p/500 | Run Group E | 10.5/200/-/500 |  |  | OFF |  | B | 3/5/4/-
2024-05-02 | Thursday | 2.1 | Physics | E12-20-008 | 6.4/10/p/500 | Run Group E | 10.5/200/-/500 |  |  | OFF |  | B | 3/5/4/-
2024-05-03 | Friday | 2.1 | Physics | E12-20-008 | 6.4/10/p/500 | Run Group E | 10.5/200/-/500 |  |  | OFF |  | B | 3/5/4/-
2024-05-04 | Saturday | 2.1 | Physics | Install |  | Run Group E | 10.5/200/-/500 | Pass change |  | OFF |  | B | -/5/3/-
2024-05-05 | Sunday | 2.1 | Physics | Install |  | Run Group E | 10.5/200/-/500 | NPS Group | 6.3/50/p/500 | OFF |  | B | -/5/3/-
2024-05-06 | Monday | 2.1 | Physics | Install |  | Run Group E | 10.5/200/-/500 | NPS Group | 6.3/50/p/500 | OFF |  | B | -/5/3/-
2024-05-07 | Tuesday | 2.1 | Physics | Install |  | Run Group E | 10.5/200/-/500 | NPS Group | 6.3/50/p/500 | OFF |  | B | -/5/3/-
2024-05-08 | Wednesday | 2.1 | Physics | Install |  | Run Group E | 10.5/200/-/500 | NPS Group | 6.3/50/p/500 | OFF |  | C | -/5/3/-
2024-05-09 | Thursday | 2.1 | Physics | Install |  | Run Group E | 10.5/200/-/500 | NPS Group | 6.3/50/p/500 | OFF |  | C | -/5/3/-
2024-05-10 | Friday | 2.1 | Physics | Install |  | Run Group E | 10.5/200/-/500 | NPS Group | 6.3/50/p/500 | OFF |  | C | -/5/3/-
2024-05-11 | Saturday | 2.1 | Physics | Install |  | Run Group E | 10.5/200/-/500 | NPS Group | 6.3/50/p/500 | OFF |  | C | -/5/3/-
2024-05-12 | Sunday | 2.1 | Physics | Install |  | Run Group E | 10.5/200/-/500 | NPS Group | 6.3/50/p/500 | OFF |  | C | -/5/3/-
2024-05-13 | Monday | 2.1 | Physics | Install |  | Run Group E | 10.5/200/-/500 | NPS Group | 6.3/50/p/500 | OFF |  | C | -/5/3/-
2024-05-14 | Tuesday | 2.1 | Physics | Install |  | Run Group E | 10.5/200/-/500 | NPS Group | 6.3/50/p/500 | OFF |  | C | -/5/3/-
2024-05-15 | Wednesday | 2.1 | Physics | Install |  | Run Group E | 10.5/200/-/500 | NPS Group | 6.3/50/p/500 | OFF |  | C | -/5/3/-
2024-05-16 | Thursday | 2.1 | Physics | Install |  | Run Group E | 10.5/200/-/500 | NPS Group | 6.3/50/p/500 | OFF |  | C | -/5/3/-
2024-05-17 | Friday | 2.1 | Physics | Install |  | Run Group E | 10.5/200/-/500 | NPS Group | 6.3/50/p/500 | OFF |  | C | -/5/3/-
2024-05-18 | Saturday | 2.1 | Physics | Install |  | Run Group E | 10.5/200/-/500 | NPS Group | 6.3/50/p/500 | OFF |  | C | -/5/3/-
2024-05-19 | Sunday | 2.1 | Physics | Install |  | Run Group E | 10.5/200/-/500 | NPS Group | 6.3/50/p/500 | OFF |  | C | -/5/3/-
2024-05-20 | Monday
2024-09-01
2024-09-02
2024-09-03
2024-09-04
2024-09-05
2024-09-06 | Friday | 2.2 | Restore | Install
2024-09-07 | Saturday | 2.2 | Restore | Install
2024-09-08 | Sunday | 2.2 | Restore | Install
2024-09-09 | Monday | 2.2 | Restore | Install
2024-09-10 | Tuesday | 2.2 | Restore | Install
2024-09-11 | Wednesday | 2.2 | Restore | Install
2024-09-12 | Thursday | 2.2 | Restore | Install
2024-09-13 | Friday | 2.2 | Restore | Install
2024-09-14 | Saturday | 2.2 | Restore | Install
2024-09-15 | Sunday | 2.2 | Restore | Install
2024-09-16 | Monday | 2.2 | Restore | Install
2024-09-17 | Tuesday | 2.2 | Physics | Install | [5 empty] | GlueX 2 / JEF | 12/200/-/250 | D | -/-/-/5.5
2024-09-18 | Wednesday | 2.2 | Physics | Install |  |  |  | E12-11-107 | 6.6/10/-/250 | GlueX 2 / JEF | 12/200/-/250 | D/C | -/-/3/5.5
2024-09-19 | Thursday | 2.2 | Physics | Install |  | Run Group L | 2.2/200/p/250 | E12-11-107 | 6.6/10/-/250 | GlueX 2 / JEF | 12/200/-/250 | B/C/D | -/1/3/5.5
2024-09-20 | Friday | 2.2 | Physics | Install |  | Run Group L | 2.2/200/p/250 | E12-11-107 | 6.6/10/-/250 | GlueX 2 / JEF | 12/200/-/250 | B/C/D | -/1/3/5.5
2024-09-21 | Saturday | 2.2 | Physics | Install |  | Run Group L | 2.2/200/p/250 | E12-11-107 | 6.6/10/-/250 | GlueX 2 / JEF | 12/200/-/250 | B/C/D | -/1/3/5.5
2024-09-22 | Sunday | 2.2 | Physics | Install |  | Run Group L | 2.2/200/p/250 | E12-11-107 | 6.6/10/-/250 | GlueX 2 / JEF | 12/200/-/250 | B/C/D | -/1/3/5.5
2024-09-23 | Monday | 2.2 | Physics | Install |  | Run Group L | 2.2/200/p/250 | Target Gas Change |  | GlueX 2 / JEF | 12/200/-/250 | B/C/D | -/1/-/5.5
2024-09-24 | Tuesday | 2.2 | Physics | Install |  | Run Group L | 2.2/200/p/250 | Target Gas Change |  | GlueX 2 / JEF | 12/200/-/250 | B/C/D | -/1/-/5.5
2024-09-25 | Wednesday | 2.2 | Physics | Install |  | Pass change |  | Pass change |  | GlueX 2 / JEF | 12/200/-/250 | B/C/D | -/5/5/5.5
2024-09-26 | Thursday | 2.2 | Physics | Install |  | Run Group L | 11/200/p/250 | E12-11-107 | 11/10/-/250 | GlueX 2 / JEF | 12/200/-/250 | B/C/D | -/5/5/5.5
2024-09-27 | Friday | 2.2 | Physics | Install |  | Run Group L | 11/200/p/250 | E12-11-107 | 11/10/-/250 | GlueX 2 / JEF | 12/200/-/250 | D/B/C | -/5/5/5.5
2024-09-28 | Saturday | 2.2 | Physics | Install |  | Run Group L | 11/200/p/250 | E12-11-107 | 11/10/-/250 | GlueX 2 / JEF | 12/200/-/250 | D/B/C | -/5/5/5.5
2024-09-29 | Sunday | 2.2 | Physics | Install |  | Run Group L | 11/200/p/250 | E12-11-107 | 11/10/-/250 | GlueX 2 / JEF | 12/200/-/250 | D/B/C | -/5/5/5.5
2024-09-30 | Monday | 2.2 | Physics | Install |  | Run Group L | 11/200/p/250 | E12-11-107 | 11/10/-/250 | GlueX 2 / JEF | 12/200/-/250 | D/B/C | -/5/5/5.5
2024-10-01 | Tuesday | 2.2 | Physics | Install |  | Run Group L | 11/200/p/250 | E12-11-107 | 11/10/-/250 | GlueX 2 / JEF | 12/200/-/250 | D/B/C | -/5/5/5.5
2024-10-02 | Wednesday | 2.2 | Physics | Install |  | Run Group L | 11/200/p/250 | E12-11-107 | 11/10/-/250 | GlueX 2 / JEF | 12/200/-/250 | D/B/C | -/5/5/5.5
2024-10-03 | Thursday | 2.2 | Physics | Install |  | Run Group L | 11/200/p/250 | E12-11-107 | 11/10/-/250 | GlueX 2 / JEF | 12/200/-/250 | D/B/C | -/5/5/5.5
2024-10-04 | Friday | 2.2 | Physics | Install |  | Run Group L | 11/200/p/250 | E12-11-107 | 11/10/-/250 | GlueX 2 / JEF | 12/200/-/250 | C/D/B/A | -/5/5/5.5
2024-10-05 | Saturday | 2.2 | Physics | Install |  | Run Group L | 11/200/p/250 | E12-11-107 | 11/10/-/250 | GlueX 2 / JEF | 12/200/-/250 | C/D/B/A | -/5/5/5.5
2024-10-06 | Sunday | 2.2 | Physics | Install |  | Run Group L | 11/200/p/250 | E12-11-107 | 11/10/-/250 | GlueX 2 / JEF | 12/200/-/250 | C/D/B/A | -/5/5/5.5
2024-10-07 | Monday | 2.2 | Physics | Install |  | Run Group L | 11/200/p/250 | E12-11-107 | 11/10/-/250 | GlueX 2 / JEF | 12/200/-/250 | C/D/B/A | -/5/5/5.5
2024-10-08 | Tuesday | 2.2 | Physics | Install |  | Run Group L | 11/200/p/250 | E12-11-107 | 11/10/-/250 | GlueX 2 / JEF | 12/200/-/250 | C/D/B/A | -/5/5/5.5
2024-10-09 | Wednesday | 2.2 | Physics | Install |  | Run Group L | 11/200/p/250 | E12-11-107 | 11/10/-/250 | GlueX 2 / JEF | 12/200/-/250 | C/D/B/A | -/5/5/5.5
2024-10-10 | Thursday | 2.2 | Physics | Install |  | Run Group L | 11/200/p/250 | E12-11-107 | 11/10/-/250 | GlueX 2 / JEF | 12/200/-/250 | C/D/B/A | -/5/5/5.5
2024-10-11 | Friday | 2.2 | Physics | Install |  | Run Group L | 11/200/p/250 | E12-11-107 | 11/10/-/250 | GlueX 2 / JEF | 12/200/-/250 | A/B/C/D | -/5/5/5.5
2024-10-12 | Saturday | 2.2 | Physics | Install |  | Run Group L | 11/200/p/250 | E12-11-107 | 11/10/-/250 | GlueX 2 / JEF | 12/200/-/250 | A/B/C/D | -/5/5/5.5
2024-10-13 | Sunday | 2.2 | Physics | Install |  | Run Group L | 11/200/p/250 | E12-11-107 | 11/10/-/250 | GlueX 2 / JEF | 12/200/-/250 | A/B/C/D | -/5/5/5.5
2024-10-14 | Monday | 2.2 | Physics | Install |  | Run Group L | 11/200/p/250 | E12-11-107 | 11/10/-/250 | GlueX 2 / JEF | 12/200/-/250 | A/B/C/D | -/5/5/5.5
2024-10-15 | Tuesday | 2.2 | Physics | Install |  | Run Group L | 11/200/p/250 | E12-11-107 | 11/10/-/250 | GlueX 2 / JEF | 12/200/-/250 | A/B/C/D | -/5/5/5.5
2024-10-16 | Wednesday | 2.2 | Physics | Install |  | Run Group L | 11/200/p/250 | E12-11-107 | 11/10/-/250 | GlueX 2 / JEF | 12/200/-/250 | A/B/C/D | -/5/5/5.5
2024-10-17 | Thursday | 2.2 | Physics | Install |  | Run Group L | 11/200/p/250 | E12-11-107 | 11/10/-/250 | GlueX 2 / JEF | 12/200/-/250 | A/B/C/D | -/5/5/5.5
2024-10-18 | Friday | 2.2 | Physics | Install |  | Run Group L | 11/200/p/250 | E12-11-107 | 11/10/-/250 | GlueX 2 / JEF | 12/200/-/250 | B/A/D/C | -/5/5/5.5
2024-10-19 | Saturday | 2.2 | Physics | Install |  | Run Group L | 11/200/p/250 | E12-11-107 | 11/10/-/250 | GlueX 2 / JEF | 12/200/-/250 | B/A/D/C | -/5/5/5.5
2024-10-20 | Sunday | 2.2 | Physics | Install |  | Run Group L | 11/200/p/250 | E12-11-107 | 11/10/-/250 | GlueX 2 / JEF | 12/200/-/250 | B/A/D/C | -/5/5/5.5
2024-10-21 | Monday | 2.2 | Physics | Install |  | Run Group L | 11/200/p/250 | E12-11-107 | 11/10/-/250 | GlueX 2 / JEF | 12/200/-/250 | B/A/D/C | -/5/5/5.5
2024-10-22 | Tuesday | 2.2 | Physics | Install |  | Run Group L | 11/200/p/250 | E12-11-107 | 11/10/-/250 | GlueX 2 / JEF | 12/200/-/250 | B/A/D/C | -/5/5/5.5
2024-10-23 | Wednesday | 2.2 | Physics | Install |  | Run Group L | 11/200/p/250 | E12-11-107 | 11/10/-/250 | GlueX 2 / JEF | 12/200/-/250 | B/A/D/C | -/5/5/5.5
2024-10-24 | Thursday | 2.2 | Physics | Install |  | Run Group L | 11/200/p/250 | E12-11-107 | 11/10/-/250 | GlueX 2 / JEF | 12/200/-/250 | B/A/D/C | -/5/5/5.5
2024-10-25 | Friday | 2.2 | Physics | Pass change |  | Run Group L | 11/200/p/250 | E12-11-107 | 11/10/-/250 | GlueX 2 / JEF | 12/200/-/250 | C/D/A/B | 3/5/5/5.5
2024-10-26 | Saturday | 2.2 | Physics | E12-07-109 | 6.6/50/p/250 | Run Group L | 11/200/p/250 | E12-11-107 | 11/10/-/250 | GlueX 2 / JEF | 12/200/-/250 | C/D/A/B | 3/5/5/5.5
2024-10-27 | Sunday | 2.2 | Physics | E12-07-109 | 6.6/50/p/250 | Run Group L | 11/200/p/250 | E12-11-107 | 11/10/-/250 | GlueX 2 / JEF | 12/200/-/250 | C/D/A/B | 3/5/5/5.5
2024-10-28 | Monday | 2.2 | Physics | E12-07-109 | 6.6/50/p/250 | Run Group L | 11/200/p/250 | E12-11-107 | 11/10/-/250 | GlueX 2 / JEF | 12/200/-/250 | C/D/A/B | 3/5/5/5.5
2024-10-29 | Tuesday | 2.2 | Physics | E12-07-109 | 6.6/50/p/250 | Run Group L | 11/200/p/250 | E12-11-107 | 11/10/-/250 | GlueX 2 / JEF | 12/200/-/250 | C/D/A/B | 3/5/5/5.5
2024-10-30 | Wednesday | 2.2 | Physics | E12-07-109 | 6.6/50/p/250 | Run Group L | 11/200/p/250 | E12-11-107 | 11/10/-/250 | GlueX 2 / JEF | 12/200/-/250 | C/D/A/B | 3/5/5/5.5
2024-10-31 | Thursday | 2.2 | Physics | E12-07-109 | 6.6/50/p/250 | Run Group L | 11/200/p/250 | E12-11-107 | 11/10/-/250 | GlueX 2 / JEF | 12/200/-/250 | C/D/A/B | 3/5/5/5.5
2024-11-01 | Friday | 2.2 | Physics | E12-07-109 | 6.6/50/p/250 | Run Group L | 11/200/p/250 | E12-11-107 | 11/10/-/250 | GlueX 2 / JEF | 12/200/-/250 | B/C/D/A | 3/5/5/5.5
2024-11-02 | Saturday | 2.2 | Physics | E12-07-109 | 6.6/50/p/250 | Run Group L | 11/200/p/250 | E12-11-107 | 11/10/-/250 | GlueX 2 / JEF | 12/200/-/250 | B/C/D/A | 3/5/5/5.5
2024-11-03 | Sunday | 2.2 | Physics | E12-07-109 | 6.6/50/p/250 | Run Group L | 11/200/p/250 | E12-11-107 | 11/10/-/250 | GlueX 2 / JEF | 12/200/-/250 | B/C/D/A | 3/5/5/5.5
2024-11-04 | Monday | 2.2 | Physics | E12-07-109 | 6.6/50/p/250 | Run Group L | 11/200/p/250 | E12-11-107 | 11/10/-/250 | GlueX 2 / JEF | 12/200/-/250 | B/C/D/A | 3/5/5/5.5
2024-11-05 | Tuesday | 2.2 | Physics | Pass change |  | Run Group L | 11/200/p/250 | E12-11-107 | 11/10/-/250 | GlueX 2 / JEF | 12/200/-/250 | B/C/D/A | 4/5/5/5.5
2024-11-06 | Wednesday | 2.2 | Physics | E12-07-109 | 8.8/50/p/250 | Run Group L | 11/200/p/250 | E12-11-107 | 11/10/-/250 | GlueX 2 / JEF | 12/200/-/250 | B/C/D/A | 4/5/5/5.5
2024-11-07 | Thursday | 2.2 | Physics | E12-07-109 | 8.8/50/p/250 | Run Group L | 11/200/p/250 | E12-11-107 | 11/10/-/250 | GlueX 2 / JEF | 12/200/-/250 | B/C/D/A | 4/5/5/5.5
2024-11-08 | Friday | 2.2 | Physics | E12-07-109 | 8.8/50/p/250 | Run Group L | 11/200/p/250 | E12-11-107 | 11/10/-/250 | GlueX 2 / JEF | 12/200/-/250 | A/B/C/D | 4/5/5/5.5
2024-11-09 | Saturday | 2.2 | Physics | E12-07-109 | 8.8/50/p/250 | Run Group L | 11/200/p/250 | E12-11-107 | 11/10/-/250 | GlueX 2 / JEF | 12/200/-/250 | A/B/C/D | 4/5/5/5.5
2024-11-10 | Sunday | 2.2 | Physics | E12-07-109 | 8.8/50/p/250 | Run Group L | 11/200/p/250 | E12-11-107 | 11/10/-/250 | GlueX 2 / JEF | 12/200/-/250 | A/B/C/D | 4/5/5/5.5
2024-11-11 | Monday | 2.2 | Physics | E12-07-109 | 8.8/50/p/250 | Run Group L | 11/200/p/250 | E12-11-107 | 11/10/-/250 | GlueX 2 / JEF | 12/200/-/250 | A/B/C/D | 4/5/5/5.5
2024-11-12 | Tuesday | 2.2 | Physics | E12-07-109 | 8.8/50/p/250 | Run Group L | 11/200/p/250 | E12-11-107 | 11/10/-/250 | GlueX 2 / JEF | 12/200/-/250 | A/B/C/D | 4/5/5/5.5
2024-11-13 | Wednesday | 2.2 | Physics | E12-07-109 | 8.8/50/p/250 | Run Group L | 11/200/p/250 | E12-11-107 | 11/10/-/250 | GlueX 2 / JEF | 12/200/-/250 | A/B/C/D | 4/5/5/5.5
2024-11-14 | Thursday | 2.2 | Physics | E12-07-109 | 8.8/50/p/250 | Run Group L | 11/200/p/250 | E12-11-107 | 11/10/-/250 | GlueX 2 / JEF | 12/200/-/250 | A/B/C/D | 4/5/5/5.5
2024-11-15 | Friday | 2.2 | Physics | E12-07-109 | 8.8/50/p/250 | Run Group L | 11/200/p/250 | E12-11-107 | 11/10/-/250 | GlueX 2 / JEF | 12/200/-/250 | D/A/B/C | 4/5/5/5.5
2024-11-16 | Saturday | 2.2 | Physics | E12-07-109 | 8.8/50/p/250 | Run Group L | 11/200/p/250 | E12-11-107 | 11/10/-/250 | GlueX 2 / JEF | 12/200/-/250 | D/A/B/C | 4/5/5/5.5
2024-11-17 | Sunday | 2.2 | Physics | E12-07-109 | 8.8/50/p/250 | Run Group L | 11/200/p/250 | E12-11-107 | 11/10/-/250 | GlueX 2 / JEF | 12/200/-/250 | D/A/B/C | 4/5/5/5.5
2024-11-18 | Monday | 2.2 | Physics | E12-07-109 | 8.8/50/p/250 | Run Group L | 11/200/p/250 | E12-11-107 | 11/10/-/250 | GlueX 2 / JEF | 12/200/-/250 | D/A/B/C | 4/5/5/5.5
2024-11-19 | Tuesday | 2.2 | Physics | E12-07-109 | 8.8/50/p/250 | Run Group L | 11/200/p/250 | E12-11-107 | 11/10/-/250 | GlueX 2 / JEF | 12/200/-/250 | D/A/B/C | 4/5/5/5.5
2024-11-20 | Wednesday | 2.2 | Physics | E12-07-109 | 8.8/50/p/250 | Run Group L | 11/200/p/250 | E12-11-107 | 11/10/-/250 | GlueX 2 / JEF | 12/200/-/250 | D/A/B/C | 4/5/5/5.5
2024-11-21 | Thursday | 2.2 | Physics | E12-07-109 | 8.8/50/p/250 | Run Group L | 11/200/p/250 | E12-11-107 | 11/10/-/250 | GlueX 2 / JEF | 12/200/-/250 | D/A/B/C | 4/5/5/5.5
2024-11-22 | Friday | 2.2 | Physics | E12-07-109 | 8.8/50/p/250 | Run Group L | 11/200/p/250 | E12-11-107 | 11/10/-/250 | GlueX 2 / JEF | 12/200/-/250 | C/D/A/B | 4/5/5/5.5
2024-11-23 | Saturday | 2.2 | Physics | E12-07-109 | 8.8/50/p/250 | Run Group L | 11/200/p/250 | E12-11-107 | 11/10/-/250 | GlueX 2 / JEF | 12/200/-/250 | C/D/A/B | 4/5/5/5.5
2024-11-24 | Sunday | 2.2 | Physics | E12-07-109 | 8.8/50/p/250 | Run Group L | 11/200/p/250 | E12-11-107 | 11/10/-/250 | GlueX 2 / JEF | 12/200/-/250 | C/D/A/B | 4/5/5/5.5
2024-11-25 | Monday | 2.2 | Physics | E12-07-109 | 8.8/50/p/250 | Run Group L | 11/200/p/250 | E12-11-107 | 11/10/-/250 | GlueX 2 / JEF | 12/200/-/250 | C/D/A/B | 4/5/5/5.5
2024-11-26 | Tuesday | 2.2 | Physics | E12-07-109 | 8.8/50/p/250 | Run Group L | 11/200/p/250 | E12-11-107 | 11/10/-/250 | GlueX 2 / JEF | 12/200/-/250 | C/D/A/B | 4/5/5/5.5
2024-11-27 | Wednesday | 2.2 | Physics | E12-07-109 | 8.8/50/p/250 | Run Group L | 11/200/p/250 | E12-11-107 | 11/10/-/250 | GlueX 2 / JEF | 12/200/-/250 | C/D/A/B | 4/5/5/5.5
2024-11-28 | Thursday | 2.2 | Physics | E12-07-109 | 8.8/50/p/250 | Run Group L | 11/200/p/250 | E12-11-107 | 11/10/-/250 | GlueX 2 / JEF | 12/200/-/250 | C/D/A/B | 4/5/5/5.5
2024-11-29 | Friday | 2.2 | Physics | E12-07-109 | 8.8/50/p/250 | Run Group L | 11/200/p/250 | E12-11-107 | 11/10/-/250 | GlueX 2 / JEF | 12/200/-/250 | B/C/D/A | 4/5/5/5.5
2024-11-30 | Saturday | 2.2 | Physics | E12-07-109 | 8.8/50/p/250 | Run Group L | 11/200/p/250 | E12-11-107 | 11/10/-/250 | GlueX 2 / JEF | 12/200/-/250 | B/C/D/A | 4/5/5/5.5
2024-12-01 | Sunday | 2.2 | Physics | E12-07-109 | 8.8/50/p/250 | Run Group L | 11/200/p/250 | E12-11-107 | 11/10/-/250 | GlueX 2 / JEF | 12/200/-/250 | B/C/D/A | 4/5/5/5.5
2024-12-02 | Monday | 2.2 | Physics | E12-07-109 | 8.8/50/p/250 | Run Group L | 11/200/p/250 | E12-11-107 | 11/10/-/250 | GlueX 2 / JEF | 12/200/-/250 | B/C/D/A | 4/5/5/5.5
2024-12-03 | Tuesday | 2.2 | Physics | E12-07-109 | 8.8/50/p/250 | Run Group L | 11/200/p/250 | E12-11-107 | 11/10/-/250 | GlueX 2 / JEF | 12/200/-/250 | B/C/D/A | 4/5/5/5.5
2024-12-04 | Wednesday | 2.2 | Physics | E12-07-109 | 8.8/50/p/250 | Run Group L | 11/200/p/250 | E12-11-107 | 11/10/-/250 | GlueX 2 / JEF | 12/200/-/250 | B/C/D/A | 4/5/5/5.5
2024-12-05 | Thursday | 2.2 | Physics | E12-07-109 | 8.8/50/p/250 | Run Group L | 11/200/p/250 | E12-11-107 | 11/10/-/250 | GlueX 2 / JEF | 12/200/-/250 | B/C/D/A | 4/5/5/5.5
2024-12-06 | Friday | 2.2 | Physics | Pass change |  | Run Group L | 11/200/p/250 | E12-11-107 | 11/10/-/250 | GlueX 2 / JEF | 12/200/-/250 | A/B/C/D | 5/5/5/5.5
2024-12-07 | Saturday | 2.2 | Physics | E12-07-109 | 11/50/p/250 | Run Group L | 11/200/p/250 | E12-11-107 | 11/10/-/250 | GlueX 2 / JEF | 12/200/-/250 | A/B/C/D | 5/5/5/5.5
2024-12-08 | Sunday | 2.2 | Physics | E12-07-109 | 11/50/p/250 | Run Group L | 11/200/p/250 | E12-11-107 | 11/10/-/250 | GlueX 2 / JEF | 12/200/-/250 | A/B/C/D | 5/5/5/5.5
2024-12-09 | Monday | 2.2 | Physics | E12-07-109 | 11/50/p/250 | Run Group L | 11/200/p/250 | E12-11-107 | 11/10/-/250 | GlueX 2 / JEF | 12/200/-/250 | A/B/C/D | 5/5/5/5.5
2024-12-10 | Tuesday | 2.2 | Physics | E12-07-109 | 11/50/p/250 | Run Group L | 11/200/p/250 | E12-11-107 | 11/10/-/250 | GlueX 2 / JEF | 12/200/-/250 | A/B/C/D | 5/5/5/5.5
2024-12-11 | Wednesday | 2.2 | Physics | E12-07-109 | 11/50/p/250 | Run Group L | 11/200/p/250 | E12-11-107 | 11/10/-/250 | GlueX 2 / JEF | 12/200/-/250 | A/B/C/D | 5/5/5/5.5
2024-12-12 | Thursday | 2.2 | Physics | E12-07-109 | 11/50/p/250 | Run Group L | 11/200/p/250 | E12-11-107 | 11/10/-/250 | GlueX 2 / JEF | 12/200/-/250 | A/B/C/D | 5/5/5/5.5
2024-12-13 | Friday | 2.2 | Physics | E12-07-109 | 11/50/p/250 | Run Group L | 11/200/p/250 | E12-11-107 | 11/10/-/250 | GlueX 2 / JEF | 12/200/-/250 | B/A/D/C | 5/5/5/5.5
2024-12-14 | Saturday | 2.2 | Physics | E12-07-109 | 11/50/p/250 | Run Group L | 11/200/p/250 | E12-11-107 | 11/10/-/250 | GlueX 2 / JEF | 12/200/-/250 | B/A/D/c | 5/5/5/5.5
2024-12-15 | Sunday | 2.2 | Physics | E12-07-109 | 11/50/p/250 | Run Group L | 11/200/p/250 | E12-11-107 | 11/10/-/250 | GlueX 2 / JEF | 12/200/-/250 | B/A/D/C | 5/5/5/5.5
2024-12-16 | Monday | 2.2 | Physics | E12-07-109 | 11/50/p/250 | Run Group L | 11/200/p/250 | E12-11-107 | 11/10/-/250 | GlueX 2 / JEF | 12/200/-/250 | B/A/D/C | 5/5/5/5.5
2024-12-17 | Tuesday | 2.2 | Physics | E12-07-109 | 11/50/p/250 | Run Group L | 11/200/p/250 | E12-11-107 | 11/10/-/250 | GlueX 2 / JEF | 12/200/-/250 | B/A/D/C | 5/5/5/5.5
2024-12-18 | Wednesday
2024-12-19 | Thursday
2024-12-20 | Friday
2024-12-21 | Saturday
2024-12-22 | Sunday
2024-12-23 | Monday
2024-12-24 | Tuesday
2024-12-25 | Wednesday
2024-12-26 | Thursday
2024-12-27 | Friday
2024-12-28 | Saturday
2024-12-29 | Sunday
2024-12-30 | Monday
2024-12-31 | Tuesday
2025-01-01 | Wednesday
2025-01-02 | Thursday
2025-01-03 | Friday
2025-01-04 | Saturday
2025-01-05 | Sunday
2025-01-06 | Monday | 2.2 | Restore
2025-01-07 | Tuesday | 2.2 | Restore
2025-01-08 | Wednesday | 2.2 | Restore
2025-01-09 | Thursday | 2.2 | Restore
2025-01-10 | Friday | 2.2 | Physics | E12-07-109 | 11/50/p/250 | Run Group L | 11/200/p/250 | E12-06-104 | 6.6/60/-/250 | GlueX 2 / JEF | 12/200/-/250 | B/A/D/C | 5/5/3/5.5
2025-01-11 | Saturday | 2.2 | Physics | E12-07-109 | 11/50/p/250 | Run Group L | 11/200/p/250 | E12-06-104 | 6.6/60/-/250 | GlueX 2 / JEF | 12/200/-/250 | B/A/D/C | 5/5/3/5.5
2025-01-12 | Sunday | 2.2 | Physics | E12-07-109 | 11/50/p/250 | Run Group L | 11/200/p/250 | E12-06-104 | 6.6/60/-/250 | GlueX 2 / JEF | 12/200/-/250 | B/A/D/C | 5/5/3/5.5
2025-01-13 | Monday | 2.2 | Physics | E12-07-109 | 11/50/p/250 | Run Group L | 11/200/p/250 | E12-06-104 | 6.6/60/-/250 | GlueX 2 / JEF | 12/200/-/250 | C/D/A/B | 5/5/3/5.5
2025-01-14 | Tuesday | 2.2 | Physics | E12-07-109 | 11/50/p/250 | Run Group L | 11/200/p/250 | E12-06-104 | 6.6/60/-/250 | GlueX 2 / JEF | 12/200/-/250 | C/D/A/B | 5/5/3/5.5
2025-01-15 | Wednesday | 2.2 | Physics | E12-07-109 | 11/50/p/250 | Run Group L | 11/200/p/250 | E12-06-104 | 6.6/60/-/250 | GlueX 2 / JEF | 12/200/-/250 | C/D/A/B | 5/5/3/5.5
2025-01-16 | Thursday | 2.2 | Physics | E12-07-109 | 11/50/p/250 | Run Group L | 11/200/p/250 | E12-06-104 | 6.6/60/-/250 | GlueX 2 / JEF | 12/200/-/250 | C/D/A/B | 5/5/3/5.5
2025-01-17 | Friday | 2.2 | Physics | E12-07-109 | 11/50/p/250 | Run Group L | 11/200/p/250 | E12-06-104 | 6.6/60/-/250 | GlueX 2 / JEF | 12/200/-/250 | C/D/A/B | 5/5/3/5.5
2025-01-18 | Saturday | 2.2 | Physics | E12-07-109 | 11/50/p/250 | Run Group L | 11/200/p/250 | E12-06-104 | 6.6/60/-/250 | GlueX 2 / JEF | 12/200/-/250 | C/D/A/B | 5/5/3/5.5
2025-01-19 | Sunday | 2.2 | Physics | E12-07-109 | 11/50/p/250 | Run Group L | 11/200/p/250 | E12-06-104 | 6.6/60/-/250 | GlueX 2 / JEF | 12/200/-/250 | C/D/A/B | 5/5/3/5.5
2025-01-20 | Monday | 2.2 | Physics | E12-07-109 | 11/50/p/250 | Run Group L | 11/200/p/250 | E12-06-104 | 6.6/60/-/250 | GlueX 2 / JEF | 12/200/-/250 | B/C/D/A | 5/5/3/5.5
2025-01-21 | Tuesday | 2.2 | Physics | E12-07-109 | 11/50/p/250 | Run Group L | 11/200/p/250 | E12-06-104 | 6.6/60/-/250 | GlueX 2 / JEF | 12/200/-/250 | B/C/D/A | 5/5/3/5.5
2025-01-22 | Wednesday | 2.2 | Physics | E12-07-109 | 11/50/p/250 | Run Group L | 11/200/p/250 | E12-06-104 | 6.6/60/-/250 | GlueX 2 / JEF | 12/200/-/250 | B/C/D/A | 5/5/3/5.5
2025-01-23 | Thursday | 2.2 | Physics | E12-07-109 | 11/50/p/250 | Run Group L | 11/200/p/250 | E12-06-104 | 6.6/60/-/250 | GlueX 2 / JEF | 12/200/-/250 | B/C/D/A | 5/5/3/5.5
2025-01-24 | Friday | 2.2 | Physics | E12-07-109 | 11/50/p/250 | Run Group L | 11/200/p/250 | E12-06-104 | 6.6/60/-/250 | GlueX 2 / JEF | 12/200/-/250 | B/C/D/A | 5/5/3/5.5
2025-01-25 | Saturday | 2.2 | Physics | E12-07-109 | 11/50/p/250 | Run Group L | 11/200/p/250 | E12-06-104 | 6.6/60/-/250 | GlueX 2 / JEF | 12/200/-/250 | B/C/D/A | 5/5/3/5.5
2025-01-26 | Sunday | 2.2 | Physics | E12-07-109 | 11/50/p/250 | Run Group L | 11/200/p/250 | E12-06-104 | 6.6/60/-/250 | GlueX 2 / JEF | 12/200/-/250 | B/C/D/A | 5/5/3/5.5
2025-01-27 | Monday | 2.2 | Physics | E12-07-109 | 11/50/p/250 | Run Group L | 11/200/p/250 | E12-06-104 | 6.6/60/-/250 | GlueX 2 / JEF | 12/200/-/250 | A/B/C/D | 5/5/3/5.5
2025-01-28 | Tuesday | 2.2 | Physics | E12-07-109 | 11/50/p/250 | Pass change |  | Pass change |  | GlueX 2 / JEF | 12/200/-/250 | A/B/C/D | 5/2/4/5.5
2025-01-29 | Wednesday | 2.2 | Physics | E12-07-109 | 11/50/p/250 | Run Group L | 2.2/200/p/250 | E12-06-104 | 8.8/60/-/250 | GlueX 2 / JEF | 12/200/-/250 | A/B/C/D | 5/2/4/5.5
2025-01-30 | Thursday | 2.2 | Physics | E12-07-109 | 11/50/p/250 | Run Group L | 2.2/200/p/250 | E12-06-104 | 8.8/60/-/250 | GlueX 2 / JEF | 12/200/-/250 | A/B/C/D | 5/2/4/5.5
2025-01-31 | Friday | 2.2 | Physics | E12-07-109 | 11/50/p/250 | Pass change |  | E12-06-104 | 8.8/60/-/250 | GlueX 2 / JEF | 12/200/-/250 | A/C/D/B | 5/3/4/5.5
2025-02-01 | Saturday | 2.2 | Physics | E12-07-109 | 11/50/p/250 | E12-23-013 | 6.6/200/-/250 | E12-06-104 | 8.8/60/-/250 | GlueX 2 / JEF | 12/200/-/250 | A/C/D/B | 5/3/4/5.5
2025-02-02 | Sunday | 2.2 | Physics | E12-07-109 | 11/50/p/250 | E12-23-013 | 6.6/200/-/250 | E12-06-104 | 8.8/60/-/250 | GlueX 2 / JEF | 12/200/-/250 | A/C/D/B | 5/3/4/5.5
2025-02-03 | Monday | 2.2 | Physics | E12-07-109 | 11/50/p/250 | E12-23-013 | 6.6/200/-/250 | E12-06-104 | 8.8/60/-/250 | GlueX 2 / JEF | 12/200/-/250 | A/C/D/B | 5/3/4/5.5
2025-02-04 | Tuesday | 2.2 | Physics | E12-07-109 | 11/50/p/250 | E12-23-013 | 6.6/200/-/250 | E12-06-104 | 8.8/60/-/250 | GlueX 2 / JEF | 12/200/-/250 | B/D/A/C | 5/3/4/5.5
2025-02-05 | Wednesday | 2.2 | Physics | E12-07-109 | 11/50/p/250 | E12-23-013 | 6.6/200/-/250 | E12-06-104 | 8.8/60/-/250 | GlueX 2 / JEF | 12/200/-/250 | B/D/A/C | 5/3/4/5.5
2025-02-06 | Thursday | 2.2 | Physics | E12-07-109 | 11/50/p/250 | E12-23-013 | 6.6/200/-/250 | E12-06-104 | 8.8/60/-/250 | GlueX 2 / JEF | 12/200/-/250 | B/D/A/C | 5/3/4/5.5
2025-02-07 | Friday | 2.2 | Physics | E12-07-109 | 11/50/p/250 | E12-23-013 | 6.6/200/-/250 | E12-06-104 | 8.8/60/-/250 | GlueX 2 / JEF | 12/200/-/250 | B/D/A/C | 5/3/4/5.5
2025-02-08 | Saturday | 2.2 | Physics | E12-07-109 | 11/50/p/250 | E12-23-013 | 6.6/200/-/250 | E12-06-104 | 8.8/60/-/250 | GlueX 2 / JEF | 12/200/-/250 | B/D/A/C | 5/3/4/5.5
2025-02-09 | Sunday | 2.2 | Physics | E12-07-109 | 11/50/p/250 | E12-23-013 | 6.6/200/-/250 | E12-06-104 | 8.8/60/-/250 | GlueX 2 / JEF | 12/200/-/250 | B/D/A/C | 5/3/4/5.5
2025-02-10 | Monday | 2.2 | Physics | E12-07-109 | 11/50/p/250 | E12-23-013 | 6.6/200/-/250 | E12-06-104 | 8.8/60/-/250 | GlueX 2 / JEF | 12/200/-/250 | B/D/A/C | 5/3/4/5.5
2025-02-11 | Tuesday | 2.2 | Physics | E12-07-109 | 11/50/p/250 | E12-23-013 | 6.6/200/-/250 | E12-06-104 | 8.8/60/-/250 | GlueX 2 / JEF | 12/200/-/250 | B/D/A/C | 5/3/4/5.5
2025-02-12 | Wednesday | 2.2 | Physics | E12-07-109 | 11/50/p/250 | E12-23-013 | 6.6/200/-/250 | E12-06-104 | 8.8/60/-/250 | GlueX 2 / JEF | 12/200/-/250 | C/D/A/B | 5/3/4/5.5
2025-02-13 | Thursday | 2.2 | Physics | E12-07-109 | 11/50/p/250 | E12-23-013 | 6.6/200/-/250 | E12-06-104 | 8.8/60/-/250 | GlueX 2 / JEF | 12/200/-/250 | C/D/A/B | 5/3/4/5.5
2025-02-14 | Friday | 2.2 | Physics | E12-07-109 | 11/50/p/250 | E12-23-013 | 6.6/200/-/250 | E12-06-104 | 8.8/60/-/250 | GlueX 2 / JEF | 12/200/-/250 | C/D/A/B | 5/3/4/5.5
2025-02-15 | Saturday | 2.2 | Physics | E12-07-109 | 11/50/p/250 | E12-23-013 | 6.6/200/-/250 | E12-06-104 | 8.8/60/-/250 | GlueX 2 / JEF | 12/200/-/250 | C/D/A/B | 5/3/4/5.5
2025-02-16 | Sunday | 2.2 | Physics | E12-07-109 | 11/50/p/250 | E12-23-013 | 6.6/200/-/250 | E12-06-104 | 8.8/60/-/250 | GlueX 2 / JEF | 12/200/-/250 | C/D/A/B | 5/3/4/5.5
2025-02-17 | Monday | 2.2 | Physics | E12-07-109 | 11/50/p/250 | E12-23-013 | 6.6/200/-/250 | Pass change |  | GlueX 2 / JEF | 12/200/-/250 | B/C/D/A | 5/3/5/5.5
2025-02-18 | Tuesday | 2.2 | Physics | E12-07-109 | 11/50/p/250 | E12-23-013 | 6.6/200/-/250 | E12-06-104 | 11/50/-/250 | GlueX 2 / JEF | 12/200/-/250 | B/C/D/A | 5/3/5/5.5
2025-02-19 | Wednesday | 2.2 | Physics | E12-07-109 | 11/50/p/250 | E12-23-013 | 6.6/200/-/250 | E12-06-104 | 11/50/-/250 | GlueX 2 / JEF | 12/200/-/250 | B/C/D/A | 5/3/5/5.5
2025-02-20 | Thursday | 2.2 | Physics | E12-07-109 | 11/50/p/250 | E12-23-013 | 6.6/200/-/250 | E12-06-104 | 11/50/-/250 | GlueX 2 / JEF | 12/200/-/250 | B/C/D/A | 5/3/5/5.5
2025-02-21 | Friday | 2.2 | Physics | E12-07-109 | 11/50/p/250 | E12-23-013 | 6.6/200/-/250 | E12-06-104 | 11/50/-/250 | GlueX 2 / JEF | 12/200/-/250 | B/C/D/A | 5/3/5/5.5
2025-02-22 | Saturday | 2.2 | Physics | E12-07-109 | 11/50/p/250 | E12-23-013 | 6.6/200/-/250 | E12-06-104 | 11/50/-/250 | GlueX 2 / JEF | 12/200/-/250 | B/C/D/A | 5/3/5/5.5
2025-02-23 | Sunday | 2.2 | Physics | E12-07-109 | 11/50/p/250 | E12-23-013 | 6.6/200/-/250 | E12-06-104 | 11/50/-/250 | GlueX 2 / JEF | 12/200/-/250 | B/C/D/A | 5/3/5/5.5
2025-02-24 | Monday | 2.2 | Physics | E12-07-109 | 11/50/p/250 | E12-23-013 | 6.6/200/-/250 | E12-06-104 | 11/50/-/250 | GlueX 2 / JEF | 12/200/-/250 | A/B/C/D | 5/3/5/5.5
2025-02-25 | Tuesday | 2.2 | Physics | E12-07-109 | 11/50/p/250 | E12-23-013 | 6.6/200/-/250 | E12-06-104 | 11/50/-/250 | GlueX 2 / JEF | 12/200/-/250 | A/B/C/D | 5/3/5/5.5
2025-02-26 | Wednesday | 2.2 | Physics | E12-07-109 | 11/50/p/250 | E12-23-013 | 6.6/200/-/250 | E12-06-104 | 11/50/-/250 | GlueX 2 / JEF | 12/200/-/250 | A/B/C/D | 5/3/5/5.5
2025-02-27 | Thursday | 2.2 | Physics | E12-07-109 | 11/50/p/250 | E12-23-013 | 6.6/200/-/250 | E12-06-104 | 11/50/-/250 | GlueX 2 / JEF | 12/200/-/250 | A/B/C/D | 5/3/5/5.5
2025-02-28 | Friday | 2.2 | Physics | E12-07-109 | 11/50/p/250 | E12-23-013 | 6.6/200/-/250 | E12-06-104 | 11/50/-/250 | GlueX 2 / JEF | 12/200/-/250 | A/B/C/D | 5/3/5/5.5
2025-03-01 | Saturday | 2.2 | Physics | E12-07-109 | 11/50/p/250 | E12-23-013 | 6.6/200/-/250 | E12-06-104 | 11/50/-/250 | GlueX 2 / JEF | 12/200/-/250 | A/B/C/D | 5/3/5/5.5
2025-03-02 | Sunday | 2.2 | Physics | E12-07-109 | 11/50/p/250 | E12-23-013 | 6.6/200/-/250 | E12-06-104 | 11/50/-/250 | GlueX 2 / JEF | 12/200/-/250 | A/B/C/D | 5/3/5/5.5
2025-03-03 | Monday | 2.2 | Physics | E12-07-109 | 11/50/p/250 | E12-23-013 | 6.6/200/-/250 | E12-06-104 | 11/50/-/250 | GlueX 2 / JEF | 12/200/-/250 | D/A/B/C | 5/3/5/5.5
2025-03-04 | Tuesday | 2.2 | Physics | E12-07-109 | 11/50/p/250 | E12-23-013 | 6.6/200/-/250 | E12-06-104 | 11/50/-/250 | GlueX 2 / JEF | 12/200/-/250 | D/A/B/C | 5/3/5/5.5
2025-03-05 | Wednesday | 2.2 | Physics | E12-07-109 | 11/50/p/250 | E12-23-013 | 6.6/200/-/250 | E12-06-104 | 11/50/-/250 | GlueX 2 / JEF | 12/200/-/250 | D/A/B/C | 5/3/5/5.5
2025-03-06 | Thursday | 2.2 | Physics | E12-07-109 | 11/50/p/250 | E12-23-013 | 6.6/200/-/250 | E12-06-104 | 11/50/-/250 | GlueX 2 / JEF | 12/200/-/250 | D/A/B/C | 5/3/5/5.5
2025-03-07 | Friday | 2.2 | Physics | E12-07-109 | 11/50/p/250 | E12-23-013 | 6.6/200/-/250 | E12-06-104 | 11/50/-/250 | GlueX 2 / JEF | 12/200/-/250 | D/A/B/C | 5/3/5/5.5
2025-03-08 | Saturday | 2.2 | Physics | E12-07-109 | 11/50/p/250 | E12-23-013 | 6.6/200/-/250 | E12-06-104 | 11/50/-/250 | GlueX 2 / JEF | 12/200/-/250 | D/A/B/C | 5/3/5/5.5
2025-03-09 | Sunday | 2.2 | Physics | E12-07-109 | 11/50/p/250 | E12-23-013 | 6.6/200/-/250 | E12-06-104 | 11/50/-/250 | GlueX 2 / JEF | 12/200/-/250 | D/A/B/C | 5/3/5/5.5
2025-03-10 | Monday | 2.2 | Physics | E12-07-109 | 11/50/p/250 | Reconfigure |  | E12-06-104 | 11/50/-/250 | GlueX 2 / JEF | 12/200/-/250 | A/B/C/D | 5/3/5/5.5
2025-03-11 | Tuesday | 2.2 | Physics | E12-07-109 | 11/50/p/250 | Reconfigure |  | E12-06-104 | 11/50/-/250 | GlueX 2 / JEF | 12/200/-/250 | A/B/C/D | 5/3/5/5.5
2025-03-12 | Wednesday | 2.2 | Physics | E12-07-109 | 11/50/p/250 | Reconfigure |  | Pass change |  | GlueX 2 / JEF | 12/200/-/250 | A/B/C/D | 5/-/3/5.5
2025-03-13 | Thursday | 2.2 | Physics | E12-07-109 | 11/50/p/250 | Reconfigure |  | E12-06-104 | 6.6/60/-/250 | GlueX 2 / JEF | 12/200/-/250 | A/B/C/D | 5/-/3/5.5
2025-03-14 | Friday | 2.2 | Physics | E12-07-109 | 11/50/p/250 | Reconfigure |  | E12-06-104 | 6.6/60/-/250 | GlueX 2 / JEF | 12/200/-/250 | A/B/C/D | 5/-/3/5.5
2025-03-15 | Saturday | 2.2 | Physics | E12-07-109 | 11/50/p/250 | Reconfigure |  | E12-06-104 | 6.6/60/-/250 | GlueX 2 / JEF | 12/200/-/250 | A/B/C/D | 5/-/3/5.5
2025-03-16 | Sunday | 2.2 | Physics | E12-07-109 | 11/50/p/250 | Reconfigure |  | E12-06-104 | 6.6/60/-/250 | GlueX 2 / JEF | 12/200/-/250 | A/B/C/D | 5/-/3/5.5
2025-03-17 | Monday | 2.2 | Physics | E12-07-109 | 11/50/p/250 | Reconfigure |  | E12-06-104 | 6.6/60/-/250 | GlueX 2 / JEF | 12/200/-/250 | D/A/B/C | 5/-/3/5.5
2025-03-18 | Tuesday | 2.2 | Physics | E12-07-109 | 11/50/p/250 | Reconfigure |  | E12-06-104 | 6.6/60/-/250 | GlueX 2 / JEF | 12/200/-/250 | D/A/B/C | 5/-/3/5.5
2025-03-19 | Wednesday | 2.2 | Physics | E12-07-109 | 11/50/p/250 | Run Group K | 8.8/200/-/250 | E12-06-104 | 6.6/60/-/250 | GlueX 2 / JEF | 12/200/-/250 | D/B/C | 5/4/3/5.5
2025-03-20 | Thursday | 2.2 | Physics | E12-07-109 | 11/50/p/250 | Run Group K | 8.8/200/-/250 | E12-06-104 | 6.6/60/-/250 | GlueX 2 / JEF | 12/200/-/250 | D/B/C | 5/4/3/5.5
2025-03-21 | Friday | 2.2 | Physics | E12-07-109 | 11/50/p/250 | Run Group K | 8.8/200/-/250 | E12-06-104 | 6.6/60/-/250 | GlueX 2 / JEF | 12/200/-/250 | D/B/C | 5/4/3/5.5
2025-03-22 | Saturday | 2.2 | Physics | E12-07-109 | 11/50/p/250 | Run Group K | 8.8/200/-/250 | E12-06-104 | 6.6/60/-/250 | GlueX 2 / JEF | 12/200/-/250 | D/B/C | 5/4/3/5.5
2025-03-23 | Sunday | 2.2 | Physics | E12-07-109 | 11/50/p/250 | Run Group K | 8.8/200/-/250 | E12-06-104 | 6.6/60/-/250 | GlueX 2 / JEF | 12/200/-/250 | D/B/C | 5/4/3/5.5
2025-03-24 | Monday | 2.2 | Physics | E12-07-109 | 11/50/p/250 | Run Group K | 8.8/200/-/250 | E12-06-104 | 6.6/60/-/250 | GlueX 2 / JEF | 12/200/-/250 | C/D/B | 5/4/3/5.5
2025-03-25 | Tuesday | 2.2 | Physics | E12-07-109 | 11/50/p/250 | Run Group K | 8.8/200/-/250 | E12-06-104 | 6.6/60/-/250 | GlueX 2 / JEF | 12/200/-/250 | C/D/B | 5/4/3/5.5
2025-03-26 | Wednesday | 2.2 | Physics | E12-07-109 | 11/50/p/250 | Run Group K | 8.8/200/-/250 | E12-06-104 | 6.6/60/-/250 | GlueX 2 / JEF | 12/200/-/250 | C/D/B | 5/4/3/5.5
2025-03-27 | Thursday | 2.2 | Physics | E12-07-109 | 11/50/p/250 | Run Group K | 8.8/200/-/250 | E12-06-104 | 6.6/60/-/250 | GlueX 2 / JEF | 12/200/-/250 | C/D/B | 5/4/3/5.5
2025-03-28 | Friday | 2.2 | Physics | E12-07-109 | 11/50/p/250 | Run Group K | 8.8/200/-/250 | E12-06-104 | 6.6/60/-/250 | GlueX 2 / JEF | 12/200/-/250 | C/D/B | 5/4/3/5.5
2025-03-29 | Saturday | 2.2 | Physics | E12-07-109 | 11/50/p/250 | Run Group K | 8.8/200/-/250 | E12-06-104 | 6.6/60/-/250 | GlueX 2 / JEF | 12/200/-/250 | C/D/B | 5/4/3/5.5
2025-03-30 | Sunday | 2.2 | Physics | E12-07-109 | 11/50/p/250 | Run Group K | 8.8/200/-/250 | E12-06-104 | 6.6/60/-/250 | GlueX 2 / JEF | 12/200/-/250 | C/D/B | 5/4/3/5.5
2025-03-31 | Monday | 2.2 | Physics | E12-07-109 | 11/50/p/250 | Run Group K | 8.8/200/-/250 | E12-06-104 | 6.6/60/-/250 | GlueX 2 / JEF | 12/200/-/250 | B/D/C | 5/4/3/5.5
2025-04-01 | Tuesday | 2.2 | Physics | E12-07-109 | 11/50/p/250 | Run Group K | 8.8/200/-/250 | E12-06-104 | 6.6/60/-/250 | GlueX 2 / JEF | 12/200/-/250 | B/D/C | 5/4/3/5.5
2025-04-02 | Wednesday | 2.2 | Physics | E12-07-109 | 11/50/p/250 | Run Group K | 8.8/200/-/250 | E12-06-104 | 6.6/60/-/250 | GlueX 2 / JEF | 12/200/-/250 | B/A/D | 5/4/3/5.5
2025-04-03 | Thursday | 2.2 | Physics | E12-07-109 | 11/50/p/250 | Run Group K | 8.8/200/-/250 | E12-06-104 | 6.6/60/-/250 | GlueX 2 / JEF | 12/200/-/250 | B/C/D | 5/4/3/5.5
2025-04-04 | Friday | 2.2 | Physics | E12-07-109 | 11/50/p/250 | Run Group K | 8.8/200/-/250 | E12-06-104 | 6.6/60/-/250 | GlueX 2 / JEF | 12/200/-/250 | B/C/D | 5/4/3/5.5
2025-04-05 | Saturday | 2.2 | Physics | E12-07-109 | 11/50/p/250 | Run Group K | 8.8/200/-/250 | Reconfigure |  | GlueX 2 / JEF | 12/200/-/250 | B/C/D | 5/4/3/5.5
2025-04-06 | Sunday | 2.2 | Physics | E12-07-109 | 11/50/p/250 | Run Group K | 8.8/200/-/250 | Pass change |  | GlueX 2 / JEF | 12/200/-/250 | B/C/D | 5/4/3/5.5
2025-04-07 | Monday | 2.2 | Physics | TBD |  | Run Group K | 8.8/200/p/250 | E12-06-107 | 11/80/-/250 | GlueX 2 / JEF | 12/200/-/250 | D/C/B | -/4/5/5.5
2025-04-08 | Tuesday | 2.2 | Physics | TBD |  | Run Group K | 8.8/200/p/250 | E12-06-107 | 11/80/-/250 | GlueX 2 / JEF | 12/200/-/250 | D/C/B | -/4/5/5.5
2025-04-09 | Wednesday | 2.2 | Physics | TBD |  | Run Group K | 8.8/200/p/250 | E12-06-107 | 11/80/-/250 | GlueX 2 / JEF | 12/200/-/250 | D/C/B | -/4/5/5.5
2025-04-10 | Thursday | 2.2 | Physics | TBD |  | Run Group K | 8.8/200/p/250 | E12-06-107 | 11/80/-/250 | GlueX 2 / JEF | 12/200/-/250 | D/C/B | -/4/5/5.5
2025-04-11 | Friday | 2.2 | Physics | TBD |  | Run Group K | 8.8/200/p/250 | E12-06-107 | 11/80/-/250 | GlueX 2 / JEF | 12/200/-/250 | D/C/B | -/4/5/5.5
2025-04-12 | Saturday | 2.2 | Physics | TBD |  | Run Group K | 8.8/200/p/250 | E12-06-107 | 11/80/-/250 | GlueX 2 / JEF | 12/200/-/250 | D/C/B | -/4/5/5.5
2025-04-13 | Sunday | 2.2 | Physics | TBD |  | Run Group K | 8.8/200/p/250 | E12-06-107 | 11/80/-/250 | GlueX 2 / JEF | 12/200/-/250 | D/C/B | -/4/5/5.5
2025-04-14 | Monday | 2.2 | Physics | TBD |  | Run Group K | 8.8/200/p/250 | E12-06-107 | 11/80/-/250 | GlueX 2 / JEF | 12/200/-/250 | B/C/D | -/4/5/5.5
2025-04-15 | Tuesday | 2.2 | Physics | TBD |  | Run Group K | 8.8/200/p/250 | E12-06-107 | 11/80/-/250 | GlueX 2 / JEF | 12/200/-/250 | B/C/D | -/4/5/5.5
2025-04-16 | Wednesday | 2.2 | Physics | TBD |  | Run Group K | 8.8/200/p/250 | E12-06-107 | 11/80/-/250 | GlueX 2 / JEF | 12/200/-/250 | B/C/D | -/4/5/5.5
2025-04-17 | Thursday | 2.2 | Physics | TBD |  | Run Group K | 8.8/200/p/250 | E12-06-107 | 11/80/-/250 | GlueX 2 / JEF | 12/200/-/250 | B/C/D | -/4/5/5.5
2025-04-18 | Friday | 2.2 | Physics | TBD |  | Run Group K | 8.8/200/p/250 | E12-06-107 | 11/80/-/250 | GlueX 2 / JEF | 12/200/-/250 | B/C/D | -/4/5/5.5
2025-04-19 | Saturday | 2.2 | Physics | TBD |  | Run Group K | 8.8/200/p/250 | E12-06-107 | 11/80/-/250 | GlueX 2 / JEF | 12/200/-/250 | B/C/D | -/4/5/5.5
2025-04-20 | Sunday | 2.2 | Physics | TBD |  | Run Group K | 8.8/200/p/250 | E12-06-107 | 11/80/-/250 | GlueX 2 / JEF | 12/200/-/250 | B/C/D | -/4/5/5.5
2025-04-21 | Monday | 2.2 | Physics | TBD |  | Run Group K | 8.8/200/p/250 | E12-06-107 | 11/80/-/250 | GlueX 2 / JEF | 12/200/-/250 | D/B/C | -/4/5/5.5
2025-04-22 | Tuesday | 2.2 | Physics | TBD |  | Run Group K | 8.8/200/p/250 | E12-06-107 | 11/80/-/250 | GlueX 2 / JEF | 12/200/-/250 | D/B/C | -/4/5/5.5
2025-04-23 | Wednesday | 2.2 | Physics | TBD |  | Run Group K | 8.8/200/p/250 | E12-06-107 | 11/80/-/250 | GlueX 2 / JEF | 12/200/-/250 | D/B/C | -/4/5/5.5
2025-04-24 | Thursday | 2.2 | Physics | TBD |  | Run Group K | 8.8/200/p/250 | E12-06-107 | 11/80/-/250 | GlueX 2 / JEF | 12/200/-/250 | D/B/C | -/4/5/5.5
2025-04-25 | Friday | 2.2 | Physics | TBD |  | Run Group K | 8.8/200/p/250 | E12-06-107 | 11/80/-/250 | GlueX 2 / JEF | 12/200/-/250 | D/B/C | -/4/5/5.5
2025-04-26 | Saturday | 2.2 | Physics | TBD |  | Run Group K | 8.8/200/p/250 | E12-06-107 | 11/80/-/250 | GlueX 2 / JEF | 12/200/-/250 | D/B/C | -/4/5/5.5
2025-04-27 | Sunday | 2.2 | Physics | TBD |  | Run Group K | 8.8/200/p/250 | E12-06-107 | 11/80/-/250 | GlueX 2 / JEF | 12/200/-/250 | D/B/C | -/4/5/5.5
2025-04-28 | Monday | 2.2 | Physics | TBD |  | Run Group K | 8.8/200/p/250 | E12-06-107 | 11/80/-/250 | GlueX 2 / JEF | 12/200/-/250 | C/D/B | -/4/5/5.5
2025-04-29 | Tuesday | 2.2 | Physics | TBD |  | Run Group K | 8.8/200/p/250 | E12-06-107 | 11/80/-/250 | GlueX 2 / JEF | 12/200/-/250 | C/D/B | -/4/5/5.5
2025-04-30 | Wednesday | 2.2 | Physics | TBD |  | Run Group K | 8.8/200/p/250 | E12-06-107 | 11/80/-/250 | GlueX 2 / JEF | 12/200/-/250 | C/D/B | -/4/5/5.5
2025-05-01 | Thursday | 2.2 | Physics | TBD |  | Run Group K | 8.8/200/p/250 | E12-06-107 | 11/80/-/250 | GlueX 2 / JEF | 12/200/-/250 | C/D/B | -/4/5/5.5
2025-05-02 | Friday | 2.2 | Physics | TBD |  | Run Group K | 8.8/200/p/250 | E12-06-107 | 11/80/-/250 | GlueX 2 / JEF | 12/200/-/250 | C/D/B | -/4/5/5.5
2025-05-03 | Saturday | 2.2 | Physics | TBD |  | Run Group K | 8.8/200/p/250 | E12-06-107 | 11/80/-/250 | GlueX 2 / JEF | 12/200/-/250 | C/D/B | -/4/5/5.5
2025-05-04 | Sunday | 2.2 | Physics | TBD |  | Run Group K | 8.8/200/p/250 | E12-06-107 | 11/80/-/250 | GlueX 2 / JEF | 12/200/-/250 | C/D/B | -/4/5/5.5
2025-05-05 | Monday | 2.2 | Physics | TBD |  | Run Group K | 8.8/200/p/250 | E12-06-107 | 11/80/-/250 | GlueX 2 / JEF | 12/200/-/250 | B/C/D | -/4/5/5.5
2025-05-06 | Tuesday | 2.2 | Physics | TBD |  | Run Group K | 8.8/200/p/250 | E12-06-107 | 11/80/-/250 | GlueX 2 / JEF | 12/200/-/250 | B/C/D | -/4/5/5.5
2025-05-07 | Wednesday | 2.2 | Physics | TBD |  | Run Group K | 8.8/200/p/250 | E12-06-107 | 11/80/-/250 | GlueX 2 / JEF | 12/200/-/250 | B/C/D | -/4/5/5.5
2025-05-08 | Thursday | 2.2 | Physics | TBD |  | Run Group K | 8.8/200/p/250 | E12-06-107 | 11/80/-/250 | GlueX 2 / JEF | 12/200/-/250 | B/C/D | -/4/5/5.5
2025-05-09 | Friday | 2.2 | Physics | TBD |  | Run Group K | 8.8/200/p/250 | E12-06-107 | 11/80/-/250 | GlueX 2 / JEF | 12/200/-/250 | B/C/D | -/4/5/5.5
2025-05-10 | Saturday | 2.2 | Physics | TBD |  | Run Group K | 8.8/200/p/250 | E12-06-107 | 11/80/-/250 | GlueX 2 / JEF | 12/200/-/250 | B/C/D | -/4/5/5.5
2025-05-11 | Sunday | 2.2 | Physics | TBD |  | Run Group K | 8.8/200/p/250 | E12-06-107 | 11/80/-/250 | GlueX 2 / JEF | 12/200/-/250 | B/C/D | -/4/5/5.5
2025-05-12 | Monday | 2.2 | Physics | TBD |  | Run Group K | 8.8/200/p/250 | E12-06-107 | 11/80/-/250 | GlueX 2 / JEF | 12/200/-/250 | B/C/D | -/4/5/5.5
2025-05-13 | Tuesday | 2.2 | Physics | TBD |  | Run Group K | 8.8/200/p/250 | E12-06-107 | 11/80/-/250 | GlueX 2 / JEF | 12/200/-/250 | B/C/D | -/4/5/5.5
2025-05-14 | Wednesday | 2.2 | Physics | TBD |  | Run Group K | 8.8/200/p/250 | E12-06-107 | 11/80/-/250 | GlueX 2 / JEF | 12/200/-/250 | B/C/D | -/4/5/5.5
2025-05-15 | Thursday | 2.2 | Physics | TBD |  | Run Group K | 8.8/200/p/250 | E12-06-107 | 11/80/-/250 | GlueX 2 / JEF | 12/200/-/250 | B/C/D | -/4/5/5.5
2025-05-16 | Friday | 2.2 | Physics | TBD |  | Run Group K | 8.8/200/p/250 | TBD |  | GlueX 2 / JEF | 12/200/-/250 | B/C/D | -/4/5/5.5
2025-05-17 | Saturday | 2.2 | Physics | TBD |  | Run Group K | 8.8/200/p/250 | TBD |  | GlueX 2 / JEF | 12/200/-/250 | B/C/D | -/4/5/5.5
2025-05-18 | Sunday | 2.2 | Physics | TBD |  | Run Group K | 8.8/200/p/250 | TBD |  | GlueX 2 / JEF | 12/200/-/250 | B/C/D | -/4/5/5.5
2025-05-19 | Monday